## Sheet
Stakeholder | EpicID | EPIC TITLE | EPIC DESCRIPTION | Story ID | Story Title | Story Description | Story Acceptance Criteria | Task ID | Task Description | Internal Estimated Hours | MASTER OF CODE HOURS | Cost
Doctors | E001 | User Authentication and Account Management | Enable doctors to register and log in with OTP mobile verification and email verification. Allow doctors to manage their profile information, including name, phone number, email, and profile picture. | S001 | Doctor Registration | As a doctor, I want to register with my name, email, phone number, and password so that I can create an account on the platform. | Given that I am a doctor, when I provide my name, email, phone number, and password, then I should be able to create an account. Given that I have registered, when I submit my details, then I should receive an email and OTP for verification. | T001 | Create a registration form on the frontend with fields for name, email, phone number, and password. | 0.55
[8 empty] | T002 | Implement form validation to ensure all fields are filled out correctly and the email and phone number follow the correct format. | 0.55
[8 empty] | T003 | Develop a backend API endpoint in Flask to handle the registration form submission. The endpoint should accept name, email, phone number, and password as inputs. | 1.2
[8 empty] | T004 | Hash the password using a secure hashing algorithm before storing it in the database. | 0.55
[8 empty] | T005 | Store the doctor's registration details (name, email, phone number, hashed password) in the AWS database. | 1.2
[8 empty] | T006 | Generate an OTP for phone verification and store it temporarily in the database associated with the doctor's phone number. | 1.2
[8 empty] | T007 | Send an email to the doctor with a verification link using an email service (e.g., AWS SES). The link should include a token for email verification. | 0.55
[8 empty] | T008 | Send an SMS to the doctor's phone number with the OTP using an SMS service (e.g., AWS SNS). | 0.55
[8 empty] | T009 | Develop a backend API endpoint in Flask to handle email verification. The endpoint should accept the token from the verification link and mark the email as verified in the database. | 1.2
[8 empty] | T010 | Develop a backend API endpoint in Flask to handle OTP verification. The endpoint should accept the OTP and the phone number, validate the OTP, and mark the phone number as verified in the database. | 1.2
[8 empty] | T011 | Create a frontend page for OTP verification where the doctor can enter the OTP received on their phone. | 0.55
[8 empty] | T012 | Create a frontend page for email verification confirmation that informs the doctor their email has been successfully verified. | 0.25
[8 empty] | T013 | Implement error handling and user feedback for cases where the registration, email verification, or OTP verification fails. | 1.2
[8 empty] | T014 | Write unit and integration tests for the registration, email verification, and OTP verification functionalities to ensure they work as expected. | 1.2
|  |  |  | S002 | Email Verification | As a doctor, I want to verify my email address so that I can confirm my account registration. | Given that I have registered, when I receive an email with a verification link, then I should be able to click the link to verify my email address. Given that I click the verification link, when my email is verified, then I should receive a confirmation message. | T015 | Create a database schema to store email verification tokens, including fields for doctor ID, token, and expiration time. | 0.55
[8 empty] | T016 | Implement a function to generate a unique email verification token and store it in the database. Inputs: doctor_id, Outputs: token. | 0.55
[8 empty] | T017 | Develop an API endpoint to trigger the sending of the verification email. Inputs: doctor_id, email, token, Outputs: success/failure message. | 0.55
[8 empty] | T018 | Integrate an email service (e.g., AWS SES) to send verification emails containing the unique token link to the doctor's registered email address. | 1.2
[8 empty] | T019 | Create a verification link handler endpoint that verifies the token from the email link. Inputs: token, Outputs: success/failure message. | 1.2
[8 empty] | T020 | Implement logic in the verification link handler to update the doctor's account status to 'verified' upon successful token validation. | 1.2
[8 empty] | T021 | Develop a function to send a confirmation email to the doctor once their email has been successfully verified. Inputs: email, Outputs: success/failure message. | 0.55
[8 empty] | T022 | Create unit tests to ensure the email verification token generation, storage, and validation processes work correctly. | 1.2
[8 empty] | T023 | Create integration tests to verify the complete flow of email verification, including sending the verification email, clicking the link, and receiving the confirmation message. | 1.2
[8 empty] | T024 | Update the front-end to display appropriate messages and prompts for email verification, including instructions to check the email and confirmation of successful verification. | 0.55
|  |  |  | S003 | OTP Mobile Verification | As a doctor, I want to verify my phone number using an OTP so that I can secure my account. | Given that I have registered, when I receive an OTP on my mobile phone, then I should be able to enter the OTP on the platform. Given that I enter the correct OTP, when I submit it, then my phone number should be verified. | T025 | Create a database schema to store OTPs and their expiration times associated with doctor accounts. | 1.2
[8 empty] | T026 | Implement an API endpoint to generate and send OTP to the doctor's registered mobile number using an SMS service (e.g., AWS SNS). | 1.2
[8 empty] | T027 | Develop a function to generate a random OTP and store it in the database with an expiration time. | 0.55
[8 empty] | T028 | Create a frontend form for OTP input where doctors can enter the OTP they received on their mobile phone. | 0.55
[8 empty] | T029 | Implement an API endpoint to verify the OTP entered by the doctor against the stored OTP in the database. | 1.2
[8 empty] | T030 | Develop a function to check the validity of the OTP (correct OTP and not expired). | 0.55
[8 empty] | T031 | Update the doctor's account status to 'verified' upon successful OTP verification. | 0.55
[8 empty] | T032 | Create error handling for incorrect or expired OTP entries and provide appropriate feedback to the user. | 0.55
[8 empty] | T033 | Send a confirmation message to the doctor upon successful phone number verification. | 0.55
[8 empty] | T034 | Write unit tests for OTP generation, storage, and verification functions to ensure they work as expected. | 1.2
[8 empty] | T035 | Integrate the OTP verification process into the existing registration flow. | 1.2
|  |  |  | S004 | Doctor Login | As a doctor, I want to log in using my registered email and password so that I can access my account. | Given that I have registered and verified my account, when I enter my email and password, then I should be able to log in. Given that I enter incorrect login details, when I attempt to log in, then I should receive an error message. | T036 | Create a login endpoint in Flask that accepts email and password as inputs. | 0.55
[8 empty] | T037 | Implement a function to validate the email and password against the database. | 0.55
[8 empty] | T038 | Set up error handling to return an appropriate error message if the email or password is incorrect. | 0.55
[8 empty] | T039 | Ensure that the login endpoint returns a success message and a session token if the email and password are correct. | 0.55
[8 empty] | T040 | Implement session management to maintain user sessions securely. | 1.2
[8 empty] | T041 | Create a function to check if the user's account is verified (both email and phone) before allowing login. | 0.55
[8 empty] | T042 | Write unit tests to verify that the login endpoint works correctly with valid credentials. | 0.55
[8 empty] | T043 | Write unit tests to verify that the login endpoint returns an error message with invalid credentials. | 0.55
[8 empty] | T044 | Integrate logging to record login attempts and their outcomes for security monitoring. | 0.55
[8 empty] | T045 | Update the user interface to include a login form with fields for email and password. | 0.55
[8 empty] | T046 | Ensure that the login form properly handles and displays error messages returned by the backend. | 0.55
[8 empty] | T047 | Deploy the updated login functionality to the development environment and perform end-to-end testing. | 0.55
|  |  |  | S005 | Profile Management | As a doctor, I want to manage my profile information, including name, phone number, email, and profile picture, so that I can keep my account details up to date. | Given that I am logged in, when I navigate to the profile management section, then I should be able to view my current profile information. Given that I am in the profile management section, when I update my name, phone number, email, or profile picture, then the changes should be saved and reflected in my profile. | T048 | Create a profile management section in the doctor dashboard where doctors can view and update their profile information. | 1.2
[8 empty] | T049 | Implement a backend API endpoint to retrieve the current profile information of the logged-in doctor. | 0.55
[8 empty] | T050 | Develop a frontend form in the profile management section to display the current profile information (name, phone number, email, and profile picture) of the doctor. | 0.55
[8 empty] | T051 | Implement input fields and validation for updating the name, phone number, email, and profile picture in the profile management form. | 0.55
[8 empty] | T052 | Create a backend API endpoint to handle profile updates, ensuring that changes to name, phone number, email, and profile picture are saved to the database. | 1.2
[8 empty] | T053 | Integrate the profile update API endpoint with the frontend form to submit changes and update the doctor's profile information. | 1.2
[8 empty] | T054 | Implement a mechanism to send an OTP to the doctor's new phone number for verification when the phone number is updated. | 1.2
[8 empty] | T055 | Implement a mechanism to send a verification email to the doctor's new email address when the email is updated. | 0.55
[8 empty] | T056 | Ensure that the profile picture upload functionality supports image validation and storage in a secure location (e.g., AWS S3). | 1.2
[8 empty] | T057 | Develop a notification system to inform the doctor of successful profile updates and any required verification steps for phone number and email changes. | 1.2
[8 empty] | T058 | Test the entire profile management workflow to ensure that profile information is correctly retrieved, updated, and reflected in the doctor's profile. | 1.2
|  |  |  | S006 | Password Reset | As a doctor, I want to reset my password if I forget it so that I can regain access to my account. | Given that I am on the login page, when I click the 'Forgot Password' link, then I should be prompted to enter my registered email. Given that I enter my registered email, when I submit it, then I should receive a password reset link via email. Given that I receive the password reset link, when I click the link and enter a new password, then my password should be updated, and I should be able to log in with the new password. | T059 | Create a 'Forgot Password' link on the login page. | 0.25
[8 empty] | T060 | Develop a form to prompt the user to enter their registered email when the 'Forgot Password' link is clicked. | 0.55
[8 empty] | T061 | Implement backend logic to handle the submission of the registered email and generate a password reset token. | 1.2
[8 empty] | T062 | Set up an email service to send the password reset link to the user's registered email address. | 1.2
[8 empty] | T063 | Create a password reset page where users can enter their new password. | 1.2
[8 empty] | T064 | Implement backend logic to verify the password reset token and update the user's password in the database. | 1.2
[8 empty] | T065 | Add validation to ensure the new password meets security requirements (e.g., minimum length, complexity). | 0.55
[8 empty] | T066 | Develop a confirmation message to inform the user that their password has been successfully reset. | 0.25
[8 empty] | T067 | Ensure that the user can log in with the new password after resetting it. | 0.55
[8 empty] | T068 | Write unit and integration tests to verify the functionality of the password reset process. | 1.2
[8 empty] | T069 | Deploy the password reset feature to the staging environment for user acceptance testing. | 0.55
[8 empty] | T070 | Update the user documentation to include instructions on how to reset the password. | 0.25
| E002 | Patient Management | Provide doctors with a list of patients who have granted access via QR code. Allow doctors to access detailed profiles, including visit and consultation histories, of each patient. | S007 | View List of Patients | As a doctor, I want to view a list of patients who have granted access via QR code so that I can easily manage and access their profiles. | Given that I am logged in as a doctor, when I navigate to the patient management section, I should see a list of patients who have granted access via QR code. Each patient entry in the list should display the patient's name and a brief summary of their latest visit. The list should be sortable by patient name and date of last visit. | T071 | Create a 'Patient Management' section in the doctor dashboard where doctors can navigate to view the list of patients. | 1.2
[8 empty] | T072 | Develop a backend API endpoint to fetch the list of patients who have granted access via QR code. The endpoint should return patient details including name and a summary of their latest visit. | 1.2
[8 empty] | T073 | Implement the frontend logic to call the backend API and display the list of patients in the 'Patient Management' section. | 1.2
[8 empty] | T074 | Ensure each patient entry in the list displays the patient's name and a brief summary of their latest visit. | 0.55
[8 empty] | T075 | Add sorting functionality to the patient list, allowing it to be sorted by patient name and date of last visit. | 0.55
[8 empty] | T076 | Implement user authentication checks to ensure that only logged-in doctors can access the 'Patient Management' section. | 0.55
[8 empty] | T077 | Design the UI for the 'Patient Management' section, ensuring it is user-friendly and consistent with the overall application design. | 1.2
[8 empty] | T078 | Write unit tests for the backend API to ensure it correctly fetches and returns the list of patients. | 0.55
[8 empty] | T079 | Write integration tests to verify that the frontend correctly displays the patient list and supports sorting by name and date of last visit. | 1.2
[8 empty] | T080 | Conduct user acceptance testing with a sample group of doctors to ensure the 'Patient Management' section meets their needs and the acceptance criteria. | 1.2
|  |  |  | S008 | Access Detailed Patient Profiles | As a doctor, I want to access detailed profiles of patients so that I can review their medical history and provide better care. | Given that I am logged in as a doctor, when I click on a patient from the list, I should be taken to a detailed profile page of that patient. The profile page should display the patient's personal information, visit history, and consultation history. The profile page should allow me to navigate back to the list of patients. | T081 | Create a Flask route to handle the request for accessing a patient's detailed profile page. This route should be accessible only to logged-in doctors. | 0.55
[8 empty] | T082 | Develop a function to retrieve the patient's personal information from the database using the patient's ID. Ensure the function returns the data in a structured format. | 0.55
[8 empty] | T083 | Develop a function to retrieve the patient's visit history from the database using the patient's ID. Ensure the function returns the data in a structured format. | 0.55
[8 empty] | T084 | Develop a function to retrieve the patient's consultation history from the database using the patient's ID. Ensure the function returns the data in a structured format. | 0.55
[8 empty] | T085 | Create a template for the detailed profile page that displays the patient's personal information, visit history, and consultation history. Ensure the template is user-friendly and follows the UI guidelines. | 1.2
[8 empty] | T086 | Integrate the functions for retrieving personal information, visit history, and consultation history into the Flask route. Ensure the data is passed to the template for rendering. | 1.2
[8 empty] | T087 | Implement navigation functionality on the detailed profile page to allow doctors to navigate back to the list of patients. Ensure the navigation is intuitive and user-friendly. | 0.55
[8 empty] | T088 | Add authentication and authorization checks to ensure that only logged-in doctors can access the detailed profile page. Implement error handling for unauthorized access. | 1.2
[8 empty] | T089 | Write unit tests to verify the correctness of the functions for retrieving personal information, visit history, and consultation history from the database. | 0.55
[8 empty] | T090 | Write integration tests to ensure that the detailed profile page correctly displays the patient's information and allows navigation back to the list of patients. | 1.2
|  |  |  | S009 | View Visit History | As a doctor, I want to view the visit history of a patient so that I can understand their past medical interactions and conditions. | Given that I am on a patient's profile page, when I click on the 'Visit History' tab, I should see a chronological list of all past visits. Each visit entry should include the date, summary of the visit, and any relevant notes or observations. I should be able to click on each visit entry to view more detailed information. | T091 | Create a 'Visit History' tab on the patient's profile page. | 0.55
[8 empty] | T092 | Develop a backend endpoint to fetch the visit history for a specific patient from the database. | 1.2
[8 empty] | T093 | Implement the frontend logic to call the backend endpoint and retrieve the visit history data when the 'Visit History' tab is clicked. | 0.55
[8 empty] | T094 | Display the visit history in a chronological list format on the 'Visit History' tab. | 1.2
[8 empty] | T095 | Ensure each visit entry includes the date, summary of the visit, and any relevant notes or observations. | 0.55
[8 empty] | T096 | Add functionality to allow users to click on each visit entry to view more detailed information. | 1.2
[8 empty] | T097 | Develop a backend endpoint to fetch detailed information for a specific visit when requested. | 1.2
[8 empty] | T098 | Implement the frontend logic to call the backend endpoint and retrieve detailed visit information when a visit entry is clicked. | 1.2
[8 empty] | T099 | Ensure the detailed visit information is displayed in a user-friendly format. | 1.2
[8 empty] | T100 | Test the entire workflow to ensure that the visit history and detailed visit information are displayed correctly and meet the acceptance criteria. | 1.2
|  |  |  | S010 | View Consultation History | As a doctor, I want to view the consultation history of a patient so that I can review past consultations and their outcomes. | Given that I am on a patient's profile page, when I click on the 'Consultation History' tab, I should see a chronological list of all past consultations. Each consultation entry should include the date, summary of the consultation, and any generated reports. I should be able to click on each consultation entry to view more detailed information. | T101 | Create a 'Consultation History' tab on the patient's profile page. | 0.55
[8 empty] | T102 | Develop a backend endpoint to fetch the list of past consultations for a specific patient. | 0.55
[8 empty] | T103 | Implement a frontend component to display a chronological list of past consultations under the 'Consultation History' tab. | 1.2
[8 empty] | T104 | Ensure each consultation entry includes the date, summary of the consultation, and any generated reports. | 0.55
[8 empty] | T105 | Develop a backend endpoint to fetch detailed information for a specific consultation entry. | 0.55
[8 empty] | T106 | Implement a frontend component to display detailed information when a consultation entry is clicked. | 1.2
[8 empty] | T107 | Integrate the backend endpoints with the frontend components to ensure data is fetched and displayed correctly. | 1.2
[8 empty] | T108 | Add error handling and loading states for the 'Consultation History' tab and detailed consultation view. | 1.2
[8 empty] | T109 | Write unit tests for the backend endpoints to ensure they return the correct data. | 0.55
[8 empty] | T110 | Write unit tests for the frontend components to ensure they render the data correctly. | 0.55
[8 empty] | T111 | Conduct end-to-end testing to verify that the 'Consultation History' tab and detailed consultation view function as expected. | 1.2
|  |  |  | S011 | Start New Consultation | As a doctor, I want to start a new consultation by scanning a patient's QR code so that the consultation is linked to the correct patient. | Given that I am logged in as a doctor, when I click on the 'Start New Consultation' button, I should be prompted to scan a patient's QR code. Upon scanning the QR code, the system should link the consultation to the correct patient and take me to a new consultation page. The new consultation page should allow me to input notes, access patient history, and generate a consultation report. | T112 | Create a 'Start New Consultation' button on the doctor dashboard. | 0.25
[8 empty] | T113 | Implement a QR code scanning functionality that is triggered when the 'Start New Consultation' button is clicked. | 1.2
[8 empty] | T114 | Develop backend logic to validate the scanned QR code and retrieve the corresponding patient information from the database. | 1.2
[8 empty] | T115 | Link the consultation session to the correct patient based on the scanned QR code. | 1.2
[8 empty] | T116 | Redirect the doctor to a new consultation page after the QR code is successfully scanned and validated. | 0.55
[8 empty] | T117 | Design the new consultation page to include sections for inputting notes, accessing patient history, and generating a consultation report. | 1.2
[8 empty] | T118 | Implement functionality on the new consultation page to allow doctors to input and save consultation notes. | 1.2
[8 empty] | T119 | Integrate patient history access on the new consultation page, allowing doctors to view past visits and consultations. | 1.2
[8 empty] | T120 | Develop a feature on the new consultation page to generate and save a structured consultation report. | 1.2
[8 empty] | T121 | Ensure that all data transmissions, including QR code scanning and patient data retrieval, are encrypted to comply with data security regulations. | 1.2
[8 empty] | T122 | Create unit and integration tests to validate the QR code scanning, patient linking, and consultation page functionalities. | 1.2
[8 empty] | T123 | Deploy the new consultation feature to a staging environment for user acceptance testing (UAT). | 0.55
[8 empty] | T124 | Collect feedback from doctors during UAT and make necessary adjustments before the final deployment. | 0.55
|  |  |  | S012 | AI-Assisted Consultation | As a doctor, I want AI assistance during consultations so that I can receive real-time analysis and summarization of the conversation. | Given that I am in a consultation session, the AI should provide real-time analysis and summarization of the conversation. The AI should prompt for specific patient information or insights based on the conversation context. The AI should generate a draft consultation report that I can review, edit, and approve. | T125 | Integrate OpenAI API for real-time conversation analysis and summarization during consultation sessions. | 6
[8 empty] | T126 | Develop a function to capture and stream live audio or text input from the consultation session to the AI system. | 1.2
[8 empty] | T127 | Implement logic to process the streamed input and generate real-time analysis and summarization using the AI. | 6
[8 empty] | T128 | Create a mechanism for the AI to prompt the doctor for specific patient information or insights based on the ongoing conversation context. | 6
[8 empty] | T129 | Develop a function to retrieve and display specific patient information or insights when prompted by the AI. | 1.2
[8 empty] | T130 | Implement logic for the AI to compile a draft consultation report based on the real-time analysis and summarization. | 1.2
[8 empty] | T131 | Create an interface for doctors to review, edit, and approve the AI-generated draft consultation report. | 1.2
[8 empty] | T132 | Ensure all data transmitted during the consultation session is encrypted to comply with data security and privacy regulations. | 1.2
[8 empty] | T133 | Develop a function to store the final approved consultation report in the database and link it to the patient's profile. | 1.2
[8 empty] | T134 | Implement error handling and logging mechanisms to ensure the AI system's reliability and provide fallback options in case of failures. | 1.2
|  |  |  | S013 | Approve and Share Consultation Reports | As a doctor, I want to approve and share consultation reports with patients so that they have access to the outcomes of their consultations. | Given that I have completed a consultation, the system should generate a consultation report. I should be able to review, edit, and approve the consultation report. Once approved, the report should be shared with the patient and stored in their consultation history. | T135 | Implement a function to generate a consultation report after a consultation is completed. The function should take consultation details as input and produce a structured report as output. | 1.2
[8 empty] | T136 | Create an API endpoint to trigger the generation of a consultation report. This endpoint should accept consultation details and return the generated report. | 0.55
[8 empty] | T137 | Develop a user interface component that allows doctors to review the generated consultation report. The component should display the report in a readable format. | 1.2
[8 empty] | T138 | Implement an edit functionality within the review interface, allowing doctors to make changes to the consultation report. The edited report should be saved and updated in real-time. | 1.2
[8 empty] | T139 | Create an API endpoint to save the edited consultation report. This endpoint should accept the edited report details and update the existing report in the database. | 0.55
[8 empty] | T140 | Develop a user interface component for doctors to approve the consultation report. This component should include an 'Approve' button that triggers the approval process. | 1.2
[8 empty] | T141 | Implement a function to handle the approval of the consultation report. This function should mark the report as approved and trigger the sharing process. | 1.2
[8 empty] | T142 | Create an API endpoint to handle the approval of the consultation report. This endpoint should update the report status to approved and initiate the sharing process. | 1.2
[8 empty] | T143 | Develop a function to share the approved consultation report with the patient. This function should send the report to the patient's profile and notify them via email. | 1.2
[8 empty] | T144 | Create an API endpoint to share the approved consultation report with the patient. This endpoint should update the patient's consultation history and send a notification email. | 1.2
[8 empty] | T145 | Implement a notification system to send an email to the patient once the consultation report is approved and shared. The email should include details on how to access the report. | 1.2
[8 empty] | T146 | Develop a user interface component for patients to view their consultation history, including the newly shared report. This component should be accessible from the patient's profile. | 1.2
[8 empty] | T147 | Ensure all data related to the consultation report (generation, review, edit, approval, and sharing) is securely stored and complies with data privacy regulations. | 6
| E003 | Consultation Process | Enable doctors to start a new consultation session by scanning the patient's QR code to link the consultation to the patient. Provide AI assistance during consultations for real-time analysis and summarization. Allow doctors to generate, review, edit, and approve consultation reports, and share approved reports with patients. | S014 | Start New Consultation by Scanning QR Code | As a doctor, I want to start a new consultation session by scanning the patient's QR code so that I can link the consultation to the patient's profile. | Given I am logged into the doctor dashboard, when I click on 'Start New Consultation', then I should be prompted to scan the patient's QR code. When the QR code is successfully scanned, then the consultation session should be linked to the patient's profile. If the QR code is invalid, then I should receive an error message indicating the issue. | T148 | Create a 'Start New Consultation' button on the doctor dashboard. | 0.25
[8 empty] | T149 | Implement a QR code scanner interface that is triggered when the 'Start New Consultation' button is clicked. | 1.2
[8 empty] | T150 | Develop functionality to capture and decode the scanned QR code. | 1.2
[8 empty] | T151 | Create a backend API endpoint to validate the scanned QR code and link the consultation session to the patient's profile. | 1.2
[8 empty] | T152 | Implement error handling to display an error message if the QR code is invalid. | 0.55
[8 empty] | T153 | Update the doctor dashboard to reflect the linked consultation session once the QR code is successfully scanned and validated. | 1.2
[8 empty] | T154 | Write unit tests to ensure the QR code scanning and validation process works correctly. | 0.55
[8 empty] | T155 | Write integration tests to verify the end-to-end flow from scanning the QR code to linking the consultation session to the patient's profile. | 1.2
[8 empty] | T156 | Ensure that all data transmission between the QR code scanner and the backend API is encrypted to comply with data security regulations. | 1.2
[8 empty] | T157 | Update the documentation to include instructions on how to use the 'Start New Consultation' feature and troubleshoot common issues. | 0.25
|  |  |  | S015 | AI Assistance During Consultation | As a doctor, I want AI assistance during consultations for real-time analysis and summarization so that I can make informed decisions quickly. | Given I am in an active consultation session, when I interact with the patient, then the AI should provide real-time analysis and summarization of the conversation. When the AI detects key medical information, then it should highlight and summarize this information for my review. If the AI is unable to provide analysis, then I should receive a notification indicating the issue. | T158 | Set up a Flask endpoint to start an active consultation session. This endpoint should initialize the AI system and prepare it for real-time analysis. | 1.2
[8 empty] | T159 | Integrate the OpenAI API to handle real-time speech-to-text conversion during the consultation session. Ensure the AI can process live audio input from the doctor and patient. | 1.2
[8 empty] | T160 | Develop a function to analyze the converted text in real-time using the OpenAI API. This function should identify key medical information and summarize it. | 1.2
[8 empty] | T161 | Implement a mechanism to highlight key medical information detected by the AI in the consultation interface. Ensure that this information is presented clearly for the doctor's review. | 1.2
[8 empty] | T162 | Create a notification system to alert the doctor if the AI is unable to provide real-time analysis. This system should log the issue and notify the doctor through the consultation interface. | 1.2
[8 empty] | T163 | Develop a function to continuously update the real-time summary of the consultation as new information is detected by the AI. Ensure that the summary is concise and relevant. | 1.2
[8 empty] | T164 | Test the real-time analysis and summarization functionality with various consultation scenarios to ensure accuracy and reliability. Include edge cases such as interruptions or multiple speakers. | 1.2
[8 empty] | T165 | Implement data encryption for all communication between the AI system and the consultation interface to ensure patient data security and compliance with Canadian Laws and Quebec Loi 25. | 6
[8 empty] | T166 | Create a user interface component within the consultation session for the doctor to view the real-time analysis and summaries provided by the AI. Ensure it is user-friendly and accessible. | 1.2
[8 empty] | T167 | Develop logging and monitoring tools to track the performance and accuracy of the AI's real-time analysis and summarization. Use this data to make continuous improvements. | 1.2
|  |  |  | S016 | Generate Consultation Report | As a doctor, I want to generate a consultation report automatically from the AI analysis so that I can save time on documentation. | Given I have completed a consultation session, when I click on 'Generate Report', then the AI should create a structured report based on the consultation. The generated report should include key points, summaries, and any flagged issues discussed during the consultation. If the report generation fails, then I should receive an error message indicating the issue. | T168 | Create an API endpoint in Flask to handle the 'Generate Report' request from the doctor. This endpoint should be accessible only to authenticated users. | 0.55
[8 empty] | T169 | Implement a function to retrieve the consultation session data from the database using the session ID provided in the 'Generate Report' request. | 0.55
[8 empty] | T170 | Integrate with the OpenAI API to analyze the retrieved consultation session data and generate a structured report. This should include key points, summaries, and any flagged issues discussed during the consultation. | 1.2
[8 empty] | T171 | Develop a function to format the AI-generated analysis into a structured consultation report. The report should be organized into sections such as key points, summaries, and flagged issues. | 1.2
[8 empty] | T172 | Implement error handling in the report generation process to catch and log any issues. If the report generation fails, return an error message to the user indicating the issue. | 1.2
[8 empty] | T173 | Create a function to save the generated consultation report to the database, ensuring that it is linked to the correct patient and consultation session. | 1.2
[8 empty] | T174 | Develop a notification system to inform the doctor if the report generation fails, providing details of the failure. | 1.2
[8 empty] | T175 | Implement a user interface component in the doctor's dashboard to trigger the 'Generate Report' action. This should include a button labeled 'Generate Report' that sends a request to the Flask API endpoint. | 0.55
[8 empty] | T176 | Ensure that the generated report is accessible from the doctor's dashboard, allowing the doctor to review, edit, and approve the report. | 1.2
[8 empty] | T177 | Test the entire report generation workflow, including successful report creation, error handling, and notification systems, to ensure it meets the acceptance criteria. | 1.2
|  |  |  | S017 | Review and Edit Consultation Report | As a doctor, I want to review and edit the consultation report generated by the AI so that I can ensure its accuracy before approval. | Given a consultation report has been generated, when I click on 'Review Report', then I should be able to view the report in detail. When I click on 'Edit Report', then I should be able to make changes to the report content. If I make changes, then the system should save the edited report and notify me of the successful update. | T178 | Create a function to retrieve the AI-generated consultation report from the database. Input: consultation ID. Output: consultation report details. | 0.55
[8 empty] | T179 | Develop a user interface component to display the consultation report in detail. Input: consultation report details. Output: detailed view of the consultation report. | 0.55
[8 empty] | T180 | Implement a feature to allow doctors to click on 'Review Report' and view the consultation report in detail. Input: consultation ID. Output: detailed consultation report view. | 0.55
[8 empty] | T181 | Create an editable form for the consultation report content. Input: consultation report details. Output: editable fields for the report content. | 1.2
[8 empty] | T182 | Implement functionality to save changes made to the consultation report. Input: edited consultation report details. Output: updated consultation report saved in the database. | 1.2
[8 empty] | T183 | Develop a notification system to inform the doctor of a successful update after saving changes to the consultation report. Input: save operation status. Output: success notification. | 0.55
[8 empty] | T184 | Ensure data validation and error handling for the consultation report editing process. Input: edited consultation report details. Output: validation errors or success message. | 1.2
[8 empty] | T185 | Integrate the consultation report editing feature with the backend API to handle data retrieval and updates. Input: API endpoints for consultation report. Output: seamless data flow between frontend and backend. | 1.2
[8 empty] | T186 | Test the entire workflow from viewing the consultation report, editing it, saving changes, and receiving a notification. Input: test cases for each step. Output: verified and bug-free consultation report editing process. | 1.2
|  |  |  | S018 | Approve and Share Consultation Report | As a doctor, I want to approve the consultation report and share it with the patient so that the patient can have access to their medical information. | Given I have reviewed and edited the consultation report, when I click on 'Approve Report', then the report should be marked as approved. When the report is approved, then it should be automatically shared with the patient via their profile. If the sharing process fails, then I should receive an error message indicating the issue. | T187 | Create a function `approve_report` that takes a consultation report ID as input and marks the report as approved in the database. | 0.55
[8 empty] | T188 | Implement a database schema update to include an 'approved' status field in the consultation reports table. | 0.55
[8 empty] | T189 | Develop an API endpoint `/approve_report` that allows doctors to send a request to approve a consultation report. | 0.55
[8 empty] | T190 | Create a function `share_report_with_patient` that takes a consultation report ID and patient ID as input and shares the approved report with the patient via their profile. | 1.2
[8 empty] | T191 | Integrate the `share_report_with_patient` function into the `approve_report` function to automatically share the report upon approval. | 1.2
[8 empty] | T192 | Implement error handling in the `approve_report` function to catch any issues during the approval or sharing process and return an appropriate error message. | 0.55
[8 empty] | T193 | Develop a notification system to send an email to the patient when a consultation report is approved and shared, including details on how to view the report. | 1.2
[8 empty] | T194 | Create unit tests for the `approve_report` function to ensure it correctly marks reports as approved and handles errors appropriately. | 0.55
[8 empty] | T195 | Create unit tests for the `share_report_with_patient` function to ensure it correctly shares the report with the patient and handles errors appropriately. | 0.55
[8 empty] | T196 | Update the doctor dashboard UI to include an 'Approve Report' button that triggers the `/approve_report` API endpoint. | 0.55
[8 empty] | T197 | Update the patient profile UI to display approved consultation reports under the consultation history section. | 0.55
[8 empty] | T198 | Ensure all data transmission related to report approval and sharing is encrypted to comply with data security and privacy regulations. | 1.2
| E004 | Interactive AI for Doctor | Allow doctors to prompt the AI agent associated with a patient to retrieve specific information or insights from the patient's conversation history. Use the AI to retrieve and summarize relevant patient history to aid the doctor during consultations. | S019 | Prompt AI for Specific Patient Information | As a doctor, I want to prompt the AI to retrieve specific information from a patient's conversation history so that I can quickly access relevant details during consultations. | Given I am logged into the doctor dashboard, when I select a patient, then I should see an option to prompt the AI for specific information. When I enter a query, the AI should retrieve and display the relevant information from the patient's conversation history. The retrieved information should be accurate and relevant to the query entered. | T199 | Create a function to authenticate the doctor and ensure they are logged into the doctor dashboard. | 0.55
[8 empty] | T200 | Develop a user interface component on the doctor dashboard that allows doctors to select a patient from a list. | 0.55
[8 empty] | T201 | Implement a backend API endpoint to fetch the list of patients associated with the logged-in doctor. | 1.2
[8 empty] | T202 | Create a user interface component that provides an option to prompt the AI for specific information once a patient is selected. | 1.2
[8 empty] | T203 | Develop a backend API endpoint to handle AI query requests, taking the doctor's query and the selected patient's ID as inputs. | 1.2
[8 empty] | T204 | Integrate the OpenAI API to process the query and retrieve relevant information from the patient's conversation history. | 1.2
[8 empty] | T205 | Implement a function to parse and format the retrieved information to ensure it is accurate and relevant to the query entered. | 1.2
[8 empty] | T206 | Create a user interface component to display the retrieved information from the AI query in a readable format. | 1.2
[8 empty] | T207 | Develop error handling mechanisms to manage scenarios where the AI fails to retrieve relevant information or the query is invalid. | 1.2
[8 empty] | T208 | Ensure all data transmissions between the frontend and backend are encrypted to comply with data security regulations. | 1.2
[8 empty] | T209 | Write unit tests and integration tests to validate the functionality of the AI query retrieval process. | 1.2
[8 empty] | T210 | Deploy the new functionality to the development environment and conduct user acceptance testing with a sample group of doctors. | 1.2
|  |  |  | S020 | AI Summarization of Patient History | As a doctor, I want the AI to summarize a patient's conversation history so that I can get a quick overview of the patient's past interactions and medical history. | Given I am viewing a patient's profile, when I click on the 'Summarize History' button, then the AI should generate a summary of the patient's conversation history. The summary should include key points such as symptoms, medical conditions, and any other relevant information. The summary should be concise and easy to read. | T211 | Create a 'Summarize History' button on the patient's profile page. | 0.25
[8 empty] | T212 | Implement an API endpoint to trigger the AI summarization process when the 'Summarize History' button is clicked. | 0.55
[8 empty] | T213 | Integrate the OpenAI API to process the patient's conversation history and generate a summary. | 1.2
[8 empty] | T214 | Fetch the patient's conversation history from the database when the AI summarization process is triggered. | 1.2
[8 empty] | T215 | Develop a function to identify and extract key points such as symptoms, medical conditions, and other relevant information from the conversation history. | 1.2
[8 empty] | T216 | Format the extracted key points into a concise and easy-to-read summary. | 1.2
[8 empty] | T217 | Store the generated summary in the database for future reference. | 0.55
[8 empty] | T218 | Display the generated summary on the patient's profile page when the summarization process is complete. | 0.55
[8 empty] | T219 | Implement error handling and notifications for any issues that occur during the summarization process. | 1.2
[8 empty] | T220 | Test the entire summarization workflow to ensure it meets the acceptance criteria and functions correctly. | 1.2
|  |  |  | S021 | Real-Time AI Assistance During Consultations | As a doctor, I want the AI to provide real-time assistance during consultations so that I can make more informed decisions based on the patient's conversation history. | Given I am in a consultation session, when I ask the AI for specific insights, then the AI should provide real-time responses based on the patient's conversation history. The AI should be able to handle multiple queries during the consultation without significant delays. The information provided by the AI should be accurate and relevant to the ongoing consultation. | T221 | Set up a Flask endpoint to handle real-time AI queries from doctors during consultations. This endpoint will receive queries and return AI-generated responses. | 1.2
[8 empty] | T222 | Integrate the OpenAI API to process the received queries and generate responses based on the patient's conversation history. | 1.2
[8 empty] | T223 | Develop a function to retrieve the patient's conversation history from the AWS database when a query is received. | 1.2
[8 empty] | T224 | Implement logic to analyze the retrieved conversation history and extract relevant information to answer the doctor's query. | 1.2
[8 empty] | T225 | Ensure the AI can handle multiple queries during a single consultation session by implementing a queue system or concurrent processing. | 1.2
[8 empty] | T226 | Optimize the response time of the AI system to ensure minimal delays in providing real-time insights. | 1.2
[8 empty] | T227 | Validate the accuracy and relevance of the AI-generated responses by comparing them with predefined test cases and real patient data. | 1.2
[8 empty] | T228 | Implement error handling and fallback mechanisms to ensure the system can gracefully handle any issues with the OpenAI API or data retrieval. | 1.2
[8 empty] | T229 | Develop a logging mechanism to track all queries and responses during consultations for future analysis and improvements. | 1.2
[8 empty] | T230 | Create a user interface component within the doctor's consultation dashboard to display the AI-generated insights in real-time. | 1.2
[8 empty] | T231 | Conduct user testing sessions with doctors to gather feedback on the AI's performance and make necessary adjustments to improve the system. | 1.2
|  |  |  | S022 | Access AI-Generated Patient Summaries | As a doctor, I want to access AI-generated summaries of patient histories so that I can review them before or during consultations. | Given I am on the doctor dashboard, when I select a patient, then I should see an option to view AI-generated summaries of the patient's history. The summaries should be up-to-date and include all relevant information from the patient's conversation history. I should be able to download or print the summaries for offline review. | T232 | Create a function to fetch patient conversation history from the database. Input: patient_id. Output: list of conversation entries. | 0.55
[8 empty] | T233 | Develop an AI model integration to generate summaries from the fetched conversation history. Input: list of conversation entries. Output: summarized text. | 6
[8 empty] | T234 | Create an API endpoint to trigger the AI summary generation. Input: patient_id. Output: AI-generated summary. | 1.2
[8 empty] | T235 | Implement a feature on the doctor dashboard to select a patient and trigger the AI summary generation via the API. Input: patient_id. Output: display AI-generated summary. | 1.2
[8 empty] | T236 | Ensure the AI-generated summary includes all relevant information from the patient's conversation history. Input: list of conversation entries. Output: comprehensive summary. | 6
[8 empty] | T237 | Add functionality to download the AI-generated summary as a PDF. Input: AI-generated summary. Output: downloadable PDF file. | 0.55
[8 empty] | T238 | Add functionality to print the AI-generated summary directly from the doctor dashboard. Input: AI-generated summary. Output: print dialog with summary content. | 0.55
[8 empty] | T239 | Implement a caching mechanism to store recent AI-generated summaries for quick access. Input: patient_id, AI-generated summary. Output: cached summary. | 1.2
[8 empty] | T240 | Ensure that the AI-generated summaries are up-to-date by refreshing the cache periodically or on-demand. Input: patient_id. Output: refreshed AI-generated summary. | 1.2
[8 empty] | T241 | Develop a user interface component on the doctor dashboard to display the AI-generated summary in a readable format. Input: AI-generated summary. Output: formatted summary display. | 1.2
[8 empty] | T242 | Implement error handling for the AI summary generation process to notify the doctor in case of any issues. Input: error message. Output: user notification. | 0.55
[8 empty] | T243 | Conduct testing to ensure the AI-generated summaries are accurate and include all relevant information. Input: test cases. Output: test results and bug fixes. | 1.2
|  |  |  | S023 | AI-Driven Insights for Patient Management | As a doctor, I want the AI to provide insights based on patient conversation histories so that I can better manage my patients and prioritize their needs. | Given I am viewing the patient list, when I click on a patient flagged by the AI, then I should see detailed insights and recommendations based on the patient's conversation history. The AI should categorize patients based on the urgency and type of their medical needs. The insights provided should help me prioritize consultations and follow-up actions. | T244 | Develop a function to retrieve and display the patient list, including patients flagged by the AI. | 1.2
[8 empty] | T245 | Implement a feature to click on a flagged patient and view detailed insights and recommendations based on the patient's conversation history. | 1.2
[8 empty] | T246 | Create an AI model to analyze patient conversation histories and categorize patients based on urgency and type of medical needs. | 12
[8 empty] | T247 | Develop a function to display categorized patients with insights to help prioritize consultations and follow-up actions. | 1.2
[8 empty] | T248 | Integrate the AI insights and recommendations into the patient list view, ensuring that doctors can easily access this information. | 1.2
[8 empty] | T249 | Ensure that the AI-generated insights are accurate, relevant, and presented in a user-friendly format. | 1.2
[8 empty] | T250 | Implement a secure data retrieval mechanism to fetch patient conversation histories from the database. | 1.2
[8 empty] | T251 | Test the AI insights and categorization feature to ensure it meets the acceptance criteria and provides value to doctors. | 1.2
[8 empty] | T252 | Develop a user interface component to display detailed insights and recommendations when a doctor clicks on a flagged patient. | 1.2
[8 empty] | T253 | Ensure compliance with data privacy and security regulations when accessing and displaying patient information. | 1.2
| E005 | Patient Flags | Provide a feature for doctors to view a list of patients categorized by flags based on the patients' onboarding responses. This helps doctors prioritize and manage patient care effectively. | S024 | View Patient Flags Dashboard | As a doctor, I want to view a dashboard that lists patients categorized by flags based on their onboarding responses so that I can quickly prioritize and manage patient care. | Given that I am logged in as a doctor, when I navigate to the patient flags dashboard, I should see a list of patients categorized by different flags. Each flag category should be clearly labeled and patients should be listed under their respective categories. The dashboard should be accessible from the main doctor dashboard. | T254 | Create a 'Patient Flags Dashboard' endpoint in the Flask backend to serve the patient flags data. | 1.2
[8 empty] | T255 | Develop a function to retrieve patient data from the database, categorized by flags based on onboarding responses. | 1.2
[8 empty] | T256 | Implement logic to categorize patients into different flag categories based on their onboarding responses. | 1.2
[8 empty] | T257 | Design and implement the front-end UI for the 'Patient Flags Dashboard' accessible from the main doctor dashboard. | 1.2
[8 empty] | T258 | Ensure each flag category is clearly labeled on the dashboard and patients are listed under their respective categories. | 0.55
[8 empty] | T259 | Integrate the front-end UI with the Flask backend to fetch and display the categorized patient data. | 1.2
[8 empty] | T260 | Add navigation to the 'Patient Flags Dashboard' from the main doctor dashboard. | 0.25
[8 empty] | T261 | Implement user authentication checks to ensure only logged-in doctors can access the 'Patient Flags Dashboard'. | 0.55
[8 empty] | T262 | Write unit tests for the backend functions to ensure correct categorization and retrieval of patient data. | 0.55
[8 empty] | T263 | Write integration tests to verify that the front-end correctly displays the categorized patient data from the backend. | 1.2
[8 empty] | T264 | Conduct user acceptance testing to ensure the dashboard meets the acceptance criteria and is user-friendly for doctors. | 0.55
|  |  |  | S025 | Filter Patients by Flag Category | As a doctor, I want to filter the list of patients by specific flag categories so that I can focus on a particular group of patients. | Given that I am on the patient flags dashboard, when I select a specific flag category, I should only see patients who fall under that category. The filter should be easy to apply and remove, allowing for quick changes between categories. | T265 | Create a new endpoint in the backend to fetch patients based on flag categories. The endpoint should accept a flag category as a parameter and return a list of patients who fall under that category. | 0.55
[8 empty] | T266 | Implement a function in the backend to query the database for patients based on the provided flag category. Ensure the function returns the necessary patient details such as name, flag category, and any other relevant information. | 1.2
[8 empty] | T267 | Develop the frontend UI component for the patient flags dashboard. This component should display a list of patients categorized by their flags. | 1.2
[8 empty] | T268 | Add a dropdown or filter menu in the patient flags dashboard UI to allow doctors to select a specific flag category. | 0.55
[8 empty] | T269 | Implement the logic in the frontend to call the backend endpoint when a specific flag category is selected from the dropdown or filter menu. The UI should update to display only the patients who fall under the selected category. | 0.55
[8 empty] | T270 | Ensure the filter functionality is easy to apply and remove. Implement a clear button or similar UI element to reset the filter and show all patients again. | 0.55
[8 empty] | T271 | Write unit tests for the backend function to ensure it correctly queries and returns patients based on the flag category. | 0.55
[8 empty] | T272 | Write integration tests for the new backend endpoint to ensure it works correctly with the frontend and returns the expected data. | 0.55
[8 empty] | T273 | Write frontend tests to ensure the filter functionality works as expected. This includes testing the dropdown/filter menu, the application of the filter, and the removal of the filter. | 0.55
[8 empty] | T274 | Conduct user acceptance testing (UAT) with a sample group of doctors to ensure the filter functionality is intuitive and meets the acceptance criteria. | 0.55
|  |  |  | S026 | View Detailed Patient Information from Flags Dashboard | As a doctor, I want to click on a patient from the flags dashboard to view their detailed profile and historical data so that I can make informed decisions about their care. | Given that I am on the patient flags dashboard, when I click on a patient's name, I should be redirected to their detailed profile page. The profile page should include the patient's visit history, consultation history, and any relevant notes or summaries. | T275 | Implement the patient flags dashboard UI with clickable patient names. | 1.2
[8 empty] | T276 | Create a backend API endpoint to fetch detailed profile data for a selected patient. | 1.2
[8 empty] | T277 | Develop the frontend logic to handle the click event on a patient's name and redirect to the detailed profile page. | 0.55
[8 empty] | T278 | Design and implement the detailed profile page layout, including sections for visit history, consultation history, and relevant notes or summaries. | 1.2
[8 empty] | T279 | Integrate the frontend with the backend API to display the fetched patient profile data on the detailed profile page. | 1.2
[8 empty] | T280 | Ensure that the visit history section displays a list of past visits with dates and summaries. | 1.2
[8 empty] | T281 | Ensure that the consultation history section displays a list of past consultations with dates, doctor's names, and summaries. | 0.55
[8 empty] | T282 | Implement the logic to fetch and display any relevant notes or summaries associated with the patient. | 1.2
[8 empty] | T283 | Test the entire flow from clicking on a patient's name in the flags dashboard to viewing the detailed profile page to ensure it meets the acceptance criteria. | 1.2
[8 empty] | T284 | Ensure that all data displayed on the detailed profile page is securely fetched and complies with data privacy regulations. | 1.2
|  |  |  | S027 | Update Patient Flags Based on New Onboarding Responses | As a doctor, I want patient flags to be automatically updated based on new onboarding responses so that the categorization remains accurate and up-to-date. | Given that a patient completes a new onboarding process, when their responses are submitted, their flag category should be updated accordingly. The updated flag should reflect on the patient flags dashboard in real-time. | T285 | Create a function to handle the submission of onboarding responses. This function should take the patient's responses as input and store them in the database. | 0.55
[8 empty] | T286 | Develop a categorization algorithm that analyzes the patient's onboarding responses and determines the appropriate flag category. This function should take the patient's responses as input and output the flag category. | 1.2
[8 empty] | T287 | Implement a function to update the patient's flag category in the database based on the output of the categorization algorithm. This function should take the patient ID and the new flag category as inputs. | 1.2
[8 empty] | T288 | Create an API endpoint to handle the submission of onboarding responses. This endpoint should call the function to store responses, run the categorization algorithm, and update the flag category in the database. | 1.2
[8 empty] | T289 | Develop a real-time update mechanism for the patient flags dashboard. This should include a WebSocket or similar technology to push updates to the dashboard whenever a patient's flag category is updated. | 1.2
[8 empty] | T290 | Implement a function to retrieve the updated flag category from the database and send it to the patient flags dashboard in real-time. | 1.2
[8 empty] | T291 | Create a unit test suite to verify the correct categorization of patient flags based on various onboarding responses. This should include edge cases and typical scenarios. | 1.2
[8 empty] | T292 | Develop integration tests to ensure that the entire flow from onboarding response submission to real-time dashboard update works as expected. | 1.2
[8 empty] | T293 | Ensure data encryption and secure transmission of onboarding responses and flag updates to comply with data privacy regulations. | 6
[8 empty] | T294 | Update the patient flags dashboard UI to reflect real-time updates. This should include visual indicators for when a flag category is updated. | 1.2
|  |  |  | S028 | Notification for Critical Flags | As a doctor, I want to receive notifications for patients who are flagged as critical based on their onboarding responses so that I can address urgent cases promptly. | Given that a patient is flagged as critical, when I log in to the platform, I should receive a notification highlighting the critical flag. The notification should include the patient's name and a brief summary of the critical issue. | T295 | Create a database schema to store patient flags, including critical flags, and their associated details (e.g., patient name, critical issue summary). | 1.2
[8 empty] | T296 | Develop a backend API endpoint to update patient flags based on onboarding responses and mark patients as critical if necessary. | 1.2
[8 empty] | T297 | Implement a backend service to check for critical flags and trigger notifications when a doctor logs into the platform. | 1.2
[8 empty] | T298 | Create a notification service to send notifications to doctors when a critical flag is detected. The notification should include the patient's name and a brief summary of the critical issue. | 1.2
[8 empty] | T299 | Develop a frontend component to display notifications to doctors upon login, highlighting any patients flagged as critical. | 1.2
[8 empty] | T300 | Integrate the notification service with the frontend component to ensure that notifications are displayed in real-time when a doctor logs in. | 1.2
[8 empty] | T301 | Implement user authentication and session management to identify when a doctor logs into the platform. | 1.2
[8 empty] | T302 | Write unit tests for the backend API endpoint to ensure that patient flags are correctly updated and critical flags are identified. | 0.55
[8 empty] | T303 | Write integration tests for the notification service to verify that notifications are sent correctly when a critical flag is detected. | 1.2
[8 empty] | T304 | Write end-to-end tests to ensure that the entire flow—from flagging a patient as critical to displaying the notification to the doctor upon login—works as expected. | 1.2
|  |  |  | S029 | Export Patient Flags Report | As a doctor, I want to export a report of patients categorized by flags so that I can review and share the information offline or with other healthcare professionals. | Given that I am on the patient flags dashboard, when I click on the export button, I should be able to download a report in PDF or CSV format. The report should include all patients and their respective flag categories, along with any relevant notes or summaries. | T305 | Create an 'Export' button on the patient flags dashboard. | 0.55
[8 empty] | T306 | Implement functionality to generate a report of patients categorized by flags when the 'Export' button is clicked. | 1.2
[8 empty] | T307 | Develop a method to format the report data into PDF and CSV formats. | 1.2
[8 empty] | T308 | Ensure the report includes all patients, their respective flag categories, and any relevant notes or summaries. | 1.2
[8 empty] | T309 | Integrate the report generation functionality with the existing patient flags dashboard. | 1.2
[8 empty] | T310 | Add a feature to download the generated report in the selected format (PDF or CSV). | 0.55
[8 empty] | T311 | Test the export functionality to ensure the report is generated correctly and includes all required information. | 1.2
[8 empty] | T312 | Implement error handling for the export process to manage any issues that arise during report generation. | 1.2
[8 empty] | T313 | Update the user interface to notify the doctor when the report is successfully generated and available for download. | 0.55
[8 empty] | T314 | Ensure that the exported report complies with data security and privacy regulations, including encryption of sensitive data. | 1.2
| E006 | Notifications and Alerts | Send email notifications to doctors for important actions such as registration, verification, and report approvals. Ensure timely communication of critical updates and actions. | S030 | Email Notification for Doctor Registration | As a doctor, I want to receive an email notification upon successful registration so that I am informed that my account has been created. | Given a doctor has successfully registered, when the registration process is completed, then an email notification is sent to the doctor's registered email address. The email should include a welcome message and a confirmation of successful registration. | T315 | Create a function `send_registration_email` that takes a doctor's email address as input and sends a registration confirmation email. | 0.55
[8 empty] | T316 | Set up an email template for the registration confirmation email. The template should include a welcome message and confirmation of successful registration. | 0.55
[8 empty] | T317 | Integrate the email sending function with the registration process. Ensure that the function is called upon successful registration of a doctor. | 0.55
[8 empty] | T318 | Configure the email server settings in the application to enable sending emails. This includes setting up SMTP server details and authentication. | 0.55
[8 empty] | T319 | Implement error handling in the `send_registration_email` function to manage scenarios where email sending fails. Log errors for further analysis. | 0.55
[8 empty] | T320 | Write unit tests for the `send_registration_email` function to ensure it sends emails correctly and handles errors as expected. | 0.55
[8 empty] | T321 | Create an integration test to verify that a registration confirmation email is sent upon successful registration of a doctor. | 1.2
[8 empty] | T322 | Update the registration process documentation to include information about the email notification feature. | 0.25
|  |  |  | S031 | Email Notification for Doctor Verification | As a doctor, I want to receive an email notification upon successful account verification so that I am informed that my account is now verified. | Given a doctor has successfully verified their account, when the verification process is completed, then an email notification is sent to the doctor's registered email address. The email should include a confirmation of successful verification and any next steps if applicable. | T323 | Set up an email service using AWS SES (Simple Email Service) to send email notifications. | 1.2
[8 empty] | T324 | Create an email template for account verification confirmation. The template should include a confirmation message and any next steps if applicable. | 0.55
[8 empty] | T325 | Develop a function in Python that triggers the email service upon successful account verification. The function should take the doctor's email address as an input. | 0.55
[8 empty] | T326 | Integrate the email notification function with the account verification process. Ensure that the function is called when the verification process is completed. | 1.2
[8 empty] | T327 | Write unit tests to verify that the email notification function sends an email with the correct template and content. | 0.55
[8 empty] | T328 | Implement logging to track when email notifications are sent, including details such as the recipient's email address and the time the email was sent. | 0.55
[8 empty] | T329 | Deploy the updated verification process and email notification function to the production environment. | 1.2
[8 empty] | T330 | Conduct end-to-end testing to ensure that a doctor receives an email notification upon successful account verification. | 1.2
|  |  |  | S032 | Email Notification for Report Approval | As a doctor, I want to receive an email notification when a consultation report is approved so that I am informed of the report's status. | Given a consultation report has been approved, when the approval process is completed, then an email notification is sent to the doctor's registered email address. The email should include details of the approved report, including patient name, consultation date, and a summary of the report. | T331 | Set up an email notification service using AWS SES (Simple Email Service) to send emails to doctors. | 1.2
[8 empty] | T332 | Create a function to trigger the email notification when a consultation report is approved. This function should be integrated with the consultation report approval workflow. | 1.2
[8 empty] | T333 | Develop a template for the email notification. The template should include placeholders for patient name, consultation date, and a summary of the report. | 0.55
[8 empty] | T334 | Implement logic to populate the email template with the relevant details of the approved consultation report. | 0.55
[8 empty] | T335 | Ensure that the email notification function retrieves the doctor's registered email address from the database. | 0.55
[8 empty] | T336 | Write unit tests to verify that the email notification function triggers correctly and sends emails with the correct content. | 0.55
[8 empty] | T337 | Write integration tests to ensure that the email notification is sent upon the approval of a consultation report. | 1.2
[8 empty] | T338 | Deploy the email notification service and integrate it with the existing consultation report approval system. | 1.2
[8 empty] | T339 | Monitor the email notification service for any errors or delivery issues and set up logging for troubleshooting. | 1.2
[8 empty] | T340 | Document the email notification feature, including setup instructions, usage, and troubleshooting steps. | 0.25
|  |  |  | S033 | Email Notification for Critical Updates | As a doctor, I want to receive email notifications for critical updates and actions so that I am always informed of important changes or actions required. | Given a critical update or action is required, when the update or action is identified, then an email notification is sent to the doctor's registered email address. The email should include details of the critical update or action required, including any deadlines or steps needed to address the update. | T341 | Set up an email notification service using a suitable library (e.g., Flask-Mail) to send emails from the Flask application. | 0.55
[8 empty] | T342 | Create a function `send_email_notification` in Python that accepts parameters: `recipient_email`, `subject`, and `message_body`. This function will handle the email sending logic. | 0.55
[8 empty] | T343 | Define a template for the critical update email that includes placeholders for the details of the critical update or action required, deadlines, and steps needed to address the update. | 0.55
[8 empty] | T344 | Implement a function `generate_critical_update_email` that accepts parameters: `doctor_email`, `update_details`, `deadline`, and `steps`. This function will populate the email template with the provided details. | 0.55
[8 empty] | T345 | Create a database model `CriticalUpdate` to store information about critical updates, including fields for `doctor_id`, `update_details`, `deadline`, `steps`, and `timestamp`. | 0.55
[8 empty] | T346 | Implement a function `identify_critical_update` that checks for conditions or events that qualify as critical updates. This function will trigger the email notification process. | 1.2
[8 empty] | T347 | Integrate the `identify_critical_update` function with relevant parts of the application where critical updates might be identified (e.g., new patient registration, report approval). | 1.2
[8 empty] | T348 | Modify the `identify_critical_update` function to call `generate_critical_update_email` and `send_email_notification` when a critical update is identified. | 1.2
[8 empty] | T349 | Test the email notification system by simulating critical updates and verifying that emails are sent to the correct recipients with accurate and complete information. | 0.55
[8 empty] | T350 | Ensure that all email communications comply with data security and privacy regulations, including encryption of email content and secure handling of email addresses. | 1.2
|  |  |  | S034 | Email Notification for New Patient Registration | As a doctor, I want to receive an email notification when a new patient registers and associates with me so that I am aware of new patients under my care. | Given a new patient has registered and associated with a doctor, when the association process is completed, then an email notification is sent to the doctor's registered email address. The email should include the patient's name, registration date, and any initial information provided by the patient. | T351 | Create a function to handle new patient registration and association with a doctor. This function should be triggered when a new patient registers and associates with a doctor. | 1.2
[8 empty] | T352 | Develop a function to generate an email notification. This function should accept parameters such as the doctor's email address, patient's name, registration date, and any initial information provided by the patient. | 0.55
[8 empty] | T353 | Integrate the email generation function with the patient registration and association process. Ensure that the email is sent once the association process is completed. | 1.2
[8 empty] | T354 | Design an email template that includes placeholders for the patient's name, registration date, and initial information. Ensure the template is professional and clear. | 0.55
[8 empty] | T355 | Implement the logic to populate the email template with the patient's name, registration date, and initial information provided by the patient. | 0.55
[8 empty] | T356 | Set up an email service (e.g., AWS SES) to send the email notifications. Ensure the service is configured to handle the email sending process securely and reliably. | 1.2
[8 empty] | T357 | Write unit tests to verify that the email notification function works correctly. Ensure the tests cover scenarios such as successful email sending and handling of missing or incorrect data. | 0.55
[8 empty] | T358 | Write integration tests to ensure that the email notification is sent correctly when a new patient registers and associates with a doctor. Verify that the email includes the correct patient's name, registration date, and initial information. | 1.2
[8 empty] | T359 | Deploy the email notification feature to the development environment. Conduct end-to-end testing to ensure the entire process works as expected, from patient registration to email notification. | 1.2
[8 empty] | T360 | Monitor the deployed feature for any issues or errors. Ensure that email notifications are being sent correctly and received by the doctors. | 0.55
| E007 | Data Security and Privacy | Implement robust access control mechanisms to protect patient data. Ensure all sensitive data is encrypted in transit and at rest to comply with Canadian Laws and Quebec Loi 25 laws. | S035 | Doctor Account Security | As a doctor, I want my account to be secured with OTP and email verification so that I can ensure that only I have access to my account. | Doctors must verify their email during registration. Doctors must verify their phone number using OTP during registration. Doctors must log in using their registered email and password. | T361 | Create a registration endpoint in Flask that accepts doctor's name, email, phone number, and password as inputs. | 0.55
[8 empty] | T362 | Implement email verification functionality: generate a unique verification link, send it to the doctor's email, and create an endpoint to handle email verification when the link is clicked. | 1.2
[8 empty] | T363 | Implement OTP generation and sending functionality: generate a unique OTP, send it to the doctor's phone number via SMS, and create an endpoint to verify the OTP. | 1.2
[8 empty] | T364 | Create a login endpoint in Flask that accepts email and password, verifies the credentials against the database, and returns an authentication token upon successful login. | 1.2
[8 empty] | T365 | Set up a database schema in AWS to store doctor registration details, including name, email, phone number, password (hashed), email verification status, and OTP verification status. | 1.2
[8 empty] | T366 | Encrypt sensitive data (passwords, OTPs) before storing them in the database using industry-standard encryption algorithms. | 1.2
[8 empty] | T367 | Ensure all data transmitted between the client and server is encrypted using HTTPS. | 0.55
[8 empty] | T368 | Implement middleware in Flask to check for email and OTP verification status during login and registration processes. | 1.2
[8 empty] | T369 | Create unit and integration tests to verify the functionality of email verification, OTP verification, and login processes. | 1.2
[8 empty] | T370 | Document the registration, email verification, OTP verification, and login API endpoints, including input parameters, expected responses, and error handling. | 0.25
|  |  |  | S036 | Secure Data Access | As a doctor, I want to access patient data securely so that I can ensure the confidentiality and integrity of the information. | All patient data must be encrypted in transit using HTTPS. All patient data must be encrypted at rest in the database. Access to patient data should be restricted to authorized users only. | T371 | Set up HTTPS for all communication between the client and server to ensure data encryption in transit. | 0.55
[8 empty] | T372 | Configure the Flask application to enforce HTTPS for all routes. | 0.55
[8 empty] | T373 | Implement SSL/TLS certificates for the Flask server to secure data transmission. | 0.55
[8 empty] | T374 | Encrypt all patient data at rest in the database using AWS KMS (Key Management Service). | 1.2
[8 empty] | T375 | Configure the database to use encrypted storage for all patient-related tables and fields. | 1.2
[8 empty] | T376 | Implement role-based access control (RBAC) to restrict access to patient data to authorized users only. | 1.2
[8 empty] | T377 | Create a user authentication system that verifies user roles and permissions before granting access to patient data. | 1.2
[8 empty] | T378 | Develop a middleware in Flask to check user authorization on each request to access patient data. | 1.2
[8 empty] | T379 | Set up logging to track access to patient data, including who accessed it and when. | 1.2
[8 empty] | T380 | Conduct security testing to ensure that data encryption in transit and at rest is functioning correctly. | 1.2
[8 empty] | T381 | Perform regular audits to verify compliance with Canadian Laws and Quebec Loi 25 laws regarding data security and privacy. | 6
|  |  |  | S037 | Role-Based Access Control | As a doctor, I want role-based access control mechanisms so that only authorized personnel can access specific data and functionalities. | Doctors can only access patient data for patients who have shared their QR code. Doctors can only view and edit consultation reports for their patients. Access logs should be maintained to track who accessed what data and when. | T382 | Implement role-based access control (RBAC) in the Flask application to restrict access to patient data based on user roles. | 1.2
[8 empty] | T383 | Create a database schema to store role definitions and permissions, ensuring that each role has specific access rights. | 1.2
[8 empty] | T384 | Develop a mechanism to assign roles to users (doctors) during registration or profile updates. | 1.2
[8 empty] | T385 | Implement a function to verify if a doctor has access to a specific patient's data based on the shared QR code. | 1.2
[8 empty] | T386 | Create an API endpoint to check if a doctor has the necessary permissions to view or edit a patient's consultation report. | 1.2
[8 empty] | T387 | Develop a middleware to enforce RBAC rules on API endpoints, ensuring that only authorized users can access specific data and functionalities. | 1.2
[8 empty] | T388 | Implement logging functionality to track all access attempts to patient data, including successful and failed attempts. | 1.2
[8 empty] | T389 | Create a secure storage mechanism for access logs, ensuring that logs are encrypted and comply with data privacy regulations. | 1.2
[8 empty] | T390 | Develop an admin interface to view and manage access logs, allowing administrators to audit who accessed what data and when. | 1.2
[8 empty] | T391 | Implement unit tests and integration tests to verify that RBAC mechanisms are correctly enforced and that access logs are accurately maintained. | 1.2
[8 empty] | T392 | Ensure that all data in transit is encrypted using HTTPS and that sensitive data at rest is encrypted in the database. | 1.2
[8 empty] | T393 | Document the RBAC implementation, including role definitions, permissions, and access control policies, to ensure compliance with Canadian Laws and Quebec Loi 25. | 1.2
|  |  |  | S038 | Secure Consultation Reports | As a doctor, I want consultation reports to be securely stored and accessed so that patient information remains confidential. | Consultation reports must be encrypted at rest in the database. Only the doctor who conducted the consultation and the patient can access the consultation report. Consultation reports should be accessible only after the doctor has approved them. | T394 | Design the database schema to include a table for storing consultation reports with fields for report content, doctor ID, patient ID, and approval status. | 1.2
[8 empty] | T395 | Implement encryption for consultation reports at rest in the database using AES-256 encryption. | 1.2
[8 empty] | T396 | Develop a function to encrypt consultation reports before saving them to the database. Input: raw report data, Output: encrypted report data. | 1.2
[8 empty] | T397 | Develop a function to decrypt consultation reports when retrieving them from the database. Input: encrypted report data, Output: raw report data. | 1.2
[8 empty] | T398 | Create an API endpoint for doctors to save consultation reports. Ensure the endpoint encrypts the report before saving it to the database. | 1.2
[8 empty] | T399 | Create an API endpoint for doctors to retrieve their consultation reports. Ensure the endpoint decrypts the report before sending it to the doctor. | 1.2
[8 empty] | T400 | Implement access control logic to ensure that only the doctor who conducted the consultation and the patient can access the consultation report. Input: user ID, report ID, Output: access granted/denied. | 1.2
[8 empty] | T401 | Develop a function to check the approval status of consultation reports. Input: report ID, Output: approval status (approved/not approved). | 0.55
[8 empty] | T402 | Create an API endpoint for doctors to approve consultation reports. Ensure the endpoint updates the approval status in the database. | 1.2
[8 empty] | T403 | Implement frontend logic to display consultation reports only after they have been approved by the doctor. | 0.55
[8 empty] | T404 | Develop unit tests for encryption and decryption functions to ensure data integrity. | 0.55
[8 empty] | T405 | Develop integration tests for API endpoints to ensure proper access control and encryption/decryption processes. | 1.2
[8 empty] | T406 | Conduct security audits to verify that consultation reports are encrypted at rest and access control mechanisms are functioning correctly. | 1.2
|  |  |  | S039 | Data Encryption Compliance | As a doctor, I want the platform to comply with Canadian Laws and Quebec Loi 25 laws so that I can be assured that patient data is handled legally and securely. | All sensitive data must be encrypted in transit and at rest. The platform must provide documentation proving compliance with Canadian Laws and Quebec Loi 25 laws. Regular audits should be conducted to ensure ongoing compliance. | T407 | Implement encryption for data in transit using HTTPS for all communication between the client and server. | 0.55
[8 empty] | T408 | Implement encryption for data at rest using AWS KMS (Key Management Service) for database encryption. | 1.2
[8 empty] | T409 | Develop a module to handle encryption and decryption of sensitive data before storing in and retrieving from the database. | 1.2
[8 empty] | T410 | Integrate AWS CloudTrail to log all access and changes to sensitive data for audit purposes. | 1.2
[8 empty] | T411 | Create a compliance documentation template outlining how the platform adheres to Canadian Laws and Quebec Loi 25 laws. | 0.25
[8 empty] | T412 | Generate initial compliance documentation detailing the encryption methods used for data in transit and at rest. | 0.25
[8 empty] | T413 | Schedule and conduct regular security audits to ensure ongoing compliance with Canadian Laws and Quebec Loi 25 laws. | 1.2
[8 empty] | T414 | Develop a reporting mechanism to document the results of each security audit and any actions taken to address identified issues. | 1.2
[8 empty] | T415 | Implement access control mechanisms to restrict access to sensitive data based on user roles and permissions. | 1.2
[8 empty] | T416 | Ensure that all access control mechanisms are logged and monitored for unauthorized access attempts. | 1.2
|  |  |  | S040 | Secure QR Code Access | As a doctor, I want to securely scan patient QR codes to access their profiles and histories so that I can ensure that only authorized access is granted. | QR codes must be securely generated and encrypted. Only authorized doctors can scan and access patient data using QR codes. Access logs should record each instance of QR code scanning and data access. | T417 | Design and implement a secure QR code generation function that encrypts the QR code data. Input: Patient ID, Output: Encrypted QR code. | 1.2
[8 empty] | T418 | Develop a function to securely store the encrypted QR code in the database. Input: Encrypted QR code, Patient ID, Output: Database entry confirmation. | 0.55
[8 empty] | T419 | Create an API endpoint for doctors to scan QR codes and decrypt the data. Input: Encrypted QR code, Doctor's credentials, Output: Decrypted Patient ID if authorized. | 1.2
[8 empty] | T420 | Implement an authorization check within the QR code scanning API to ensure only authorized doctors can access patient data. Input: Doctor's credentials, Patient ID, Output: Authorization status (True/False). | 1.2
[8 empty] | T421 | Develop a logging mechanism to record each instance of QR code scanning and data access. Input: Doctor's ID, Patient ID, Timestamp, Output: Log entry in the database. | 1.2
[8 empty] | T422 | Integrate the QR code scanning API with the patient profile access system to retrieve and display patient data securely. Input: Decrypted Patient ID, Output: Patient profile data. | 1.2
[8 empty] | T423 | Ensure all data in transit during QR code generation, scanning, and data retrieval is encrypted using HTTPS. Input: Data packets, Output: Encrypted data packets. | 0.55
[8 empty] | T424 | Conduct security testing to verify that QR codes are securely generated, stored, and accessed only by authorized doctors. Input: Test cases, Output: Test results and security validation. | 1.2
[8 empty] | T425 | Document the QR code generation, storage, and access process, including security measures and compliance with Canadian Laws and Quebec Loi 25. Input: Process details, Output: Comprehensive documentation. | 1.2
|  |  |  | S041 | Notification of Data Access | As a doctor, I want to receive notifications when patient data is accessed so that I can monitor and ensure data security. | Doctors receive email notifications when patient data is accessed. Notifications include details of who accessed the data and when. Doctors can review access logs through their dashboard. | T426 | Set up an email notification service using AWS SES (Simple Email Service) to send notifications to doctors when patient data is accessed. | 1.2
[8 empty] | T427 | Develop a function to trigger email notifications when patient data is accessed. The function should include details of who accessed the data and when. | 1.2
[8 empty] | T428 | Create a database schema to log access events, including the doctor ID, patient ID, timestamp, and type of access (view, edit, etc.). | 1.2
[8 empty] | T429 | Implement an API endpoint to log access events in the database whenever patient data is accessed. | 1.2
[8 empty] | T430 | Develop a backend service that listens for access events and triggers the email notification function. | 1.2
[8 empty] | T431 | Create a dashboard section for doctors to review access logs. This section should display a list of access events with details such as who accessed the data and when. | 1.2
[8 empty] | T432 | Implement pagination and filtering options on the access logs dashboard to allow doctors to easily navigate and find specific access events. | 0.55
[8 empty] | T433 | Ensure that all data transmitted for logging access events and sending email notifications is encrypted in transit using HTTPS. | 0.55
[8 empty] | T434 | Ensure that access logs stored in the database are encrypted at rest to comply with Canadian Laws and Quebec Loi 25 laws. | 1.2
[8 empty] | T435 | Develop unit and integration tests to verify the functionality of the email notification service, access logging, and the access logs dashboard. | 1.2
Patients | E001 | User Authentication and Account Management | Enable patients to securely register, log in, and manage their profile information. This includes email and phone OTP verification during registration and the ability to update profile details such as name, phone number, email, and profile picture. | S001 | Patient Registration with Email and Phone OTP Verification | As a patient, I want to register an account using my name, email, phone number, and password, so that I can securely access the platform. | Given that I am on the registration page, when I enter my name, email, phone number, and password, then I should be able to submit the form. Given that I have submitted the registration form, when I receive an OTP on my phone, then I should be able to enter the OTP to verify my phone number. Given that I have submitted the registration form, when I receive an email with a verification link, then I should be able to click the link to verify my email. | T001 | Create the registration page with fields for name, email, phone number, and password. | 0.55
[8 empty] | T002 | Implement form validation to ensure all required fields (name, email, phone number, and password) are filled out correctly. | 0.55
[8 empty] | T003 | Develop the backend endpoint to handle registration form submissions and store user data in the database. | 1.2
[8 empty] | T004 | Integrate an OTP service to send an OTP to the user's phone number upon form submission. | 1.2
[8 empty] | T005 | Create a frontend interface for OTP entry and verification. | 1.2
[8 empty] | T006 | Develop the backend logic to verify the OTP entered by the user and update the user's phone verification status in the database. | 1.2
[8 empty] | T007 | Integrate an email service to send a verification email with a unique link to the user's email address upon form submission. | 1.2
[8 empty] | T008 | Create a backend endpoint to handle email verification when the user clicks the verification link. | 1.2
[8 empty] | T009 | Update the user's email verification status in the database upon successful verification. | 0.55
[8 empty] | T010 | Implement error handling and user feedback for scenarios such as incorrect OTP entry, expired OTP, and invalid email verification link. | 1.2
[8 empty] | T011 | Write unit and integration tests to ensure the registration, OTP verification, and email verification functionalities work as expected. | 1.2
|  |  |  | S002 | Patient Login | As a patient, I want to log in using my registered email and password so that I can access my account. | Given that I am on the login page, when I enter my registered email and password, then I should be able to submit the form to log in. Given that I have entered valid credentials, when I click the login button, then I should be redirected to my dashboard. Given that I have entered invalid credentials, when I click the login button, then I should see an error message indicating incorrect email or password. | T012 | Create a login page with fields for email and password. | 0.55
[8 empty] | T013 | Implement form validation to ensure both email and password fields are filled before submission. | 0.55
[8 empty] | T014 | Develop backend API endpoint to handle login requests, accepting email and password as inputs. | 0.55
[8 empty] | T015 | Integrate the login form with the backend API to submit the email and password for authentication. | 0.55
[8 empty] | T016 | Implement logic to verify the entered email and password against the stored user credentials in the database. | 1.2
[8 empty] | T017 | Handle successful login by redirecting the user to their dashboard upon valid credentials. | 0.55
[8 empty] | T018 | Handle unsuccessful login attempts by displaying an error message indicating incorrect email or password. | 0.55
[8 empty] | T019 | Ensure the login process is secure by using HTTPS for data transmission and encrypting sensitive information. | 1.2
[8 empty] | T020 | Create unit tests to verify the login functionality, including valid and invalid credential scenarios. | 0.55
[8 empty] | T021 | Implement logging for login attempts, including successful and failed attempts, for security monitoring. | 1.2
|  |  |  | S003 | Patient Profile Management - View Profile | As a patient, I want to view my profile information so that I can see my current details. | Given that I am logged in, when I navigate to the profile page, then I should see my current name, phone number, email, and profile picture. | T022 | Create a 'Profile' endpoint in Flask that retrieves the current user's profile information from the database. | 0.55
[8 empty] | T023 | Implement a function to fetch the user's name, phone number, email, and profile picture from the database. | 0.55
[8 empty] | T024 | Develop a front-end component in the desktop application that calls the 'Profile' endpoint and displays the retrieved profile information. | 1.2
[8 empty] | T025 | Ensure the front-end component includes fields for name, phone number, email, and profile picture, and properly formats the displayed information. | 0.55
[8 empty] | T026 | Add authentication middleware to the 'Profile' endpoint to ensure only logged-in users can access their profile information. | 0.55
[8 empty] | T027 | Write unit tests for the 'Profile' endpoint to verify it correctly retrieves and returns the user's profile information. | 0.55
[8 empty] | T028 | Write integration tests to ensure the front-end component correctly displays the profile information retrieved from the 'Profile' endpoint. | 1.2
[8 empty] | T029 | Implement error handling in the 'Profile' endpoint to manage cases where the user's profile information cannot be retrieved. | 0.55
[8 empty] | T030 | Add logging to the 'Profile' endpoint to track access and any errors encountered during the retrieval process. | 0.55
[8 empty] | T031 | Deploy the updated profile management feature to the development environment and conduct end-to-end testing to ensure it meets the acceptance criteria. | 1.2
|  |  |  | S004 | Patient Profile Management - Update Name | As a patient, I want to update my name so that my profile reflects my current information. | Given that I am on the profile page, when I edit the name field, then I should be able to save the changes. Given that I have saved the changes, when I refresh the profile page, then I should see the updated name. | T032 | Create a function to handle the update of the patient's name in the database. The function should take the patient's ID and the new name as inputs and update the corresponding record in the database. | 0.55
[8 empty] | T033 | Implement a frontend form on the profile page that allows the patient to edit their name. The form should include a text input field for the name and a save button. | 0.55
[8 empty] | T034 | Add validation to the frontend form to ensure that the name field is not empty and meets any other required criteria (e.g., length, character set). | 0.55
[8 empty] | T035 | Create an API endpoint in Flask to handle the name update request. The endpoint should accept the patient's ID and the new name as parameters and call the function to update the database. | 0.55
[8 empty] | T036 | Implement frontend logic to call the API endpoint when the save button is clicked. The logic should include error handling to display appropriate messages if the update fails. | 0.55
[8 empty] | T037 | Update the frontend to refresh the profile page after the name has been successfully updated. This can be done by re-fetching the profile data from the server and updating the displayed information. | 0.55
[8 empty] | T038 | Write unit tests for the backend function that updates the patient's name in the database to ensure it works correctly with various inputs. | 0.55
[8 empty] | T039 | Write integration tests for the API endpoint to ensure that it correctly handles valid and invalid requests and updates the database as expected. | 1.2
[8 empty] | T040 | Write end-to-end tests for the frontend form to ensure that the entire process of updating the name, including form validation, API call, and page refresh, works as expected. | 1.2
|  |  |  | S005 | Patient Profile Management - Update Phone Number | As a patient, I want to update my phone number so that my profile reflects my current contact information. | Given that I am on the profile page, when I edit the phone number field, then I should be able to save the changes. Given that I have saved the changes, when I refresh the profile page, then I should see the updated phone number. Given that I have updated my phone number, when I save the changes, then I should receive an OTP to verify the new phone number. | T041 | Create a function to handle the update of the phone number in the patient's profile. This function should take the patient's ID and new phone number as inputs and update the phone number in the database. | 0.55
[8 empty] | T042 | Implement input validation in the phone number update function to ensure the new phone number is in the correct format before saving it to the database. | 0.55
[8 empty] | T043 | Develop a function to generate and send an OTP to the new phone number for verification. This function should take the new phone number as input and use an external service (e.g., Twilio) to send the OTP. | 1.2
[8 empty] | T044 | Create an endpoint in the Flask application to handle the phone number update request. This endpoint should call the phone number update function and the OTP generation function. | 1.2
[8 empty] | T045 | Implement a function to verify the OTP entered by the patient. This function should take the patient's ID, new phone number, and OTP as inputs and verify the OTP against the one sent to the new phone number. | 1.2
[8 empty] | T046 | Develop a user interface component on the profile page to allow patients to edit their phone number. This component should include an input field for the new phone number and a button to save the changes. | 0.55
[8 empty] | T047 | Create a user interface component to handle OTP verification. This component should include an input field for the OTP and a button to submit the OTP for verification. | 0.55
[8 empty] | T048 | Update the profile page to display the new phone number after it has been successfully updated and verified. Ensure the page refreshes to reflect the updated phone number. | 0.55
[8 empty] | T049 | Implement error handling and user feedback for the phone number update process. This should include displaying appropriate error messages if the phone number format is invalid, if the OTP generation fails, or if the OTP verification fails. | 1.2
[8 empty] | T050 | Write unit tests for the phone number update function, OTP generation function, and OTP verification function to ensure they work as expected. | 0.55
[8 empty] | T051 | Write integration tests for the phone number update process, including updating the phone number, generating and sending the OTP, and verifying the OTP. | 1.2
|  |  |  | S006 | Patient Profile Management - Update Email | As a patient, I want to update my email so that my profile reflects my current contact information. | Given that I am on the profile page, when I edit the email field, then I should be able to save the changes. Given that I have saved the changes, when I refresh the profile page, then I should see the updated email. Given that I have updated my email, when I save the changes, then I should receive a verification email to confirm the new email address. | T052 | Create a function to handle email updates in the patient profile. The function should accept the patient's ID and the new email as inputs and update the email in the database. | 0.55
[8 empty] | T053 | Implement input validation for the email field to ensure that the new email address is in a valid format before saving. | 0.55
[8 empty] | T054 | Update the profile page UI to include an editable email field with a save button. Ensure that the save button triggers the email update function. | 0.55
[8 empty] | T055 | Create a function to send a verification email to the new email address. The function should generate a unique verification link and send it to the provided email. | 1.2
[8 empty] | T056 | Integrate the email update function with the profile page so that when the email is edited and saved, the new email is updated in the database. | 1.2
[8 empty] | T057 | Implement a mechanism to refresh the profile page after the email update to display the updated email address. | 0.55
[8 empty] | T058 | Create a verification endpoint that handles the verification link click. This endpoint should verify the email and update the verification status in the database. | 1.2
[8 empty] | T059 | Update the database schema to include a field for email verification status and a field for storing the verification token. | 0.55
[8 empty] | T060 | Implement error handling for scenarios where the email update or verification process fails, providing appropriate feedback to the user. | 1.2
[8 empty] | T061 | Write unit tests to ensure that the email update function, validation, and verification email sending work as expected. | 1.2
[8 empty] | T062 | Write integration tests to verify that the entire email update and verification process works correctly from the profile page to the verification endpoint. | 1.2
|  |  |  | S007 | Patient Profile Management - Update Profile Picture | As a patient, I want to update my profile picture so that my profile reflects my current appearance. | Given that I am on the profile page, when I upload a new profile picture, then I should be able to save the changes. Given that I have saved the changes, when I refresh the profile page, then I should see the updated profile picture. | T063 | Create a profile page with a section for updating the profile picture. | 1.2
[8 empty] | T064 | Implement a file upload feature on the profile page to allow patients to select and upload a new profile picture. | 1.2
[8 empty] | T065 | Validate the uploaded file to ensure it meets the required format (e.g., JPEG, PNG) and size constraints. | 0.55
[8 empty] | T066 | Develop a backend API endpoint to handle the profile picture upload, including saving the file to the server or cloud storage (e.g., AWS S3). | 1.2
[8 empty] | T067 | Update the patient's profile data in the database to reference the new profile picture URL after a successful upload. | 0.55
[8 empty] | T068 | Implement a mechanism to display the updated profile picture on the profile page after the changes are saved. | 1.2
[8 empty] | T069 | Ensure the profile page refreshes correctly to show the updated profile picture after saving the changes. | 0.55
[8 empty] | T070 | Write unit tests to verify that the profile picture upload and update functionality works as expected. | 0.55
[8 empty] | T071 | Write integration tests to ensure that the profile picture is correctly updated in the database and displayed on the profile page. | 1.2
[8 empty] | T072 | Conduct user acceptance testing (UAT) to confirm that the profile picture update feature meets the acceptance criteria and functions correctly from the user's perspective. | 1.2
| E002 | AI-Guided Onboarding Process | Provide an AI-guided onboarding process where patients can start a new visit, answer dynamic questions based on conversation context, and have their responses stored in a structured format. This process will generate a patient summary that can be viewed by both the patient and the doctor. | S008 | Start New Visit | As a patient, I want to start a new visit so that I can go through the AI-guided onboarding process. | Given I am logged into the platform, when I click on the 'Start New Visit' button, then the AI-guided onboarding process should begin. The AI should greet me and explain the onboarding process. The AI should ask initial questions to gather basic information. | T073 | Create a 'Start New Visit' button on the patient dashboard. | 0.25
[8 empty] | T074 | Implement the backend logic to handle the 'Start New Visit' button click event. | 0.55
[8 empty] | T075 | Develop an API endpoint to initialize the AI-guided onboarding process when the 'Start New Visit' button is clicked. | 1.2
[8 empty] | T076 | Integrate the AI system to greet the patient and explain the onboarding process upon starting a new visit. | 1.2
[8 empty] | T077 | Design and implement the initial questions that the AI will ask to gather basic patient information. | 1.2
[8 empty] | T078 | Ensure the AI system can dynamically generate and ask follow-up questions based on the patient's responses. | 1.2
[8 empty] | T079 | Store the patient's responses in a structured format in the database. | 1.2
[8 empty] | T080 | Encrypt the stored responses to ensure data security and compliance with Canadian Laws and Quebec Loi 25. | 6
[8 empty] | T081 | Test the entire AI-guided onboarding process to ensure it begins correctly when the 'Start New Visit' button is clicked, the AI greets the patient, explains the process, and asks initial questions. | 1.2
[8 empty] | T082 | Implement error handling and user notifications for any issues encountered during the onboarding process. | 1.2
|  |  |  | S009 | Dynamic Questioning | As a patient, I want the AI to ask me dynamic questions based on the conversation context so that the onboarding process feels personalized and relevant. | Given I am in the onboarding process, when I provide an answer, then the AI should ask follow-up questions based on my previous responses. The AI should be able to handle various types of responses and adjust its questions accordingly. | T083 | Design the AI question flow logic to handle dynamic question generation based on previous responses. | 6
[8 empty] | T084 | Implement the AI question flow logic using OpenAI API to generate follow-up questions based on the patient's previous responses. | 1.2
[8 empty] | T085 | Create a function to store patient responses in a structured format in the database. | 1.2
[8 empty] | T086 | Develop an API endpoint to handle patient responses and trigger the AI to generate the next question. | 1.2
[8 empty] | T087 | Integrate the AI question flow logic with the patient onboarding interface to display questions and capture responses. | 1.2
[8 empty] | T088 | Implement error handling and edge case management for various types of responses (e.g., invalid input, no response). | 1.2
[8 empty] | T089 | Test the AI question flow to ensure it adjusts questions based on different types of patient responses. | 1.2
[8 empty] | T090 | Ensure the AI can handle interruptions or topic changes and maintain the context of the conversation. | 1.2
[8 empty] | T091 | Create unit tests and integration tests to validate the dynamic question generation and response handling. | 1.2
[8 empty] | T092 | Document the AI question flow logic, API endpoints, and response handling for future maintenance and updates. | 0.55
|  |  |  | S010 | Store Responses | As a patient, I want my responses during the onboarding process to be stored in a structured format so that they can be used to generate a patient summary. | Given I am answering questions during the onboarding process, when I submit a response, then the response should be stored in a structured format in the database. All responses should be securely stored and encrypted. | T093 | Design the database schema to store patient responses in a structured format. Ensure the schema accommodates dynamic questions and answers. | 1.2
[8 empty] | T094 | Implement a Flask API endpoint to receive and store patient responses during the onboarding process. The endpoint should validate the input data and ensure it matches the defined schema. | 1.2
[8 empty] | T095 | Develop a function to encrypt patient responses before storing them in the database. Use industry-standard encryption methods to ensure data security. | 1.2
[8 empty] | T096 | Integrate the encryption function with the Flask API endpoint to ensure all patient responses are encrypted before storage. | 1.2
[8 empty] | T097 | Create a database model in Python that represents the structured format for storing patient responses. This model should include fields for question ID, response, timestamp, and any other relevant metadata. | 1.2
[8 empty] | T098 | Write unit tests for the Flask API endpoint to ensure it correctly handles valid and invalid input data, and that it properly stores encrypted responses in the database. | 1.2
[8 empty] | T099 | Implement a logging mechanism to track all API requests and responses for auditing and debugging purposes. Ensure that sensitive data is not logged. | 1.2
[8 empty] | T100 | Develop a function to decrypt patient responses when retrieving them from the database. Ensure this function is integrated with any API endpoints that need to access patient responses. | 1.2
[8 empty] | T101 | Conduct security testing to verify that patient responses are securely stored and encrypted in the database, and that they can be decrypted correctly when needed. | 1.2
[8 empty] | T102 | Document the API endpoint, including the request format, response format, and any required authentication or authorization details. Ensure the documentation is clear and accessible for future reference. | 0.55
|  |  |  | S011 | Generate Patient Summary | As a patient, I want a summary of my onboarding responses to be generated so that I can review it and share it with my doctor. | Given I have completed the onboarding process, when the AI finishes asking questions, then a patient summary should be generated based on my responses. The summary should be clear, concise, and include all relevant information gathered during the onboarding. | T103 | Create a function to retrieve all responses from the onboarding process for a given patient ID. | 0.55
[8 empty] | T104 | Develop a function to format the retrieved responses into a structured summary format. | 0.55
[8 empty] | T105 | Implement logic to ensure the summary includes all relevant information gathered during the onboarding process. | 1.2
[8 empty] | T106 | Integrate the summary generation function with the AI system to trigger upon completion of the onboarding process. | 1.2
[8 empty] | T107 | Create a function to store the generated summary in the database securely. | 1.2
[8 empty] | T108 | Develop an API endpoint to retrieve the stored summary for a given patient ID. | 0.55
[8 empty] | T109 | Ensure the generated summary is clear and concise by implementing a review mechanism to validate the summary content. | 1.2
[8 empty] | T110 | Implement unit tests to verify the accuracy and completeness of the generated summaries. | 0.55
[8 empty] | T111 | Develop a user interface component to display the generated summary to the patient. | 1.2
[8 empty] | T112 | Ensure the summary is accessible from the patient's dashboard under the 'Visit History' tab. | 0.55
|  |  |  | S012 | View Patient Summary | As a patient, I want to view my generated patient summary so that I can understand the information that will be shared with my doctor. | Given I have completed the onboarding process and a summary has been generated, when I navigate to the 'Visit History' tab, then I should be able to view my patient summary. The summary should be easily accessible and readable. | T113 | Create a 'Visit History' tab in the patient dashboard that is accessible after the patient logs in. | 0.55
[8 empty] | T114 | Develop a backend API endpoint to retrieve the patient summary data from the database once the onboarding process is completed. | 1.2
[8 empty] | T115 | Implement the frontend logic to call the backend API and fetch the patient summary data when the 'Visit History' tab is accessed. | 1.2
[8 empty] | T116 | Design a user-friendly interface to display the patient summary in the 'Visit History' tab, ensuring it is easily accessible and readable. | 1.2
[8 empty] | T117 | Ensure that the patient summary data is securely transmitted and complies with data privacy regulations. | 1.2
[8 empty] | T118 | Write unit tests to verify that the patient summary is correctly retrieved and displayed in the 'Visit History' tab. | 0.55
[8 empty] | T119 | Conduct user acceptance testing (UAT) to ensure that the patient summary is easily accessible and readable as per the acceptance criteria. | 0.55
|  |  |  | S013 | Edit Profile Information | As a patient, I want to manage my profile information so that my details are always up-to-date. | Given I am logged into the platform, when I navigate to the 'Profile Page', then I should be able to view and edit my profile information. Changes to my profile should be saved and reflected immediately. | T120 | Create a 'Profile Page' endpoint in the Flask backend to serve the profile management interface for patients. | 1.2
[8 empty] | T121 | Develop a frontend component for the 'Profile Page' using a modern JavaScript framework (e.g., React) to display and edit profile information. | 1.2
[8 empty] | T122 | Implement a form on the 'Profile Page' that allows patients to view and edit their profile information, including name, phone number, email, and profile picture. | 1.2
[8 empty] | T123 | Create API endpoints in Flask for retrieving and updating patient profile information in the database. | 1.2
[8 empty] | T124 | Integrate the frontend form with the backend API to fetch the current profile information when the 'Profile Page' is loaded. | 1.2
[8 empty] | T125 | Implement input validation on the frontend to ensure that the profile information entered by the patient is in the correct format. | 0.55
[8 empty] | T126 | Add functionality to the form to allow patients to upload and update their profile picture. | 1.2
[8 empty] | T127 | Ensure that changes made to the profile information are sent to the backend API and saved in the database. | 1.2
[8 empty] | T128 | Implement real-time feedback on the frontend to notify patients that their profile changes have been successfully saved. | 1.2
[8 empty] | T129 | Add error handling on the frontend to display appropriate error messages if the profile update fails. | 0.55
[8 empty] | T130 | Ensure that the updated profile information is immediately reflected on the 'Profile Page' after a successful save. | 1.2
[8 empty] | T131 | Write unit tests for the backend API endpoints to ensure they correctly handle retrieving and updating profile information. | 0.55
[8 empty] | T132 | Write integration tests to verify that the frontend and backend components work together seamlessly to allow patients to view and edit their profile information. | 1.2
[8 empty] | T133 | Conduct user acceptance testing to ensure that the 'Profile Page' meets the acceptance criteria and provides a smooth user experience. | 0.55
|  |  |  | S014 | QR Code for Doctor Access | As a patient, I want to have a QR code that doctors can scan to access my visit and consultation histories so that I can easily share my medical information. | Given I am logged into the platform, when I navigate to the 'Profile Page', then I should see a QR code. When a doctor scans the QR code, they should be able to access my visit and consultation histories. | T134 | Create a 'Profile Page' endpoint in the Flask backend to serve the profile page for logged-in patients. | 0.55
[8 empty] | T135 | Develop a function to generate a unique QR code for each patient upon profile page load. | 0.55
[8 empty] | T136 | Integrate the QR code generation function with the 'Profile Page' endpoint to display the QR code on the profile page. | 1.2
[8 empty] | T137 | Implement a database schema to store the mapping between patient IDs and their QR codes. | 1.2
[8 empty] | T138 | Create a secure API endpoint to retrieve visit and consultation histories based on the scanned QR code. | 1.2
[8 empty] | T139 | Ensure the QR code contains a secure token that maps to the patient's ID without exposing sensitive information. | 1.2
[8 empty] | T140 | Develop a function to fetch and display the patient's visit and consultation histories when the QR code is scanned. | 1.2
[8 empty] | T141 | Implement access control to ensure only authorized doctors can access patient data via the QR code. | 1.2
[8 empty] | T142 | Add logging and monitoring to track QR code scans and access to patient data for security and auditing purposes. | 1.2
[8 empty] | T143 | Test the QR code generation, scanning, and data retrieval processes to ensure they meet the acceptance criteria. | 1.2
| E003 | Chat Interface with AI | Implement a chat interface on the patient dashboard that allows patients to interact with an AI agent via text or voice. The AI will have access to the entire conversation history to provide informed responses, analyze conversations for emotional and physical well-being, and summarize long conversations. | S015 | Chat Interface Access | As a patient, I want to access the chat interface from my dashboard so that I can interact with the AI agent easily. | Given I am logged in, when I navigate to my dashboard, then I should see a chat icon at the bottom right corner. When I click on the chat icon, then the chat interface should open, allowing me to start a conversation with the AI agent. | T144 | Create a chat icon component that will be displayed at the bottom right corner of the patient dashboard. | 0.55
[8 empty] | T145 | Implement the functionality to display the chat icon only when the patient is logged in. | 0.55
[8 empty] | T146 | Develop the logic to open the chat interface when the chat icon is clicked. | 0.55
[8 empty] | T147 | Design the chat interface layout, ensuring it is user-friendly and intuitive. | 1.2
[8 empty] | T148 | Integrate the chat interface with the AI agent backend to allow real-time text interactions. | 1.2
[8 empty] | T149 | Ensure the AI agent has access to the patient's conversation history for informed responses. | 1.2
[8 empty] | T150 | Implement error handling for scenarios where the chat interface fails to open or the AI agent is unavailable. | 1.2
[8 empty] | T151 | Test the chat icon visibility and functionality across different browsers and devices. | 0.55
[8 empty] | T152 | Test the chat interface to ensure it opens correctly and allows patients to start a conversation with the AI agent. | 1.2
[8 empty] | T153 | Deploy the chat interface to the patient dashboard and monitor for any issues or feedback. | 0.55
|  |  |  | S016 | Text Interaction with AI | As a patient, I want to interact with the AI agent via text so that I can ask questions and receive responses. | Given the chat interface is open, when I type a message and press send, then the AI agent should respond with a relevant answer. The AI agent should have access to my conversation history to provide informed responses. | T154 | Create a chat interface on the patient dashboard that includes a text input field and a send button. | 0.55
[8 empty] | T155 | Implement a function to capture text input from the user and send it to the AI agent when the send button is pressed. | 0.55
[8 empty] | T156 | Develop an API endpoint to send the user's message to the AI agent and receive a response. | 1.2
[8 empty] | T157 | Integrate the API endpoint with the chat interface to display the AI agent's response in the chat window. | 1.2
[8 empty] | T158 | Ensure the AI agent has access to the patient's conversation history by implementing a function to retrieve past conversations from the database. | 1.2
[8 empty] | T159 | Modify the AI agent to use the retrieved conversation history to generate contextually relevant responses. | 1.2
[8 empty] | T160 | Implement error handling for the chat interface to manage cases where the AI agent fails to respond. | 0.55
[8 empty] | T161 | Test the chat interface to ensure that messages are sent and received correctly, and that the AI agent provides relevant responses based on the conversation history. | 1.2
[8 empty] | T162 | Ensure all data transmission between the chat interface and the AI agent is encrypted to comply with data security and privacy regulations. | 1.2
[8 empty] | T163 | Deploy the chat interface to the patient dashboard and monitor for any issues or improvements. | 0.55
|  |  |  | S017 | Voice Interaction with AI | As a patient, I want to interact with the AI agent via voice so that I can communicate more naturally. | Given the chat interface is open, when I click on the microphone icon and speak, then the AI agent should convert my speech to text and respond accordingly. The AI agent should have access to my conversation history to provide informed responses. | T164 | Implement the chat interface with a microphone icon on the patient dashboard. | 0.55
[8 empty] | T165 | Integrate the OpenAI API for voice-to-text conversion to handle patient speech input. | 1.2
[8 empty] | T166 | Develop functionality to capture and process voice input when the microphone icon is clicked. | 1.2
[8 empty] | T167 | Convert captured voice input to text using the OpenAI API and handle any errors or exceptions. | 1.2
[8 empty] | T168 | Ensure the AI agent has access to the patient's conversation history stored in the database. | 1.2
[8 empty] | T169 | Implement logic for the AI agent to provide contextually informed responses based on the converted text and conversation history. | 1.2
[8 empty] | T170 | Display the AI agent's text response in the chat interface. | 0.55
[8 empty] | T171 | Test the voice-to-text conversion and AI response functionality with various accents and speech patterns. | 1.2
[8 empty] | T172 | Ensure secure data transmission for voice input and text responses to comply with data privacy regulations. | 1.2
[8 empty] | T173 | Add logging for voice input processing and AI responses for debugging and monitoring purposes. | 0.55
|  |  |  | S018 | Conversation History Access | As a patient, I want the AI agent to have access to my entire conversation history so that it can provide more accurate and informed responses. | Given I have previous conversations with the AI, when I start a new conversation, then the AI should be able to reference my past interactions to provide contextually relevant responses. | T174 | Set up a database schema to store conversation histories, ensuring each conversation is linked to the respective patient. | 1.2
[8 empty] | T175 | Implement an API endpoint to save new conversations to the database, ensuring the data is encrypted in transit and at rest. | 1.2
[8 empty] | T176 | Develop a function to retrieve the entire conversation history for a specific patient from the database. | 1.2
[8 empty] | T177 | Integrate the conversation retrieval function with the AI agent, allowing it to access past interactions when a new conversation starts. | 1.2
[8 empty] | T178 | Enhance the AI agent's response generation logic to utilize the retrieved conversation history for providing contextually relevant responses. | 1.2
[8 empty] | T179 | Implement error handling and logging for the conversation retrieval process to ensure robustness and traceability. | 1.2
[8 empty] | T180 | Create unit tests to verify that conversation histories are correctly stored and retrieved from the database. | 1.2
[8 empty] | T181 | Conduct integration testing to ensure the AI agent can access and utilize past conversation histories during new interactions. | 1.2
[8 empty] | T182 | Ensure compliance with data privacy regulations (Canadian Laws and Quebec Loi 25) for storing and accessing patient conversation histories. | 6
[8 empty] | T183 | Update the patient dashboard UI to indicate that the AI agent has access to past conversation histories for providing informed responses. | 0.55
|  |  |  | S019 | Conversation Summarization | As a patient, I want the AI agent to summarize long conversations so that I can easily review the key points. | Given a conversation exceeds a certain length, when I request a summary, then the AI agent should provide a concise summary of the main points discussed. The summary should be stored in the database for future reference. | T184 | Create a function `summarize_conversation` that takes a conversation transcript as input and returns a concise summary of the main points discussed. | 1.2
[8 empty] | T185 | Integrate the OpenAI API to process the conversation transcript and generate a summary using NLP techniques. | 1.2
[8 empty] | T186 | Implement a mechanism to detect when a conversation exceeds a predefined length and trigger the summarization process. | 1.2
[8 empty] | T187 | Develop an API endpoint `/summarize` that accepts a conversation transcript, processes it, and returns the summary. | 1.2
[8 empty] | T188 | Store the generated summary in the database with a reference to the original conversation transcript for future reference. | 1.2
[8 empty] | T189 | Ensure that the stored summary is encrypted in the database to comply with data security and privacy regulations. | 1.2
[8 empty] | T190 | Create a user interface component on the patient dashboard that allows patients to request a summary of their conversation. | 1.2
[8 empty] | T191 | Implement error handling to manage cases where the summarization process fails or the conversation transcript is invalid. | 0.55
[8 empty] | T192 | Write unit tests to verify the functionality of the `summarize_conversation` function and the API endpoint. | 0.55
[8 empty] | T193 | Conduct integration testing to ensure that the summarization feature works seamlessly within the patient dashboard. | 1.2
|  |  |  | S020 | Emotional and Physical Well-being Analysis | As a patient, I want the AI agent to analyze my conversations for emotional and physical well-being so that I can receive insights into my health. | Given I have a conversation with the AI, when the conversation ends, then the AI should analyze the text for emotional and physical well-being indicators. The analysis results should be displayed to me and stored in the database for future reference. | T194 | Implement a function to capture and store the entire conversation text between the patient and the AI agent. | 0.55
[8 empty] | T195 | Develop a module to analyze the conversation text for emotional well-being indicators using sentiment analysis via the OpenAI API. | 1.2
[8 empty] | T196 | Develop a module to analyze the conversation text for physical well-being indicators by identifying keywords and phrases related to physical symptoms and conditions. | 1.2
[8 empty] | T197 | Integrate the emotional and physical well-being analysis modules to generate a comprehensive analysis report. | 1.2
[8 empty] | T198 | Create a database schema to store the analysis results, including emotional and physical well-being indicators. | 1.2
[8 empty] | T199 | Implement a function to save the analysis results into the database following the defined schema. | 1.2
[8 empty] | T200 | Develop a user interface component on the patient dashboard to display the analysis results after the conversation ends. | 1.2
[8 empty] | T201 | Ensure that the analysis results are encrypted before storing them in the database to comply with data security and privacy regulations. | 1.2
[8 empty] | T202 | Test the end-to-end workflow from conversation capture to analysis and display to ensure accuracy and reliability. | 1.2
|  |  |  | S021 | Data Storage | As a patient, I want all my conversations and summaries to be stored securely so that I can access them later. | Given I have a conversation with the AI, when the conversation ends, then the entire conversation and any generated summaries should be stored in the database. The stored data should be encrypted to comply with Canadian Laws and Quebec Loi 25 laws. | T203 | Set up the database schema to store conversations and summaries. Ensure the schema includes fields for patient ID, conversation text, summary text, timestamps, and any relevant metadata. | 1.2
[8 empty] | T204 | Implement a function to save conversation data to the database. This function should take patient ID, conversation text, and summary text as inputs and store them in the database. | 0.55
[8 empty] | T205 | Integrate the conversation storage function with the AI chat interface. Ensure that each conversation is saved to the database when the conversation ends. | 1.2
[8 empty] | T206 | Implement encryption for data in transit using HTTPS. Ensure that all data sent to and from the database is encrypted. | 1.2
[8 empty] | T207 | Implement encryption for data at rest in the database. Use industry-standard encryption algorithms to encrypt conversation and summary data before storing it. | 6
[8 empty] | T208 | Develop a function to retrieve stored conversations and summaries from the database. This function should take patient ID as input and return the corresponding conversation and summary data. | 1.2
[8 empty] | T209 | Ensure compliance with Canadian Laws and Quebec Loi 25 by conducting a security audit of the data storage and encryption mechanisms. Address any identified vulnerabilities. | 6
[8 empty] | T210 | Create unit tests to verify that conversations and summaries are correctly stored and retrieved from the database. Ensure that the tests cover both successful and edge cases. | 0.55
[8 empty] | T211 | Create integration tests to verify that the encryption mechanisms for data in transit and at rest are functioning correctly. Ensure that the tests cover both successful and edge cases. | 1.2
[8 empty] | T212 | Update the patient dashboard to include a section where patients can view their stored conversations and summaries. Ensure that the data is retrieved securely and displayed correctly. | 1.2
| E004 | Viewing Historical Data | Allow patients to view their past onboarding summaries and consultation histories. This includes providing a tab for onboarding history and another for consultation history, where patients can access detailed reports of their interactions and consultations. | S022 | View Onboarding History Tab | As a patient, I want to access a tab for onboarding history so that I can view summaries of my past onboarding sessions. | Given I am logged in, when I navigate to the dashboard, then I should see a tab labeled 'Onboarding History'. When I click on the 'Onboarding History' tab, I should see a list of my past onboarding sessions. Each onboarding session should display a summary including the date and key details of the session. | T213 | Create a new tab labeled 'Onboarding History' in the patient dashboard. | 0.25
[8 empty] | T214 | Implement a backend API endpoint to retrieve the list of past onboarding sessions for the logged-in patient. | 0.55
[8 empty] | T215 | Design the frontend UI to display the list of past onboarding sessions under the 'Onboarding History' tab. | 0.55
[8 empty] | T216 | Ensure each onboarding session entry includes the date and key details of the session. | 0.55
[8 empty] | T217 | Integrate the frontend UI with the backend API to fetch and display the onboarding sessions when the 'Onboarding History' tab is clicked. | 1.2
[8 empty] | T218 | Implement authentication checks to ensure that only logged-in patients can access the 'Onboarding History' tab. | 0.55
[8 empty] | T219 | Test the 'Onboarding History' tab to ensure it displays the correct information for different patient accounts. | 0.55
[8 empty] | T220 | Ensure that the data displayed in the 'Onboarding History' tab is securely transmitted and complies with Canadian Laws and Quebec Loi 25 laws. | 6
|  |  |  | S023 | View Detailed Onboarding Summary | As a patient, I want to view detailed reports of my past onboarding sessions so that I can review the information collected during those sessions. | Given I am on the 'Onboarding History' tab, when I click on a specific onboarding session, then I should see a detailed report of that session. The detailed report should include all questions asked and my responses during the onboarding session. | T221 | Create a new endpoint in the backend to fetch detailed onboarding session reports for a specific patient. The endpoint should accept the patient's ID and the session ID as inputs and return the detailed report. | 1.2
[8 empty] | T222 | Implement a function in the backend to query the database for the detailed onboarding session report based on the provided patient ID and session ID. Ensure the function retrieves all questions asked and the corresponding responses. | 1.2
[8 empty] | T223 | Design a new UI component in the frontend for displaying the detailed onboarding session report. The component should be able to render the list of questions and responses in a user-friendly format. | 1.2
[8 empty] | T224 | Integrate the new UI component into the 'Onboarding History' tab. Ensure that when a specific onboarding session is clicked, the detailed report is fetched from the backend and displayed using the new UI component. | 1.2
[8 empty] | T225 | Add a click event handler to the onboarding session entries in the 'Onboarding History' tab. The handler should trigger the fetch request to the new backend endpoint and pass the necessary patient ID and session ID. | 0.55
[8 empty] | T226 | Implement error handling in the frontend to display an appropriate message if the detailed report cannot be fetched (e.g., due to network issues or invalid session ID). | 0.55
[8 empty] | T227 | Ensure that all data transmitted between the frontend and backend is encrypted to comply with data security and privacy regulations. | 1.2
[8 empty] | T228 | Write unit tests for the backend function that queries the database to ensure it correctly retrieves the detailed onboarding session report. | 0.55
[8 empty] | T229 | Write integration tests for the new endpoint to ensure it correctly handles requests and returns the expected data. | 1.2
[8 empty] | T230 | Write end-to-end tests to verify that the entire flow—from clicking an onboarding session in the 'Onboarding History' tab to displaying the detailed report—is functioning correctly. | 1.2
|  |  |  | S024 | View Consultation History Tab | As a patient, I want to access a tab for consultation history so that I can view summaries of my past consultations with doctors. | Given I am logged in, when I navigate to the dashboard, then I should see a tab labeled 'Consultation History'. When I click on the 'Consultation History' tab, I should see a list of my past consultations. Each consultation should display a summary including the date and key details of the consultation. | T231 | Create a new route in the Flask application for the 'Consultation History' tab accessible from the patient dashboard. | 0.55
[8 empty] | T232 | Develop a front-end component for the 'Consultation History' tab that is visible on the patient dashboard when the user is logged in. | 1.2
[8 empty] | T233 | Implement authentication middleware to ensure that only logged-in patients can access the 'Consultation History' tab. | 0.55
[8 empty] | T234 | Design the back-end logic to fetch the list of past consultations for the logged-in patient from the database. | 1.2
[8 empty] | T235 | Create a database query to retrieve consultation summaries, including the date and key details, for the logged-in patient. | 0.55
[8 empty] | T236 | Develop the front-end logic to display the list of past consultations in the 'Consultation History' tab, including the date and key details for each consultation. | 1.2
[8 empty] | T237 | Ensure that the consultation data is displayed in a user-friendly format, with each entry showing the date and key details of the consultation. | 0.55
[8 empty] | T238 | Write unit tests for the back-end route to ensure that it correctly fetches and returns the consultation history for the logged-in patient. | 0.55
[8 empty] | T239 | Write integration tests to verify that the 'Consultation History' tab is only accessible to logged-in patients and displays the correct data. | 1.2
[8 empty] | T240 | Perform end-to-end testing to ensure that the entire flow from logging in to viewing the 'Consultation History' tab works as expected. | 1.2
|  |  |  | S025 | View Detailed Consultation Report | As a patient, I want to view detailed reports of my past consultations so that I can review the information discussed during those consultations. | Given I am on the 'Consultation History' tab, when I click on a specific consultation, then I should see a detailed report of that consultation. The detailed report should include the doctor's notes, AI-generated summaries, and any other relevant information from the consultation. | T241 | Create a 'Consultation History' tab on the patient dashboard that lists all past consultations. | 1.2
[8 empty] | T242 | Develop a backend API endpoint to fetch the list of past consultations for a patient from the database. | 0.55
[8 empty] | T243 | Implement the frontend logic to call the backend API and display the list of consultations under the 'Consultation History' tab. | 0.55
[8 empty] | T244 | Design the UI for the consultation list, ensuring each entry includes the date and a brief summary. | 0.55
[8 empty] | T245 | Create a backend API endpoint to fetch detailed consultation reports based on a selected consultation ID. | 1.2
[8 empty] | T246 | Implement the frontend logic to handle click events on consultation entries, triggering a call to the detailed consultation report API. | 0.55
[8 empty] | T247 | Design the UI for displaying detailed consultation reports, including sections for the doctor's notes, AI-generated summaries, and any other relevant information. | 1.2
[8 empty] | T248 | Ensure the detailed consultation report UI dynamically populates with data retrieved from the backend API. | 1.2
[8 empty] | T249 | Implement data encryption for consultation data both in transit and at rest to comply with data security regulations. | 1.2
[8 empty] | T250 | Add error handling and user notifications for scenarios where consultation data retrieval fails. | 0.55
[8 empty] | T251 | Conduct end-to-end testing to ensure that the consultation history and detailed report functionalities work seamlessly. | 1.2
|  |  |  | S026 | Secure Access to Historical Data | As a patient, I want to ensure that my historical data is securely accessible so that my privacy is maintained. | All data should be encrypted in transit and at rest to comply with Canadian Laws and Quebec Loi 25 laws. Access to historical data should be restricted to authenticated users only. Sensitive information should not be displayed in URL parameters or other insecure methods. | T252 | Implement data encryption for historical data in transit using HTTPS. | 0.55
[8 empty] | T253 | Implement data encryption for historical data at rest using AES-256 encryption. | 1.2
[8 empty] | T254 | Create a user authentication mechanism to ensure only authenticated users can access historical data. | 1.2
[8 empty] | T255 | Develop a secure login system that verifies user credentials before granting access to historical data. | 1.2
[8 empty] | T256 | Ensure that sensitive information is not included in URL parameters by using secure session tokens or POST requests for data retrieval. | 0.55
[8 empty] | T257 | Create API endpoints for retrieving historical data that require authentication tokens. | 1.2
[8 empty] | T258 | Implement backend logic to fetch and decrypt historical data from the database upon authenticated requests. | 1.2
[8 empty] | T259 | Develop frontend components to display historical data securely, ensuring data is fetched via authenticated API calls. | 1.2
[8 empty] | T260 | Conduct security testing to verify that data encryption in transit and at rest is functioning correctly. | 1.2
[8 empty] | T261 | Perform penetration testing to ensure that access to historical data is restricted to authenticated users only. | 1.2
[8 empty] | T262 | Review and update privacy policies to ensure compliance with Canadian Laws and Quebec Loi 25 laws. | 0.55
[8 empty] | T263 | Implement logging and monitoring to track access to historical data and detect unauthorized access attempts. | 1.2
|  |  |  | S027 | User-Friendly Interface for Historical Data | As a patient, I want a user-friendly interface for viewing my historical data so that I can easily navigate and understand the information. | The interface should be modern, sleek, and minimalistic. Tabs for 'Onboarding History' and 'Consultation History' should be clearly labeled and easily accessible from the dashboard. Summaries and detailed reports should be presented in a clear and organized manner. | T264 | Design the UI/UX for the historical data interface, ensuring it is modern, sleek, and minimalistic. Create wireframes and mockups for the 'Onboarding History' and 'Consultation History' tabs. | 0.55
[8 empty] | T265 | Implement the 'Onboarding History' tab on the patient dashboard. Ensure it is clearly labeled and easily accessible. | 0.55
[8 empty] | T266 | Implement the 'Consultation History' tab on the patient dashboard. Ensure it is clearly labeled and easily accessible. | 0.55
[8 empty] | T267 | Develop the backend API to fetch onboarding history data for the logged-in patient. Ensure data is retrieved in a structured and organized format. | 1.2
[8 empty] | T268 | Develop the backend API to fetch consultation history data for the logged-in patient. Ensure data is retrieved in a structured and organized format. | 1.2
[8 empty] | T269 | Integrate the backend API with the frontend to display the onboarding history in the 'Onboarding History' tab. Ensure the data is presented in a clear and organized manner. | 1.2
[8 empty] | T270 | Integrate the backend API with the frontend to display the consultation history in the 'Consultation History' tab. Ensure the data is presented in a clear and organized manner. | 1.2
[8 empty] | T271 | Implement pagination or infinite scroll for the 'Onboarding History' and 'Consultation History' tabs to handle large amounts of data efficiently. | 1.2
[8 empty] | T272 | Add sorting and filtering options for the 'Onboarding History' and 'Consultation History' tabs to enhance data navigation and accessibility. | 1.2
[8 empty] | T273 | Conduct usability testing with patients to gather feedback on the interface's user-friendliness and make necessary adjustments based on the feedback. | 1.2
[8 empty] | T274 | Ensure that all data displayed in the 'Onboarding History' and 'Consultation History' tabs is encrypted in transit and at rest to comply with Canadian Laws and Quebec Loi 25 laws. | 1.2
[8 empty] | T275 | Implement error handling and user notifications for scenarios where data retrieval fails or there are no historical records to display. | 0.55
| E005 | Profile Management and QR Code Access | Enable patients to manage their profile information and generate a QR code that doctors can scan to access the patient's visit and consultation histories. This feature will be available on the patient's profile page. | S028 | Patient Profile Management | As a patient, I want to manage my profile information (name, phone number, email, and profile picture) so that I can keep my contact details up-to-date and personalize my account. | Patients can view their current profile information. Patients can edit and save changes to their name, phone number, email, and profile picture. Changes to profile information are updated in the database and reflected immediately. | T276 | Create a 'Profile Management' section on the patient's profile page where current profile information (name, phone number, email, and profile picture) is displayed. | 1.2
[8 empty] | T277 | Develop a backend API endpoint to fetch the current profile information from the database for the logged-in patient. | 0.55
[8 empty] | T278 | Implement frontend form fields in the 'Profile Management' section for editing the patient's name, phone number, email, and profile picture. | 0.55
[8 empty] | T279 | Develop a backend API endpoint to update the patient's profile information in the database when changes are submitted. | 1.2
[8 empty] | T280 | Ensure that the profile picture upload functionality supports image validation and storage in a secure location (e.g., AWS S3). | 1.2
[8 empty] | T281 | Implement frontend form validation to ensure that the input data for name, phone number, and email are in the correct format before submission. | 0.55
[8 empty] | T282 | Create a mechanism to send an OTP to the patient's new phone number for verification when the phone number is updated. | 1.2
[8 empty] | T283 | Develop a backend API endpoint to verify the OTP and update the phone number in the database upon successful verification. | 1.2
[8 empty] | T284 | Create a mechanism to send a verification email to the patient's new email address when the email is updated. | 1.2
[8 empty] | T285 | Develop a backend API endpoint to verify the email address when the patient clicks the verification link in the email. | 0.55
[8 empty] | T286 | Implement a frontend notification system to inform the patient of the successful update of their profile information. | 0.55
[8 empty] | T287 | Ensure that all changes to the profile information are immediately reflected on the profile page after successful update and verification. | 1.2
[8 empty] | T288 | Conduct end-to-end testing to ensure that the profile management functionality works seamlessly, including fetching current information, editing, saving changes, and reflecting updates immediately. | 1.2
|  |  |  | S029 | Generate QR Code for Profile | As a patient, I want to generate a QR code on my profile page so that doctors can scan it to access my visit and consultation histories. | Patients can generate a unique QR code from their profile page. The QR code links to the patient's visit and consultation histories. The QR code is updated in real-time if any changes are made to the patient's visit or consultation histories. | T289 | Create a new endpoint in the Flask backend to generate a unique QR code for each patient. The endpoint should accept the patient's ID as input and return the QR code. | 1.2
[8 empty] | T290 | Implement a function in the backend to generate a QR code that encodes a URL linking to the patient's visit and consultation histories. Use a library like qrcode to generate the QR code. | 1.2
[8 empty] | T291 | Store the generated QR code in the database associated with the patient's profile. Ensure that the QR code is updated in real-time if any changes are made to the patient's visit or consultation histories. | 1.2
[8 empty] | T292 | Create a new route in the Flask backend to handle requests for accessing a patient's visit and consultation histories via the QR code URL. Ensure that the route verifies the doctor's authorization before granting access. | 1.2
[8 empty] | T293 | Update the patient's profile page on the frontend to include a section for generating and displaying the QR code. Add a button that triggers the QR code generation process. | 0.55
[8 empty] | T294 | Implement a frontend function to call the backend endpoint for generating the QR code when the button is clicked. Display the generated QR code on the patient's profile page. | 0.55
[8 empty] | T295 | Ensure that the QR code is dynamically updated in real-time on the patient's profile page if any changes are made to the patient's visit or consultation histories. Use WebSocket or polling to achieve real-time updates. | 1.2
[8 empty] | T296 | Add a notification system to inform the patient when their QR code is scanned and accessed by a doctor. Implement both backend and frontend components for this notification system. | 1.2
[8 empty] | T297 | Write unit tests for the backend functions related to QR code generation and storage to ensure they work as expected. | 0.55
[8 empty] | T298 | Write integration tests to verify that the QR code generation, storage, and real-time updates work seamlessly together. Ensure that the QR code links correctly to the patient's visit and consultation histories. | 1.2
|  |  |  | S030 | View Visit History | As a patient, I want to view my visit history so that I can keep track of my past medical visits and summaries. | Patients can access a 'Visit History' tab from their profile page. The 'Visit History' tab displays a list of past visits with summaries. Each visit summary includes the date, AI-generated summary, and any relevant notes. | T299 | Create a 'Visit History' tab on the patient's profile page. | 1.2
[8 empty] | T300 | Develop a backend API endpoint to retrieve the list of past visits for a patient. | 0.55
[8 empty] | T301 | Implement the frontend logic to call the backend API and display the list of past visits in the 'Visit History' tab. | 1.2
[8 empty] | T302 | Design the UI for the 'Visit History' tab to display each visit summary, including the date, AI-generated summary, and any relevant notes. | 1.2
[8 empty] | T303 | Integrate the AI-generated summaries and relevant notes into the visit summary display. | 1.2
[8 empty] | T304 | Ensure that the visit history data is securely transmitted and displayed, complying with data security and privacy regulations. | 1.2
[8 empty] | T305 | Implement a mechanism to handle and display errors if the visit history data retrieval fails. | 0.55
[8 empty] | T306 | Write unit tests for the backend API endpoint to ensure it correctly retrieves the list of past visits. | 0.55
[8 empty] | T307 | Write integration tests to verify that the 'Visit History' tab correctly displays the retrieved visit summaries. | 1.2
[8 empty] | T308 | Conduct user acceptance testing to ensure the 'Visit History' tab meets the acceptance criteria and provides a user-friendly experience. | 0.55
|  |  |  | S031 | View Consultation History | As a patient, I want to view my consultation history so that I can review past consultations with my doctors. | Patients can access a 'Consultation History' tab from their profile page. The 'Consultation History' tab displays a list of past consultations. Each consultation entry includes the date, doctor's name, and a summary of the consultation. | T309 | Create a 'Consultation History' tab on the patient's profile page. | 0.55
[8 empty] | T310 | Develop a backend API endpoint to fetch the list of past consultations for a patient from the database. | 1.2
[8 empty] | T311 | Implement the frontend logic to call the backend API and retrieve the consultation history data when the 'Consultation History' tab is accessed. | 1.2
[8 empty] | T312 | Design and implement the UI for displaying the list of past consultations, including the date, doctor's name, and a summary of each consultation. | 1.2
[8 empty] | T313 | Ensure that the consultation history data is securely transmitted and displayed, complying with data privacy regulations. | 1.2
[8 empty] | T314 | Implement error handling for scenarios where the consultation history data cannot be retrieved or is empty. | 0.55
[8 empty] | T315 | Write unit tests for the backend API endpoint to ensure it correctly fetches and returns the consultation history data. | 0.55
[8 empty] | T316 | Write integration tests to verify that the frontend correctly displays the consultation history data retrieved from the backend. | 1.2
[8 empty] | T317 | Conduct user acceptance testing to ensure the 'Consultation History' tab meets the acceptance criteria and provides a seamless user experience. | 0.55
|  |  |  | S032 | Secure Data Access via QR Code | As a patient, I want to ensure that only authorized doctors can access my visit and consultation histories via the QR code so that my medical information remains private and secure. | QR code access is restricted to authorized doctors who have scanned the code. Doctors must log in to their accounts to access the patient's information via the QR code. Patients receive a notification when their QR code is scanned and accessed by a doctor. | T318 | Implement QR code generation functionality on the patient's profile page. Ensure the QR code is unique for each patient and links to their visit and consultation histories. | 1.2
[8 empty] | T319 | Create a backend API endpoint to generate and retrieve the QR code for a patient. Ensure the endpoint is secure and accessible only to authenticated users. | 1.2
[8 empty] | T320 | Develop a mechanism to restrict QR code access to authorized doctors. Implement a check to ensure that only doctors who have scanned the QR code and are logged in can access the patient's information. | 1.2
[8 empty] | T321 | Implement a login check for doctors accessing patient information via the QR code. Ensure that doctors must be logged in to their accounts to view the patient's visit and consultation histories. | 1.2
[8 empty] | T322 | Create a notification system to inform patients when their QR code is scanned and accessed by a doctor. Ensure the notification includes details such as the doctor's name and the time of access. | 1.2
[8 empty] | T323 | Develop a secure method to log and track QR code scans and data access. Ensure that each instance of QR code scanning and data access is recorded with relevant details. | 1.2
[8 empty] | T324 | Ensure all data transmitted via the QR code is encrypted in transit and at rest. Implement encryption protocols to protect patient information. | 1.2
[8 empty] | T325 | Test the entire QR code access flow to ensure that only authorized doctors can access patient information, doctors must be logged in to view the data, and patients receive notifications when their QR code is scanned. | 1.2
[8 empty] | T326 | Update the patient profile page UI to include the QR code generation feature and ensure it is user-friendly and accessible. | 0.55
|  |  |  | S033 | Profile Page Navigation | As a patient, I want an intuitive profile page layout so that I can easily navigate to manage my profile, view visit history, and view consultation history. | The profile page includes clearly labeled sections for 'Profile Management', 'Visit History', and 'Consultation History'. Navigation between sections is smooth and user-friendly. The profile page design is consistent with the modern, sleek, and minimalistic UI guidelines. | T327 | Design the layout for the profile page, ensuring it includes clearly labeled sections for 'Profile Management', 'Visit History', and 'Consultation History'. | 0.55
[8 empty] | T328 | Implement the 'Profile Management' section on the profile page, allowing patients to view and edit their profile information. | 1.2
[8 empty] | T329 | Implement the 'Visit History' section on the profile page, displaying a list of past visits with summaries. | 1.2
[8 empty] | T330 | Implement the 'Consultation History' section on the profile page, displaying a list of past consultations with summaries. | 0.55
[8 empty] | T331 | Ensure smooth navigation between the 'Profile Management', 'Visit History', and 'Consultation History' sections using intuitive UI elements such as tabs or buttons. | 0.55
[8 empty] | T332 | Apply modern, sleek, and minimalistic UI design guidelines to the profile page, ensuring consistency with the overall platform design. | 0.55
[8 empty] | T333 | Conduct usability testing to ensure that the profile page layout is intuitive and user-friendly for patients. | 0.55
[8 empty] | T334 | Integrate the profile page with the backend to fetch and update profile information, visit history, and consultation history. | 1.2
[8 empty] | T335 | Implement data encryption for profile information, visit history, and consultation history to comply with Canadian Laws and Quebec Loi 25 laws. | 6
[8 empty] | T336 | Develop automated tests to verify the functionality and navigation of the profile page, ensuring all sections are accessible and working as expected. | 0.55
|  |  |  | S034 | Update Notification Settings | As a patient, I want to manage my notification settings so that I can control how and when I receive updates about my profile and medical histories. | Patients can access notification settings from their profile page. Patients can choose to receive notifications via email, SMS, or both. Changes to notification settings are saved and applied immediately. | T337 | Create a 'Notification Settings' section on the patient's profile page. | 0.55
[8 empty] | T338 | Develop a form within the 'Notification Settings' section that allows patients to select their preferred notification methods (email, SMS, or both). | 0.55
[8 empty] | T339 | Implement backend logic to save the selected notification preferences to the database. | 1.2
[8 empty] | T340 | Ensure that the saved notification preferences are immediately applied and reflected in the user's profile. | 1.2
[8 empty] | T341 | Integrate the notification settings with the existing notification system to send notifications based on the user's preferences. | 1.2
[8 empty] | T342 | Develop a feature to retrieve and display the current notification settings when the patient navigates to the 'Notification Settings' section. | 1.2
[8 empty] | T343 | Implement validation to ensure that at least one notification method is selected before saving the preferences. | 0.55
[8 empty] | T344 | Create unit tests to verify that the notification settings are saved correctly and applied immediately. | 0.55
[8 empty] | T345 | Create integration tests to ensure that notifications are sent according to the selected preferences. | 1.2
[8 empty] | T346 | Update the user interface to provide feedback to the patient when their notification settings are successfully saved. | 0.55
| E006 | Notifications and Alerts | Send email notifications to patients for important actions such as registration, verification, and report approvals. This ensures that patients are kept informed about their account activities and medical updates. | S035 | Email Notification for Registration | As a patient, I want to receive an email notification upon successful registration so that I am aware that my account has been created. | Given a patient has successfully registered, when the registration process is complete, then an email notification is sent to the patient's registered email address. The email should include a welcome message and confirmation of successful registration. | T347 | Create a function `send_registration_email` that takes a patient's email address as input and sends a registration confirmation email. | 0.55
[8 empty] | T348 | Set up an email service using AWS SES (Simple Email Service) to handle the sending of emails. | 1.2
[8 empty] | T349 | Design an email template for the registration confirmation email that includes a welcome message and confirmation of successful registration. | 0.55
[8 empty] | T350 | Integrate the `send_registration_email` function with the patient registration process to trigger the email upon successful registration. | 1.2
[8 empty] | T351 | Implement error handling in the `send_registration_email` function to log any issues that occur during the email sending process. | 0.55
[8 empty] | T352 | Write unit tests for the `send_registration_email` function to ensure it behaves as expected. | 0.55
[8 empty] | T353 | Write integration tests to verify that the email is sent upon successful patient registration. | 0.55
[8 empty] | T354 | Deploy the email service configuration and ensure that it is properly integrated with the registration workflow. | 1.2
[8 empty] | T355 | Verify that the email template renders correctly and includes the welcome message and confirmation of successful registration. | 0.55
[8 empty] | T356 | Conduct end-to-end testing to ensure that a registration email is sent to the patient's registered email address upon successful registration. | 1.2
|  |  |  | S036 | Email Notification for Email Verification | As a patient, I want to receive an email notification with a verification link so that I can verify my email address. | Given a patient has registered, when the registration process is complete, then an email notification containing a verification link is sent to the patient's registered email address. The email should include instructions on how to verify the email address. | T357 | Set up an email service using AWS SES (Simple Email Service) to send verification emails. | 0.55
[8 empty] | T358 | Create a function to generate a unique verification token for each registered patient. | 0.55
[8 empty] | T359 | Store the verification token securely in the database associated with the patient's account. | 1.2
[8 empty] | T360 | Develop an email template that includes the verification link and instructions on how to verify the email address. | 0.55
[8 empty] | T361 | Create a function to send the verification email to the patient's registered email address using the AWS SES service. | 0.55
[8 empty] | T362 | Integrate the email sending function with the patient registration process to trigger the email upon successful registration. | 1.2
[8 empty] | T363 | Develop an API endpoint to handle the email verification process when the patient clicks the verification link. | 1.2
[8 empty] | T364 | Create a function to validate the verification token from the link and update the patient's account status to 'verified' in the database. | 1.2
[8 empty] | T365 | Implement error handling and logging for the email sending and verification processes to ensure reliability and traceability. | 1.2
[8 empty] | T366 | Write unit tests to verify the functionality of the email service, token generation, email sending, and verification processes. | 1.2
[8 empty] | T367 | Perform end-to-end testing to ensure that the email notification is sent correctly and the verification process works as expected. | 1.2
|  |  |  | S037 | Email Notification for Phone OTP Verification | As a patient, I want to receive an email notification confirming my phone number verification so that I know my phone number has been successfully verified. | Given a patient has successfully verified their phone number using OTP, when the verification is complete, then an email notification is sent to the patient's registered email address. The email should include a message confirming the successful verification of the phone number. | T368 | Create a function `send_phone_verification_email(patient_email)` that takes the patient's email as input and sends an email notification confirming the successful verification of their phone number. | 0.55
[8 empty] | T369 | Integrate the `send_phone_verification_email` function into the phone number verification process to trigger the email notification upon successful OTP verification. | 1.2
[8 empty] | T370 | Set up an email template for the phone number verification confirmation. The template should include a message confirming the successful verification of the phone number. | 0.55
[8 empty] | T371 | Configure the email service (e.g., AWS SES) to send emails using the predefined template. Ensure the service is capable of handling the email sending process securely. | 1.2
[8 empty] | T372 | Implement error handling in the `send_phone_verification_email` function to log any issues that occur during the email sending process and provide fallback mechanisms. | 1.2
[8 empty] | T373 | Write unit tests for the `send_phone_verification_email` function to ensure it correctly sends the email notification with the appropriate content. | 0.55
[8 empty] | T374 | Write integration tests to verify that the email notification is sent upon successful OTP verification in the phone number verification workflow. | 1.2
[8 empty] | T375 | Deploy the updated phone number verification process and email notification functionality to the development environment for testing. | 1.2
[8 empty] | T376 | Conduct end-to-end testing to ensure that the email notification is sent correctly when a patient successfully verifies their phone number using OTP. | 1.2
[8 empty] | T377 | Monitor the deployment in the production environment to ensure that the email notifications are being sent as expected and address any issues that arise. | 1.2
|  |  |  | S038 | Email Notification for Report Approval | As a patient, I want to receive an email notification when a consultation report is approved by the doctor so that I am informed about the status of my medical reports. | Given a doctor has approved a consultation report, when the approval process is complete, then an email notification is sent to the patient's registered email address. The email should include details of the approved report and instructions on how to view it. | T378 | Set up an email notification service using a suitable library (e.g., Flask-Mail) to send emails from the application. | 0.55
[8 empty] | T379 | Create a function `send_email_notification` that takes the patient's email address, subject, and body content as inputs and sends an email. | 0.55
[8 empty] | T380 | Design an email template for the consultation report approval notification. The template should include placeholders for the patient's name, report details, and instructions on how to view the report. | 0.55
[8 empty] | T381 | Implement a function `generate_report_approval_email_content` that takes the patient's name and report details as inputs and returns the formatted email content using the designed template. | 0.55
[8 empty] | T382 | Create a database trigger or event listener that detects when a consultation report is approved by a doctor. | 1.2
[8 empty] | T383 | Implement a function `on_report_approval` that is called when a consultation report is approved. This function should retrieve the patient's email address and report details. | 1.2
[8 empty] | T384 | In the `on_report_approval` function, call `generate_report_approval_email_content` to generate the email content. | 0.55
[8 empty] | T385 | In the `on_report_approval` function, call `send_email_notification` with the patient's email address, a subject line (e.g., 'Your Consultation Report is Approved'), and the generated email content. | 0.55
[8 empty] | T386 | Write unit tests for `send_email_notification` to ensure it sends emails correctly. | 0.55
[8 empty] | T387 | Write unit tests for `generate_report_approval_email_content` to ensure it formats the email content correctly. | 0.55
[8 empty] | T388 | Write integration tests for `on_report_approval` to ensure it triggers the email notification correctly when a report is approved. | 1.2
[8 empty] | T389 | Deploy the email notification service and ensure it is integrated with the existing application infrastructure. | 1.2
[8 empty] | T390 | Monitor and log email notifications to ensure they are being sent successfully and troubleshoot any issues that arise. | 1.2
|  |  |  | S039 | Email Notification for Account Activity | As a patient, I want to receive email notifications for any significant account activities so that I am kept informed about my account status. | Given any significant account activity occurs (e.g., password change, profile update), when the activity is completed, then an email notification is sent to the patient's registered email address. The email should include details of the activity and any necessary follow-up actions. | T391 | Set up an email notification service using a suitable library (e.g., Flask-Mail) to send emails from the application. | 1.2
[8 empty] | T392 | Create a function to trigger email notifications for significant account activities such as password changes and profile updates. | 0.55
[8 empty] | T393 | Develop a template for the email notification that includes details of the activity and any necessary follow-up actions. | 0.55
[8 empty] | T394 | Implement logic to detect significant account activities (e.g., password change, profile update) within the application. | 1.2
[8 empty] | T395 | Integrate the email notification function with the logic that detects significant account activities to automatically send an email when such activities occur. | 1.2
[8 empty] | T396 | Ensure that the email notification function retrieves the patient's registered email address from the database. | 0.55
[8 empty] | T397 | Test the email notification function to verify that emails are sent correctly upon significant account activities. | 0.55
[8 empty] | T398 | Add logging to the email notification function to record when emails are sent and any errors that occur during the process. | 0.55
[8 empty] | T399 | Update the user interface to inform patients that they will receive email notifications for significant account activities. | 0.55
[8 empty] | T400 | Deploy the email notification service to the production environment and monitor for any issues. | 1.2