## Sheet
EpicID | EPIC TITLE | EPIC DESCRIPTION | Story ID | Story Description | Story Acceptance Criteria | Task ID | Task Description
E001 | Doctor Authentication and Security | Develop a secure login system with mobile number and OTP verification to ensure that only authorized doctors can access the application. Implement additional security measures for re-authentication to maintain data security after periods of inactivity. | S001 | As a Doctor, I want to log in using my mobile number and receive an OTP so that my access is secure and verified. | Doctor inputs mobile number and requests an OTP. System sends an OTP to the provided mobile number. Doctor enters the received OTP to log in. System verifies OTP and grants access if correct. | T001 | Design the user interface for the doctor login screen, including input fields for the mobile number and a button to request an OTP. Ensure that the design is user-friendly and accessible on various devices. Estimated completion: 3 days.
[6 empty] | T002 | Implement the backend logic to generate an OTP when a mobile number is entered and the OTP request button is clicked. This includes server-side validation of the mobile number format. Estimated completion: 2 days.
[6 empty] | T003 | Set up integration with an SMS gateway to send the OTP to the doctor's mobile number. Configure the system to handle potential errors like SMS send failure and provide appropriate feedback to the user. Estimated completion: 4 days.
[6 empty] | T004 | Develop the functionality for doctors to input the received OTP and submit it for verification. This includes creating an input field and submission button on the existing login interface. Estimated completion: 2 days.
[6 empty] | T005 | Create a secure method on the backend to verify the entered OTP against the generated OTP. This should include a time limit for OTP validity and error handling for incorrect entries. Estimated completion: 3 days.
[6 empty] | T006 | Implement login success and failure responses. On successful OTP verification, grant access to the doctor and redirect to the dashboard. On failure, display an appropriate error message and allow re-attempt. Estimated completion: 2 days.
[6 empty] | T007 | Ensure all data transmitted during the login process is secured using HTTPS to prevent interception of sensitive information such as mobile numbers and OTPs. Estimated completion: 1 day.
[6 empty] | T008 | Conduct testing across different devices and networks to ensure the login functionality works reliably and securely under various conditions. This includes testing edge cases such as multiple simultaneous login attempts and rapid re-requesting of OTP. Estimated completion: 3 days.
[6 empty] | T009 | Prepare documentation that includes details about the login process, system architecture related to login, and guidelines for troubleshooting common login issues. Estimated completion: 2 days.
[6 empty] | T010 | Plan and execute a training session for the support team on the new login system to ensure they can effectively assist doctors and address any OTP related queries or issues. Estimated completion: 1 day.
|  |  | S002 | As a Doctor, I want the application to automatically log me out after 5 minutes of inactivity and require re-authentication so that unauthorized access is prevented if I leave my device unattended. | Detect inactivity for a period of 5 minutes. Automatically log out the user after 5 minutes of inactivity. Prompt for mobile number and OTP upon next action after auto-logout. Verify OTP and grant access for successful re-authentication. | T011 | Implement inactivity detection mechanism in the application to monitor user activity and identify when no actions have been taken for a period of 5 minutes. Set a deadline to complete this task within 1 week.
[6 empty] | T012 | Develop functionality to automatically log out users after 5 minutes of detected inactivity. Include unit tests to ensure this feature works reliably. This task should be completed within 2 weeks.
[6 empty] | T013 | Create a login prompt that appears after automatic logout due to inactivity. This prompt should request the mobile number and OTP from the user. Aim to have this task done within 1.5 weeks.
[6 empty] | T014 | Set up the OTP verification system to validate the user upon re-entry after an automatic logout. Include security measures to handle potential brute force attacks. Schedule completion within 3 weeks.
[6 empty] | T015 | Integrate the inactivity detection, automatic logout, login prompt, and OTP verification features into the existing doctor's application platform, ensuring smooth operation and user experience. Allocate 1 week for integration and testing.
[6 empty] | T016 | Perform comprehensive testing of the entire inactivity detection and automatic logout process to ensure functionality aligns with the acceptance criteria. Dedicate 2 weeks for multiple rounds of testing and adjustments based on feedback.
[6 empty] | T017 | Document the development process, user manual, and troubleshooting guide for the new automatic logout and re-authentication feature. Completion expected in 1 week.
|  |  | S003 | As a Doctor, I want the system to limit the number of failed login attempts to prevent unauthorized access from brute force attacks. | Limit the number of consecutive failed login attempts to 5. Lock the account temporarily for 15 minutes after 5 failed attempts. Notify the doctor via SMS when the account is locked and unlocked. | T018 | Implement a counter mechanism in the authentication system to track the number of consecutive failed login attempts by a doctor. The counter resets after a successful login or after the account is unlocked. Time estimated to implement: 2 days.
[6 empty] | T019 | Develop functionality to lock a doctor's account for 15 minutes upon reaching the threshold of 5 consecutive failed login attempts. The lockout mechanism should prevent further login attempts during this period. Time estimated to implement: 3 days.
[6 empty] | T020 | Integrate SMS notification system to alert doctors when their account is locked and when it is unlocked. This involves configuring the SMS gateway and ensuring the messages are sent securely and reliably. Time estimated to implement: 3 days.
[6 empty] | T021 | Create automated tests to verify that the lockout mechanism and SMS notifications function correctly under various scenarios, such as multiple failed attempts, successful login after lockout, and reception of SMS notifications. Time estimated to complete: 2 days.
[6 empty] | T022 | Coordinate with the security team to review and approve the implementations for handling failed login attempts to ensure it meets security standards and complies with privacy regulations. Time estimated to complete: 1 day.
[6 empty] | T023 | Schedule a deployment of the new login security features to the staging environment for further integration testing and to gather initial feedback from a select group of users. Time estimated for deployment and initial feedback collection: 2 days.
[6 empty] | T024 | Prepare and update the doctor user guide and training materials to include information on new security measures related to failed login attempts and account lockout procedures. Time estimated to complete: 2 days.
[6 empty] | T025 | Monitor and analyze the system logs post-deployment to ensure that the new features are functioning as intended and to identify any potential issues or improvements in the account lockout and SMS notification processes. Time estimated for ongoing monitoring and analysis: 5 days.
|  |  | S004 | As a Doctor, I want my session to be secure through the use of HTTPS and unique session identifiers so that my interactions with the app are secure and private. | Ensure all data transmission is done over HTTPS. Generate a unique session identifier for each login session. Ensure session identifiers are invalidated upon logout. | T026 | Implement HTTPS for all app data transmissions: Configure the application server to enforce HTTPS protocol for all incoming and outgoing connections to ensure secure data transmission. This task should be completed within 1 week and involves updating server settings and acquiring necessary SSL/TLS certificates.
[6 empty] | T027 | Develop functionality to generate unique session identifiers: Create a method in the authentication service to generate a unique session identifier for each user upon login. This identifier will be used to track the session's validity and must be implemented securely using cryptographic methods. Target to complete this task in 2 days.
[6 empty] | T028 | Store session identifiers securely: Ensure that session identifiers are stored securely on the server using encryption. This task involves setting up encrypted storage solutions and should be completed within 3 days.
[6 empty] | T029 | Implement session identifier invalidation on logout: Develop a logout function that invalidates the session identifier when a user logs out. This function must securely erase or overwrite the session identifier. Plan for 2 days to implement and test this functionality.
[6 empty] | T030 | Test session management security: Conduct thorough testing to verify that all data transmission is done over HTTPS, unique session identifiers are generated and stored securely, and that identifiers are properly invalidated upon logout. Allocate 5 days for a complete testing cycle including unit, integration, and system tests.
[6 empty] | T031 | Document the implementation process: Create detailed documentation on the implementation of secure session management, including how to enforce HTTPS, manage session identifiers, and handle session expiration. This task should take 2 days and will involve writing up the technical processes and configuration steps.
|  |  | S005 | As a Doctor, I want to have the option to enable two-factor authentication for added security. | Provide an option in the profile settings to enable two-factor authentication. Send an OTP to the registered mobile number everytime a login attempt is made if two-factor is enabled. Require the OTP along with the usual password for successful login if two-factor is enabled. | T032 | Design a user interface option in the profile settings for enabling two-factor authentication, ensuring it is intuitive and clearly labeled.
[6 empty] | T033 | Implement backend logic to update and store the two-factor authentication setting in the doctor's profile securely.
[6 empty] | T034 | Develop functionality that triggers an OTP to be sent to the doctor's registered mobile number each time a login attempt is made when two-factor authentication is enabled.
[6 empty] | T035 | Integrate with an SMS gateway provider (like Twilio) for reliable delivery of OTPs.
[6 empty] | T036 | Modify the existing login process to require input of both the password and the OTP when two-factor authentication is enabled.
[6 empty] | T037 | Set up server-side validation to check the correctness of the OTP along with the password during the login process.
[6 empty] | T038 | Implement frontend changes to prompt for an OTP on the login screen when two-factor authentication is enabled.
[6 empty] | T039 | Carry out comprehensive testing to ensure that enabling/disabling two-factor authentication updates the system correctly and that the login process works as expected with two-factor authentication.
[6 empty] | T040 | Deploy updates to a staging environment to perform integration and security testing.
[6 empty] | T041 | Prepare documentation for end-users on how to enable and use two-factor authentication, including troubleshooting common issues.
[6 empty] | T042 | Roll out the feature to a limited user group to gather initial feedback and adjust based on the responses.
[6 empty] | T043 | Plan and execute a full deployment of the feature, including monitoring and support for any raised issues post-launch.
E002 | Patient Data Access and Management | Provide doctors with the ability to access and review comprehensive patient profiles, including health assessments and medical history, through a streamlined interface. This should help doctors prepare for and conduct consultations more effectively, although they should not be able to modify patient-entered data. | S006 | As a Doctor, I want to securely log in using my mobile number and OTP so that I can access patient data securely. | Doctor can enter mobile number on login screen. OTP is sent to the doctor's mobile number. Doctor can enter OTP to successfully log in. System locks out the user after three unsuccessful OTP attempts. | T044 | Design the user interface for the login screen where doctors can enter their mobile number. The design should be intuitive and accessible, ensuring compliance with accessibility standards. Estimated duration: 2 days.
[6 empty] | T045 | Implement the front-end code for the login screen based on the approved designs. This includes form fields for mobile number entry and OTP entry, and a submit button. Use responsive design principles to ensure compatibility across devices. Estimated duration: 3 days.
[6 empty] | T046 | Develop the backend API to receive the mobile number from the login form and trigger the OTP service. Ensure that the API can handle concurrent requests securely. Estimated duration: 3 days.
[6 empty] | T047 | Integrate an OTP service provider (like Twilio) to send an OTP to the mobile number provided by the doctor. Set up configurations for OTP validity and rate limits. Estimated duration: 2 days.
[6 empty] | T048 | Develop the backend logic to verify the entered OTP against the sent OTP. Include logic to handle cases where the OTP is incorrect or has expired. Estimated duration: 3 days.
[6 empty] | T049 | Implement a lockout mechanism that activates after three consecutive unsuccessful OTP verification attempts. The lockout should temporarily disable login capability for the user for a predefined time period. Estimated duration: 2 days.
[6 empty] | T050 | Create unit tests for each component of the login process, including mobile number input, OTP sending, OTP verification, and the lockout mechanism. Ensure comprehensive coverage to prevent regressions. Estimated duration: 3 days.
[6 empty] | T051 | Conduct integration testing to ensure that the new login system works seamlessly with the existing patient data access system. Tests should include scenarios for both successful and unsuccessful logins. Estimated duration: 2 days.
[6 empty] | T052 | Develop and integrate detailed logging for each step of the login process to aid in debugging and tracking user activities. Ensure that sensitive data like OTPs are not logged. Estimated duration: 2 days.
[6 empty] | T053 | Prepare documentation for the new login functionality, detailing the flow, configurations, and how to handle common issues like OTP failures or account lockouts. The documentation should be accessible to both developers and support teams. Estimated duration: 2 days.
[6 empty] | T054 | Plan and execute a phased rollout of the new login system, initially releasing the feature to a small percentage of users to monitor performance and gather feedback before a full rollout. Estimated duration: 1 week.
|  |  | S007 | As a Doctor, I want to access and review patient profiles and their medical history so that I can prepare for and tailor my consultations effectively. | Doctor can select a patient from a patient list in the app. Patient’s complete profile along with medical history is viewable but not editable. Profiles include all AI-generated notes and health assessments. Doctors can navigate through different sections of the medical history smoothly. | T055 | Design a user interface for the patient list where doctors can easily select a patient. Include search and filter functionalities to handle large datasets. Expected completion: 3 days.
[6 empty] | T056 | Implement backend API to retrieve patient list from the database securely. Ensure that the API can handle search queries and filter parameters. Expected completion: 4 days.
[6 empty] | T057 | Develop the functionality to display a patient's complete profile and medical history in a read-only format to ensure data cannot be edited by the doctor. Expected completion: 5 days.
[6 empty] | T058 | Integrate the display of AI-generated notes and health assessments into the patient profile view. Fetch data from AI services and display them appropriately in the profile. Expected completion: 4 days.
[6 empty] | T059 | Create a navigation system within the patient profile view that allows doctors to smoothly transition between different sections of the medical history. Implement UI components like tabs or side navigation menus. Expected completion: 3 days.
[6 empty] | T060 | Conduct a security review to ensure that all data transmissions are secure and that patient data is only accessible by authorized doctors. Expected completion: 2 days.
[6 empty] | T061 | Test the patient selection functionality with mock data to ensure robust search and filtering capabilities. Expected completion: 2 days.
[6 empty] | T062 | Perform end-to-end testing of the patient profile viewing functionality to ensure all components work together seamlessly and the data is displayed correctly. Expected completion: 3 days.
[6 empty] | T063 | Organize a training session for the development team on HIPAA compliance and data handling protocols to prevent unauthorized data modification. Expected completion: 1 day.
[6 empty] | T064 | Prepare deployment plans and migration strategies for introducing the new patient profile viewing capabilities into the existing system without downtime. Expected completion: 2 days.
[6 empty] | T065 | Schedule a review meeting with stakeholders to demonstrate the new functionalities and gather feedback for any necessary adjustments. Expected completion: 1 day.
|  |  | S008 | As a Doctor, I want to utilize an AI-powered medical scribe to document observations during consultations so that I can minimize manual data entry and focus more on patient care. | AI scribe activates by voice command or button within the app during consultation. AI accurately transcribes spoken medical notes into text. Transcribed notes can be reviewed and saved by the doctor immediately after the consultation. Transcribed data is securely saved in patient's digital profile. | T066 | Design a user interface button and voice command activation feature for the AI-powered medical scribe within the doctor's consultation application. Ensure the design is intuitive and easily accessible during consultations. Estimated completion time: 1 week.
[6 empty] | T067 | Integrate speech recognition technology that supports medical terminology into the application to enable the AI-powered medical scribe to accurately transcribe spoken notes. Choose a speech recognition provider and configure the API for medical contexts. Estimated completion time: 2 weeks.
[6 empty] | T068 | Develop functionality for the AI scribe to transcribe spoken words into text in real-time during a medical consultation. Include error handling to manage and log transcription inaccuracies. Estimated completion time: 3 weeks.
[6 empty] | T069 | Implement a review interface within the app where doctors can immediately review, edit, and confirm the accuracy of the transcribed medical notes post-consultation. Ensure this interface is user-friendly and allows for quick modifications. Estimated completion time: 2 weeks.
[6 empty] | T070 | Create a secure backend process to save the transcribed and reviewed medical notes into the patient's digital profile. Ensure the data is encrypted and conforms to HIPAA regulations for data security. Estimated completion time: 2 weeks.
[6 empty] | T071 | Conduct thorough testing of the AI-powered medical scribe feature to ensure accuracy in diverse real-world scenarios and compliance with medical documentation standards. Include unit tests, integration tests, and user acceptance testing with real doctors. Estimated completion time: 3 weeks.
[6 empty] | T072 | Prepare documentation for the AI scribe feature, covering user instructions, troubleshooting, and FAQs. Ensure the documentation is clear and accessible within the app. Estimated completion time: 1 week.
[6 empty] | T073 | Set up a feedback mechanism for doctors to report any issues or suggest improvements for the AI scribe feature, directly within the app. Use this feedback for continuous improvement of the system. Estimated completion time: 1 week.
|  |  | S009 | As a Doctor, I want to review and validate patient onboarding data inputted by AI tools to ensure accuracy before it's added to the patient's official file. | Doctors can access a section for AI-inputted data review in the patient’s profile. AI-inputted data should be clearly marked and differentiated from manually entered data. Doctors can confirm the accuracy with a digital signature or correctness checkbox. Once validated, data is marked as reviewed and locked for editing. | T074 | Design a separate section in the patient's profile interface specifically for reviewing AI-inputted data. Ensure it is visually distinct from sections containing manually entered data. Completion of the design by the UI/UX team within 1 week.
[6 empty] | T075 | Develop backend functionality to tag and store data as 'AI-inputted' vs 'manually entered'. This should be implemented in the database schema by the backend team within 2 weeks.
[6 empty] | T076 | Implement frontend functionality for doctors to access the AI-inputted data review section. This includes navigation changes and ensuring compatibility with various devices. Task to be completed by the frontend development team within 1.5 weeks.
[6 empty] | T077 | Create a digital signature or checkbox feature that allows doctors to confirm the accuracy of the AI-inputted data. This requires frontend components and backend logic to record the validation status. Estimated completion time is 1 week.
[6 empty] | T078 | Once validated by the doctor, lock the AI-inputted data for editing and mark it as reviewed in the system. Develop the backend logic to update data status and restrict further modifications. Task to be completed within 1 week.
[6 empty] | T079 | Conduct integration tests to verify that the AI-inputted data can be reviewed, validated, and locked properly without impacting other patient data. Allocate 1 week for testing.
[6 empty] | T080 | Plan a training session for doctors to educate them on how to use the new AI-data review functionality. Prepare materials and schedule the session to be conducted within 2 weeks after deployment.
[6 empty] | T081 | Deploy the new changes to a staging environment for UAT (User Acceptance Testing) involving real users (doctors). Gather feedback and make required adjustments. Set aside 2 weeks for UAT and final adjustments.
|  |  | S010 | As a Doctor, I want to securely log out of the application so that I can ensure no unauthorized access to patient data on my device. | Logout option is easily accessible from any screen within the app. Session is completely terminated upon logging out. Post logout, re-login requires mobile number and OTP verification to access. | T082 | Design a UI button for logout that is consistently visible on all screens of the doctor's interface. This button should be intuitive and easily accessible to ensure compliance with the first acceptance criteria. Estimated time for completion: 2 hours.
[6 empty] | T083 | Implement backend functionality to terminate the session completely upon clicking the logout button. This includes clearing all session-related data and cookies to prevent unauthorized access, aligning with the second acceptance criteria. Estimated time for completion: 4 hours.
[6 empty] | T084 | Develop a re-authentication process that triggers when a user attempts to log back in after logging out. This involves setting up the mobile number input, OTP request dispatch, and OTP verification mechanisms, ensuring it meets the third acceptance criteria. Estimated time for completion: 6 hours.
[6 empty] | T085 | Conduct integration testing to verify that the logout functionality works seamlessly across different devices and does not retain any session data post-logout. Estimated time for completion: 3 hours.
[6 empty] | T086 | Perform security testing to ensure that after logout, re-authentication is mandatory and no session data can be accessed without proper OTP verification. Estimated time for completion: 3 hours.
[6 empty] | T087 | Prepare documentation for the logout and re-authentication functionality, detailing the process and any necessary steps or considerations for future maintenance and updates. Estimated time for completion: 2 hours.
E003 | AI-Enhanced Medical Tools | Incorporate AI-powered tools such as a medical scribe to transcribe doctor’s observations during patient interactions and an AI-powered form input system to organize consultation data into structured patient notes. This will reduce manual data entry and enhance the accuracy of medical records. | S011 | As a Doctor, I want an AI-powered medical scribe to transcribe my verbal observations during patient interactions so that I can maintain accurate and comprehensive medical records without manual data entry. | The system accurately transcribes spoken words into text. Transcriptions are timestamped and correctly attached to the patient’s record. The system allows doctors to review and edit transcriptions before finalizing. Transcriptions are completed in real-time with minimal delay. | T088 | Research and select AI transcription technologies that are suitable for clinical environments, focusing on accuracy and real-time processing capabilities. Completion due within 2 weeks.
[6 empty] | T089 | Develop a module that integrates the chosen AI transcription technology into the existing healthcare platform, ensuring it captures and transcribes spoken words during doctor-patient interactions. Target completion in 4 weeks.
[6 empty] | T090 | Implement timestamp functionality in the transcription module to tag each transcribed entry with the exact date and time of the doctor's narration. This task should be completed within 1 week after the integration.
[6 empty] | T091 | Create a user interface that allows doctors to review, edit, and finalize transcriptions before they are added to the patient's medical record. Include functionality for easy navigation and editing. Scheduled finish in 3 weeks.
[6 empty] | T092 | Ensure that the transcription process is completed in real-time with minimal delay. Test and optimize the system for performance under typical clinical interaction loads. Completion targeted within 2 weeks of the first deployment.
[6 empty] | T093 | Conduct a pilot testing phase with a select group of doctors to use the transcription system in live patient interactions, gathering feedback on transcription accuracy, ease of review, editing capabilities, and real-time performance. Complete pilot testing and feedback collection within 4 weeks.
[6 empty] | T094 | Analyze feedback from pilot testing to identify any issues or areas for improvement in the transcription system. Plan adjustments and optimizations based on actual user experiences. Completion of analysis and planning improvements should be done within 1 week post-pilot testing.
[6 empty] | T095 | Implement the necessary improvements and optimizations to the transcription system based on feedback from the pilot testing. This task should be completed within 3 weeks after receiving feedback.
[6 empty] | T096 | Plan and conduct a final round of testing to confirm that all issues identified during pilot testing have been resolved and that the system meets all specified acceptance criteria. Finish comprehensive testing within 2 weeks.
[6 empty] | T097 | Prepare and conduct training sessions for all doctors on how to effectively use the new AI-powered medical scribe system. Include guides on accessing, reviewing, editing, and finalizing transcriptions. Schedule and complete training within 2 weeks following the final testing phase.
[6 empty] | T098 | Deploy the AI-powered transcription system across all clinical settings after successful training and final testing. Go-live scheduled within 1 week post-training.
|  |  | S012 | As a Doctor, I want to use an AI-powered form input system that automatically organizes consultation data into structured patient notes so that I can ensure data is systematically captured and easily retrievable. | AI form input accurately captures and organizes data from consultations into predefined categories. Structured data is editable and can be reviewed by doctors before saving. System provides templates for different types of consultations. Integration with EHR (Electronic Health Record) systems for seamless data transfer. | T099 | Design and develop an AI form input system that captures and categorizes consultation data into predefined templates. Ensure the system uses natural language processing to accurately interpret and organize data from spoken or typed input. Deadline: 3 weeks.
[6 empty] | T100 | Create an interface for doctors to review, edit, and confirm the accuracy of the structured data captured by the AI form input system. This interface should allow modifications before final submission and saving of the consultation notes. Deadline: 2 weeks.
[6 empty] | T101 | Develop a variety of templates for different types of consultations, such as general check-ups, follow-up visits, and specialized assessments. Collaborate with clinical experts to ensure these templates meet medical standards and are comprehensive. Deadline: 4 weeks.
[6 empty] | T102 | Integrate the AI form input system with existing Electronic Health Record (EHR) systems used by the healthcare facility. This task involves working with IT to ensure data from the AI system can be seamlessly transferred and stored in the EHR without manual intervention. Deadline: 5 weeks.
[6 empty] | T103 | Conduct a pilot test of the AI form input system with a small group of doctors to gather feedback on the accuracy of data capture and the usability of the editing interface. Use the feedback to make necessary adjustments. Deadline: 1 week post-completion of development tasks.
[6 empty] | T104 | Organize a training session for doctors to demonstrate how to use the new AI form input system and educate them on how to effectively utilize the templates and editing features. Deadline: 1 week after pilot testing.
[6 empty] | T105 | Implement security measures to ensure that the data captured and transferred by the AI form input system is compliant with healthcare regulations, such as HIPAA in the U.S., ensuring data privacy and protection. Deadline: Ongoing, with initial setup completed before pilot testing.
|  |  | S013 | As a Doctor, I want an interface where I can review, validate, and approve the AI-generated patient notes so that I can ensure the accuracy and completeness of the medical records. | The review interface is user-friendly and allows for easy editing and approval of notes. Doctors receive notifications for records that require review. Changes and approvals are logged for audit purposes. Review process is integrated within the doctors’ workflow, ensuring minimal disruption. | T106 | Design a user-friendly interface for reviewing AI-generated patient notes. Include features for easy navigation, editing, and approval of notes to meet the criteria of user-friendliness and ease of use. Estimated completion: 3 days.
[6 empty] | T107 | Develop a notification system to alert doctors when AI-generated notes are ready for review. Ensure compatibility across various devices and platforms used by doctors. Estimated completion: 2 days.
[6 empty] | T108 | Implement logging functionality to record all changes and approvals made to AI-generated notes. Ensure logs capture user ID, timestamp, and nature of the change for audit purposes. Estimated completion: 4 days.
[6 empty] | T109 | Integrate the review and approval process for AI-generated notes into the existing workflow of doctors. This may involve modifying the doctor's dashboard to include access to the review interface and ensuring minimal disruption to their current processes. Estimated completion: 5 days.
[6 empty] | T110 | Conduct usability testing with a group of doctors to ensure the review interface meets their needs and is intuitive. Gather feedback and make necessary adjustments based on the findings. Estimated completion: 2 weeks.
[6 empty] | T111 | Set up a monitoring system to track the usage and performance of the review interface, ensuring it operates efficiently and reliably within the doctor's workflow. Estimated completion: 1 week.
|  |  | S014 | As a Doctor, I want the AI tools to integrate seamlessly with our existing healthcare systems so that I can maintain a consistent workflow and avoid technology conflicts. | Ensure compatibility with major EHR systems used in healthcare. Data synchronization must be secure and comply with healthcare regulations. System should support data export and import functionalities. Minimal downtime during integration with real-time data handling capabilities. | T112 | Conduct a compatibility assessment of the AI tools with major EHR systems used in healthcare. Document the requirements for each system, identify common standards and protocols needed for integration. (Timeline: 2 weeks)
[6 empty] | T113 | Develop a secure data synchronization module that ensures encrypted transmission of data between the AI tools and existing EHR systems. Include mechanisms such as SSL/TLS for data in transit and AES for data at rest. Perform security audits to comply with healthcare regulations. (Timeline: 4 weeks)
[6 empty] | T114 | Implement data import and export functionalities in the AI tools. This should support various data formats common in healthcare systems (e.g., HL7, FHIR). Ensure these functionalities allow seamless data flow without information loss. (Timeline: 3 weeks)
[6 empty] | T115 | Plan and execute a phased integration process to minimize downtime in clinical operations. Include steps for pre-integration testing, live deployment in a controlled environment, and full rollout. Ensure real-time data handling capabilities are tested and optimized during the integration. (Timeline: 5 weeks)
[6 empty] | T116 | Set up a pilot testing phase post-integration to collect feedback and monitor the system's performance in real-time. Adjust integration mechanics based on feedback to reduce any disruptions and optimize workflows. (Timeline: 2 weeks)
[6 empty] | T117 | Develop comprehensive documentation and training materials for system administrators and IT support teams on managing and troubleshooting the integrated AI tools within the EHR systems. (Timeline: 2 weeks)
[6 empty] | T118 | Conduct regular review and maintenance sessions post-integration to ensure that all components of the AI tools function seamlessly with the EHR systems and any new updates in either system are accommodated. (Timeline: Ongoing, first review after 1 month)
|  |  | S015 | As a Doctor, I want to ensure that the AI tools have secure access controls and comply with data privacy regulations so that patient information is protected against unauthorized access. | System requires strong authentication mechanisms for access. All data transfers are encrypted. Compliance with HIPAA or relevant data protection regulations. Activity logs are maintained for security audits. | T119 | Design a strong authentication mechanism for AI tools access, incorporating multi-factor authentication (MFA) with options such as biometrics, SMS OTP, or app-based OTP. Plan to complete the design within 2 weeks.
[6 empty] | T120 | Implement encryption protocols for all data transfers involving AI tools, using AES-256 encryption standard. Target implementation and testing completion within 3 weeks.
[6 empty] | T121 | Consult with a HIPAA compliance expert to review the current AI tool's data handling methods and ensure they meet HIPAA regulations. Schedule the consultation within 1 week and plan for potential adjustments based on feedback to be deployed over the next 4 weeks.
[6 empty] | T122 | Develop and integrate a system for real-time activity logging that captures all user interactions with AI tools, including access times, types of data accessed, and user identification. Aim to have a working prototype within 4 weeks.
[6 empty] | T123 | Conduct a security audit of the newly implemented authentication and encryption measures by a third-party security firm to ensure they are robust. Organize the audit to be completed within 6 weeks from the implementation date.
[6 empty] | T124 | Prepare and conduct training sessions for the medical staff on the new security features and compliance measures of the AI tools. Plan to roll out training sessions within 2 weeks after all security measures are implemented.
[6 empty] | T125 | Set up continuous monitoring and alerting for any unauthorized access attempts or non-compliance with HIPAA regulations, using an existing security information and event management (SIEM) system. Complete setup within 5 weeks.
E004 | Medical Resource Accessibility | Integrate access to a library of medical resources, research papers, and continuing education materials to help doctors stay updated on the latest medical advances and treatment options. Include functionalities for sharing relevant information with patients to aid in their understanding of their condition and treatment. | S016 | As a doctor, I want to access an integrated library of medical resources and research papers so that I can stay updated on the latest medical advances and treatment options. | Ensure the library is regularly updated with the latest research and publications. Provide search and filter capabilities to quickly find relevant documents. Allow downloading and offline access to materials. | T126 | Design and set up a database schema for storing medical resources and research papers, ensuring fields for metadata such as publication date, author, and topic are included. Task to be completed within 1 week by the database team.
[6 empty] | T127 | Develop a backend API to handle CRUD operations for the medical resources library. This includes endpoints for creating, reading, updating, and deleting documents, with completion expected in 2 weeks by the backend development team.
[6 empty] | T128 | Implement a periodic update mechanism to fetch the latest research and publications from predefined medical journals and databases. This task should be automated using a scheduled script or service, developed over 3 weeks by a backend developer.
[6 empty] | T129 | Create an indexing and search functionality using Elasticsearch or a similar service to allow fast and efficient searching of documents based on various criteria. Implementation should be done in 2 weeks by the search engine specialist.
[6 empty] | T130 | Develop front-end interfaces for accessing the library, with features for searching, filtering, and sorting documents. Include responsive design to ensure usability across devices. Task to be completed in 3 weeks by the front-end team.
[6 empty] | T131 | Enable document download functionality with secure access, ensuring materials can be saved for offline use. Include PDF and other relevant formats. This should be implemented in 1 week by a full-stack developer.
[6 empty] | T132 | Test all functionalities including database operations, search and filter capabilities, and download mechanisms to ensure they work seamlessly and securely. Testing phase to be completed in 1 week by the QA team.
[6 empty] | T133 | Deploy the library system to a staging environment for internal review and feedback. Adjust based on feedback and prepare for production deployment. Staging review and adjustments to be completed in 1 week.
[6 empty] | T134 | Document the usage instructions and technical details of the medical resources library for both internal maintenance and end-user guidance. Documentation to be prepared in 1 week by the technical writing team.
[6 empty] | T135 | Monitor and optimize the performance of the library system post-launch, addressing any issues related to load times or user accessibility. Ongoing monitoring to be set up by the IT support team.
|  |  | S017 | As a doctor, I want to have access to continuing education modules so that I can further my knowledge and meet my professional development requirements. | Modules must be accredited and count towards continuing education credits. Include a variety of formats such as video, articles, and interactive content. Track progress and completion of modules. | T136 | Research and partner with accredited education providers to source continuing education modules that are eligible for credits. Aim to finalize partnerships within 4 weeks.
[6 empty] | T137 | Design a content management system (CMS) interface for uploading and categorizing educational modules in various formats (videos, articles, interactive content). Development should start by week 5 and end by week 8.
[6 empty] | T138 | Implement a multimedia handling system to support video and interactive content without performance issues. Plan integration tests with the CMS in week 9.
[6 empty] | T139 | Develop a user interface within the doctor’s portal for accessing continuing education modules. Include filters for module format and accreditation status. Scheduled for completion by week 10.
[6 empty] | T140 | Create a back-end system to track each doctor's progress and completion of modules. Include functionality to save and resume modules. Target to complete by week 12.
[6 empty] | T141 | Test the entire module access and tracking system for bugs and usability issues in a staging environment before going live in week 13.
[6 empty] | T142 | Prepare and conduct a training session for doctors on how to use the continuing education features by the end of week 14.
[6 empty] | T143 | Launch the continuing education module feature and monitor usage and performance metrics for the first month post-launch.
|  |  | S018 | As a doctor, I want to easily share relevant medical information with patients so that they can better understand their condition and treatment options. | Enable secure sharing of information directly to patients' mobile devices or emails. Allow customization of what information is shared to suit individual patient needs. Provide templates for common conditions and treatments for quick sharing. | T144 | Design and develop a secure API to facilitate the transfer of medical information from the doctor's portal to the patient's mobile device or email. Ensure end-to-end encryption for data security. Estimated completion time: 2 weeks.
[6 empty] | T145 | Create a user interface on the doctor's portal for selecting the type of information to be shared with patients. This interface should include checkboxes or dropdown menus for different categories of information. Estimated completion time: 1 week.
[6 empty] | T146 | Implement a customization feature in the doctor's portal that allows doctors to tailor the information based on the specific needs of each patient, such as adjusting the level of detail or adding personalized notes. Estimated completion time: 1.5 weeks.
[6 empty] | T147 | Develop a set of pre-defined templates for common conditions and treatments that doctors can quickly select and send to patients. These templates should be editable to accommodate modifications by the doctor. Estimated completion time: 2 weeks.
[6 empty] | T148 | Ensure compliance with healthcare regulations such as HIPAA when sharing medical information to protect patient privacy. Include consent forms or disclaimers as necessary. Estimated completion time: 1 week.
[6 empty] | T149 | Test the entire system for security vulnerabilities and ensure that only authorized personnel can access and send patient information. Include penetration testing and encryption validation. Estimated completion time: 2 weeks.
[6 empty] | T150 | Prepare training materials and conduct training sessions for doctors on how to use the new features for sharing information with patients. Focus on security practices and customization options. Estimated completion time: 1 week.
[6 empty] | T151 | Roll out the feature in a phased manner starting with a pilot group of doctors and gather feedback to make necessary adjustments before a full-scale launch. Estimated completion time: 3 weeks.
|  |  | S019 | As a doctor, I want to provide educational tools to patients so that they can learn about their health conditions in an interactive manner. | Include multimedia resources such as videos, infographics, and diagrams. Interactive quizzes to test patients' understanding of their conditions. Tools should be accessible via mobile and web platforms to accommodate all patients. | T152 | Design and develop an interactive multimedia content library that includes videos, infographics, and diagrams. Ensure compatibility across both mobile and web platforms. (Deadline: 3 weeks from project start, Responsible: Front-end Development Team)
[6 empty] | T153 | Implement interactive quizzes related to various health conditions within the educational tools section. Include features for instant feedback and scoring to engage users. (Deadline: 4 weeks from project start, Responsible: Back-end Development Team)
[6 empty] | T154 | Ensure all multimedia content and interactive tools are fully responsive and accessible on mobile devices and web browsers, testing on a range of devices and operating systems. (Deadline: 5 weeks from project start, Responsible: QA Team)
[6 empty] | T155 | Create backend APIs to manage and serve multimedia content and quiz data dynamically, ensuring scalability and security. (Deadline: 3 weeks from project start, Responsible: Back-end Development Team)
[6 empty] | T156 | Set up a content management system (CMS) for admins to easily add, update, or remove multimedia resources and quizzes without developer intervention. (Deadline: 4 weeks from project start, Responsible: Back-end Development Team)
[6 empty] | T157 | Develop user interfaces for educational tools that are intuitive and user-friendly, with clear navigation and accessible design. (Deadline: 3 weeks from project start, Responsible: UI/UX Design Team)
[6 empty] | T158 | Integrate analytics to track user engagement with multimedia resources and quizzes, allowing for future improvements based on user interaction data. (Deadline: 6 weeks from project start, Responsible: Data Analysis Team)
[6 empty] | T159 | Conduct user acceptance testing with a group of doctors and patients to gather feedback on the usability and educational value of the multimedia resources and quizzes. (Deadline: 7 weeks from project start, Responsible: QA Team)
[6 empty] | T160 | Prepare documentation and training materials for system administrators and end-users to facilitate the adoption and effective use of the new educational tools. (Deadline: 8 weeks from project start, Responsible: Technical Writing Team)
[6 empty] | T161 | Launch a pilot program to introduce the educational tools to a limited user group before a full-scale rollout, to address any unforeseen issues and gather initial user feedback. (Deadline: 9 weeks from project start, Responsible: Project Management Team)
|  |  | S020 | As a doctor, I want to receive feedback on the educational material provided to patients so that I can improve the resources and their delivery. | Implement a feedback mechanism where patients can rate and comment on materials. Collect and analyze feedback data to identify areas for improvement. Provide monthly reports on feedback trends and suggested enhancements. | T162 | Design and implement a feedback form for educational materials that allows patients to submit a star rating (1-5) and text comments. Ensure fields for rating and comments are mandatory. Set implementation completion within 2 weeks.
[6 empty] | T163 | Develop a backend service to securely store patient feedback on educational materials. Include fields for user ID, material ID, rating, comments, and timestamp. Ensure data privacy compliance. Completion due within 3 weeks.
[6 empty] | T164 | Create a data aggregation and analysis tool to process feedback from educational materials, categorize comments, and calculate average ratings and trends. Plan to deploy the tool within 4 weeks.
[6 empty] | T165 | Implement a reporting module to generate monthly feedback reports on educational materials. Reports should include average ratings, common themes in comments, and recommendations for improvements. Schedule the first report generation within 6 weeks.
[6 empty] | T166 | Integrate feedback mechanisms directly into the educational materials section of the app, with clearly visible feedback buttons or links. Test user interface for ease of use and visibility. Complete integration and testing in 3 weeks.
[6 empty] | T167 | Set up a scheduler in the system to automatically generate and distribute feedback trend reports to doctors on the first day of each month. Ensure secure email distribution. Complete setup within 1 week.
[6 empty] | T168 | Conduct a training session for doctors on how to interpret feedback reports and how to implement suggested enhancements based on patient feedback. Arrange the session within 7 weeks from project start.
[6 empty] | T169 | Perform comprehensive testing of the entire feedback system, including form submission, data storage security, analysis tool accuracy, and report generation, to ensure all components function as expected. Complete testing phase within 8 weeks.
E005 | Doctor Profile Management | Allow doctors to manage their own profiles within the app, including updating personal and professional information such as hospital affiliation and contact details, ensuring that the information remains current and accurate. | S021 | As a Doctor, I want to update my personal information such as name, profile picture, and contact details so that my profile remains current and accurate. | Doctor can access their profile edit page. Fields for name, profile picture, and contact details are editable. Changes are saved and immediately reflected in the doctor's profile. Ensure data validation for contact details. | T170 | Implement backend API endpoint to handle GET requests for fetching existing doctor profile information for the profile edit page. Ensure it retrieves name, profile picture, and contact details. Task should be completed by the backend team within 2 days.
[6 empty] | T171 | Design and develop the front-end interface for the doctor's profile edit page. The interface should include form fields for name, profile picture, and contact details. Include a 'Save' button to submit changes. UI/UX team should complete this within 3 days.
[6 empty] | T172 | Implement backend API endpoint for POST requests to update doctor profile information including name, profile picture, and contact details. This task includes ensuring that the new data replaces the old data in the database. Backend team should complete this within 2 days.
[6 empty] | T173 | Create client-side JavaScript functionality to handle the submission of the profile edit form, including data validation for contact details (e.g., valid email format, phone number length). This task should be completed by the front-end team in 1 day.
[6 empty] | T174 | Integrate the front-end profile edit form with the backend API endpoints. This includes fetching current profile data to populate the form and sending updated data to the backend. This integration task should be handled by the front-end team and completed in 2 days.
[6 empty] | T175 | Implement immediate feedback on the UI after successful profile update, such as a confirmation message or a visual indication that changes have been saved. Front-end team should implement this within 1 day.
[6 empty] | T176 | Conduct comprehensive testing of the new profile edit functionality, covering both front-end and backend systems. This includes testing form submission, data validation, API endpoints, and database updates. QA team should complete testing in 3 days.
[6 empty] | T177 | Set up security measures to ensure that only the authenticated doctor can access and edit their profile. This includes implementing proper authentication checks and possibly using session tokens. Security team to review and implement necessary measures within 2 days.
[6 empty] | T178 | Prepare deployment scripts and migration strategies to deploy the new profile edit functionality to the production environment. DevOps team should prepare and test deployment within 2 days.
[6 empty] | T179 | Document the new profile management features including details on how to access the profile edit page, how to edit fields, expected validation errors, and troubleshooting steps. Technical writing team should complete documentation within 3 days.
|  |  | S022 | As a Doctor, I want to update my hospital affiliation details so that my current working institution is accurately reflected in my profile. | Doctor can access a section in the profile to update hospital affiliation. Doctor can select their affiliated hospital from a pre-populated list of registered institutions. Updates are saved and visible on the profile immediately after submission. System verifies the affiliation with the hospital database before updating. | T180 | Design a UI section in the doctor’s profile for updating hospital affiliation details. Include a dropdown menu populated with registered hospitals. Ensure the UI is intuitive and easy to access as per acceptance criteria.
[6 empty] | T181 | Develop the backend logic to fetch the list of registered hospitals from the hospital database. This list will populate the dropdown menu in the doctor’s profile update section.
[6 empty] | T182 | Implement a feature that allows doctors to select their new hospital affiliation from the dropdown menu and submit the update. This should trigger a backend process to update their profile information.
[6 empty] | T183 | Create an API endpoint that handles the submission of updated hospital affiliation details. This endpoint should update the doctor’s profile in the database and return a success response.
[6 empty] | T184 | Develop a verification process that checks the selected hospital against the hospital database to confirm its existence and validity before updating the doctor’s profile.
[6 empty] | T185 | Integrate real-time feedback on the profile update page showing the status of the update (e.g., updating, successful update, error in update) to enhance user experience and align with the acceptance criteria.
[6 empty] | T186 | Set up a notification mechanism that alerts the doctor once the hospital affiliation update is successfully saved. This could be in the form of a popup message or a banner on the profile page.
[6 empty] | T187 | Implement rigorous security measures to ensure that the hospital affiliation update process is secure and that data integrity is maintained. This includes using HTTPS for data transmission and implementing proper authentication and authorization checks.
[6 empty] | T188 | Conduct unit testing of the new hospital affiliation update feature to ensure that it works as expected. This includes testing the UI, API endpoint, database updates, and verification process.
[6 empty] | T189 | Plan and execute integration testing with the hospital database to ensure that the verification and update processes interact correctly with external systems.
[6 empty] | T190 | Prepare and update system documentation to include details on the new hospital affiliation update feature, covering both the technical implementation and the user interface. Ensure that the documentation is clear and accessible for future reference.
[6 empty] | T191 | Schedule a training session for doctors to demonstrate the new hospital affiliation update feature, ensuring they understand how to access and use it effectively.
|  |  | S023 | As a Doctor, I want to update my medical credentials including my MD ID so that my qualifications are up-to-date for patient and peer review. | Doctor can edit their MD ID and other credentials through their profile settings. System checks the validity of the MD ID against a medical credentials database. Updates are saved and reflected in the profile once validated. | T192 | Design and implement a user interface for doctors to access and edit their MD ID and other credentials in the profile settings section of the app. This task includes creating input fields and edit buttons in the UI. Ensure the interface is user-friendly and accessible. Estimated completion time: 2 days.
[6 empty] | T193 | Develop backend functionality to handle the submission of updated medical credentials, including MD ID. This includes setting up API endpoints to receive data from the frontend, process it, and prepare for validation. Estimated completion time: 3 days.
[6 empty] | T194 | Integrate a service to check the validity of the MD ID against a medical credentials database. This task involves creating a connection to an external database or service that can validate MD IDs, handling the validation logic, and returning the validation status. Estimated completion time: 3 days.
[6 empty] | T195 | Implement logic to save the updated MD ID and credentials to the doctor's profile in the database only if the validation is successful. Ensure transactional integrity, such that no data is saved unless all validations pass. Estimated completion time: 2 days.
[6 empty] | T196 | Create unit tests to ensure that the edit functionality works correctly, especially the validation checks and data saving logic. This includes writing tests for successful edits, handling of invalid data, and failure to pass validation. Estimated completion time: 2 days.
[6 empty] | T197 | Update the user documentation to include instructions on how to update MD IDs and other credentials, highlighting the validation process and any constraints related to credentials update. Estimated completion time: 1 day.
[6 empty] | T198 | Conduct a peer review session to evaluate the implemented features for editing MD ID and credentials, focusing on code quality, security measures, and adherence to the acceptance criteria. Estimated time: 1 day.
[6 empty] | T199 | Deploy the changes to a staging environment to simulate real-world usage and conduct integration testing, ensuring that the new functionality interacts correctly with existing features and external systems. Estimated time: 2 days.
[6 empty] | T200 | Prepare and deliver a training session for the support team on the new credentials updating feature, explaining the validation process, potential user queries, and troubleshooting common issues. Estimated completion time: 1 day.
[6 empty] | T201 | Monitor and gather feedback on the functionality from real users in the production environment post-deployment, and plan for any necessary adjustments or improvements based on the feedback. Ongoing for 2 weeks post-launch.
|  |  | S024 | As a Doctor, I want to manage the privacy settings of my profile to control what information is visible to patients and other doctors. | Doctors can access privacy settings from their profile dashboard. Options available to set visibility for contact details, hospital affiliation, and credentials. Changes are applied immediately and affect what others see on the doctor’s profile. | T202 | Design the User Interface (UI) for the privacy settings section in the doctor's profile dashboard, ensuring it is intuitive and accessible. This task should be completed within 3 working days.
[6 empty] | T203 | Implement front-end functionality for the privacy settings section, allowing doctors to view and change visibility options for their contact details, hospital affiliation, and credentials. Target to complete this implementation in 5 working days.
[6 empty] | T204 | Develop back-end services to handle the updating of privacy settings. This includes API endpoints to retrieve current settings and to save updated settings. This task should be completed within 5 working days.
[6 empty] | T205 | Integrate front-end and back-end services for the privacy settings feature, ensuring changes are reflected immediately in the doctor's profile and visible to others based on the updated settings. Set a deadline of 2 working days for integration testing.
[6 empty] | T206 | Conduct a series of tests including unit testing, integration testing, and user acceptance testing, to ensure that the functionality meets all acceptance criteria and is bug-free. Allocate 3 working days for this task.
[6 empty] | T207 | Prepare and update system documentation to include details about the new privacy settings feature, ensuring that technical support teams and developers can understand and maintain the feature. Complete this documentation within 2 working days.
[6 empty] | T208 | Plan and execute a training session for doctors to educate them on how to use the new privacy settings feature effectively. This should be scheduled within 1 week of feature deployment and take approximately 2 hours.
[6 empty] | T209 | Deploy the new privacy settings feature to the production environment after all testing is completed and ensure it goes live by the end of the development cycle, approximately 20 working days from the start of the project.
[6 empty] | T210 | Monitor the feature post-deployment for any potential issues and gather feedback from users to ensure it meets their needs effectively. Continuous monitoring for the first month after release.
|  |  | S025 | As a Doctor, I want to securely logout from the application to ensure my account remains secure when not in use. | Logout button is easily accessible from any screen within the doctor’s interface. Upon logout, the user is redirected to the login screen. Session is terminated on the server to prevent unauthorized access. | T211 | Design a universally accessible logout button that is visible and can be reached from any interface screen within the doctor's app module. Task must be completed within 2 days.
[6 empty] | T212 | Implement a logout function that ensures the user is redirected to the login screen after successful logout. Include a session validation check to confirm logout before redirection. Task must be completed within 3 days.
[6 empty] | T213 | Develop backend functionality to terminate all active sessions on the server once a logout request is made. This includes invalidating session tokens. Task should be tested to ensure no data leakage or unauthorized access post-logout. Task must be completed within 4 days.
[6 empty] | T214 | Conduct integration testing to verify that the logout button reliably performs the required actions across all platforms (web, iOS, Android). This should include testing the session termination on the server. Task must be completed within 3 days after the development tasks are completed.
[6 empty] | T215 | Perform User Acceptance Testing (UAT) with a focus group of doctors to ensure the logout functionality meets their expectations and is easy to use from any screen within the app. Collect feedback and make necessary adjustments. Task must be scheduled within 1 week of completing integration testing.
[6 empty] | T216 | Document the logout feature implementation details, including the user flow, server-side session management, and secure redirection protocols. Ensure the documentation is ready for review by the system security team to validate compliance with best practices. Documentation should be completed within 2 days post-development.
E001 | Patient Registration and Profile Management | Enable patients to register, create, and manage their profiles using mobile number and OTP, allowing them to link/unlink to a hospital, update personal and health information, and manage security settings. | S001 | As a Patient, I want to register using my mobile number and OTP so that I can securely create my own profile. | Registration page accessible from the mobile app Fields for mobile number entry OTP sent to entered mobile number Validation of OTP to complete registration Confirmation message upon successful registration | T001 | Design and implement a registration page in the mobile app that is user-friendly and accessible directly from the main menu. This task should be completed within 1 week by the UI/UX design team.
[6 empty] | T002 | Develop input fields specifically for mobile number entry on the registration page, including appropriate validation rules (e.g., format, mandatory field). This should be achieved by the front-end development team within 3 days.
[6 empty] | T003 | Integrate the backend system to send an OTP to the entered mobile number using an SMS gateway service. This should include error handling for failed SMS sends and be completed within 2 weeks by the backend development team.
[6 empty] | T004 | Implement OTP validation logic to verify the user-entered OTP against the server-stored value. This should include a timeout for OTP validity and should be completed within 1 week by the backend development team.
[6 empty] | T005 | Upon successful registration, trigger a confirmation message to the user and redirect them to their newly created profile page. This task should be implemented by the front-end team and should take 2 days.
[6 empty] | T006 | Conduct comprehensive testing, including unit tests for each component (input validation, OTP sending and validation) and integration tests for the registration process. This testing phase should be completed within 1 week by the QA team.
[6 empty] | T007 | Ensure the registration page and process are compliant with data protection regulations, including secure handling and storage of mobile numbers and OTPs. Compliance verification should be completed within 1 week by the security team.
|  |  | S002 | As a Patient, I want to link my profile to a hospital using a security code so that my medical records can be integrated and accessed by the hospital. | Option to enter a security code provided by the hospital Verification of the security code Linking patient profile to hospital upon successful verification Ability to unlink profile from the hospital Confirmation messages for both linking and unlinking actions | T008 | Design the UI element for entering the security code into the patient's profile page, ensuring it is user-friendly and accessible.
[6 empty] | T009 | Implement the backend service to verify the entered security code against the hospital's database, using secure API calls.
[6 empty] | T010 | Develop the functionality to link the patient's profile to the hospital database upon successful security code verification, ensuring data consistency and integrity.
[6 empty] | T011 | Create a feature in the patient profile settings that allows for unlinking from the hospital, including backend support to securely sever connections.
[6 empty] | T012 | Implement confirmation dialogs that appear after successful linking and unlinking actions, providing clear feedback to the user.
[6 empty] | T013 | Conduct testing to ensure that the security code entry, verification, linking, and unlinking processes all handle common edge cases and error handling smoothly.
[6 empty] | T014 | Prepare and deploy database migrations necessary for storing links between patient profiles and hospitals, ensuring all privacy and security standards are met.
[6 empty] | T015 | Create comprehensive documentation on the process of linking and unlinking patient profiles to hospitals for future reference and support personnel.
|  |  | S003 | As a Patient, I want to update my personal information such as age, gender, and contact details so that my profile remains up-to-date. | Access to edit personal information from profile settings Fields to update age, gender, phone number, and other personal details Save changes functionality Confirmation message upon successful update | T016 | Design the user interface for the personal information editing section in the profile settings. Ensure it is accessible and user-friendly, with clear labels for editing age, gender, phone number, and other personal details. Completion target: 3 days.
[6 empty] | T017 | Implement input fields for age, gender, phone number, and other personal details within the profile settings page. Validate inputs to ensure data integrity (e.g., phone numbers in correct format, age as numeric input). Completion target: 5 days.
[6 empty] | T018 | Develop the backend functionality to update and store the changed personal information in the database securely. This includes handling POST requests when a user submits their updated details. Completion target: 5 days.
[6 empty] | T019 | Create a 'Save Changes' button on the profile update page. Ensure it triggers the correct events to capture and process the updated information when clicked. Completion target: 2 days.
[6 empty] | T020 | Implement a confirmation message that appears to users upon successfully updating their profile. This message should confirm that their personal information has been updated. Completion target: 2 days.
[6 empty] | T021 | Conduct unit testing on the new fields and functionality to ensure that all data is processed correctly and that no existing features are broken. Include tests for successful data submission and error handling. Completion target: 3 days.
[6 empty] | T022 | Schedule a review session with the QA team to go over the implemented features and make sure everything aligns with the user story and acceptance criteria. Gather feedback and implement necessary adjustments. Completion target: 2 days after initial testing.
[6 empty] | T023 | Prepare user documentation and help content for updating personal information on the profile settings page. This should guide users on how to access and use the new functionality. Completion target: 3 days.
|  |  | S004 | As a Patient, I want to update my health information like allergies, medications, and chronic conditions to keep my health records accurate. | Access to a section for health information within the profile Options to add or modify information about allergies, medications, and conditions Save functionality for any changes made Confirmation message upon successful updates | T024 | Design a dedicated UI section for health information management within the patient profile. This should include tabs or sections for allergies, medications, and chronic conditions. Ensure the design is user-friendly and accessible. Estimated completion: 3 days.
[6 empty] | T025 | Implement the backend API to handle CRUD operations (Create, Read, Update, Delete) for health information such as allergies, medications, and chronic conditions. Ensure APIs are secure and data is validated before processing. Estimated completion: 5 days.
[6 empty] | T026 | Develop the frontend functionality to interact with the backend API. This includes forms to add and modify health information and mechanisms to retrieve and display existing data. Include input validations to prevent incorrect data entry. Estimated completion: 4 days.
[6 empty] | T027 | Integrate a save button with functionality to update the user's health information in the database. Ensure changes are only submitted when the user confirms, to prevent accidental data loss. Estimated completion: 2 days.
[6 empty] | T028 | Implement a confirmation message that appears after successful updating of health information. This should be clear and indicate exactly what information has been updated. Estimated completion: 1 day.
[6 empty] | T029 | Conduct comprehensive testing to ensure that all components (UI, APIs, data validation, save functionality) work seamlessly together and data integrity is maintained. Include unit tests, integration tests, and user acceptance testing. Estimated completion: 3 days.
[6 empty] | T030 | Prepare documentation that covers the new health information management features, including screenshots and step-by-step instructions on how to use the new features. This documentation should be accessible from within the app. Estimated completion: 2 days.
|  |  | S005 | As a Patient, I want to manage my security settings, including changing passwords and setting up security questions, to enhance the security of my account. | Access to security settings from the profile menu Options to change password and setup or change security questions Effective validation on all inputs Confirmation message upon successful changes | T031 | Design the UI for the security settings menu accessible from the profile menu ensuring it aligns with the app's overall design language and is user-friendly. Include options for password change and security question setup. Estimated completion: 3 days.
[6 empty] | T032 | Implement the backend API to support password changes. This should include secure handling of passwords, hashing for storage, and integration with the existing authentication system. Estimated completion: 5 days.
[6 empty] | T033 | Develop functionality for adding and modifying security questions. This includes storing questions and hashed answers securely in the database. Estimated completion: 4 days.
[6 empty] | T034 | Create input validation rules for new passwords and security answers to ensure they meet security standards (e.g., minimum length, complexity). Implement these validations on both the client and server sides. Estimated completion: 3 days.
[6 empty] | T035 | Integrate real-time feedback on input validation for password and security question answers in the UI to enhance user experience by instantly informing users if their inputs are valid. Estimated completion: 2 days.
[6 empty] | T036 | Program confirmation messages to be displayed upon successful update of security settings. Ensure these messages are clear and provide reassurance that the changes have been securely saved. Estimated completion: 1 day.
[6 empty] | T037 | Conduct a security review of the new features, including penetration testing and code review, to ensure there are no vulnerabilities introduced. Estimated completion: 5 days.
[6 empty] | T038 | Prepare user documentation and help content for managing security settings, including how to change passwords and set up security questions. Estimated completion: 2 days.
[6 empty] | T039 | Develop an automated test suite to test the new security settings features comprehensively, including UI, API, and integration tests. Estimated completion: 4 days.
[6 empty] | T040 | Stage the changes in a pre-production environment and conduct user acceptance testing (UAT) to ensure the updates meet user expectations and acceptance criteria. Gather feedback and make necessary adjustments. Estimated completion: 3 days.
[6 empty] | T041 | Plan and execute the deployment of the security settings update to the production environment, including database migrations and application updates. Ensure minimal downtime during deployment. Estimated completion: 2 days.
|  |  | S006 | As a Patient, I want to be able to securely log out from the application to ensure my account is secure when not in use. | Logout option easily accessible in the application Confirmation prompt to avoid accidental logouts Redirection to the login screen post-logout Clear session data on logout to prevent unauthorized access | T042 | Design a logout button that is easily accessible across all screens of the mobile application, ensuring it is visible and reachable irrespective of the user's current navigation within the app. Task should be completed within 3 days.
[6 empty] | T043 | Implement a confirmation prompt when the user selects the logout option. This prompt should ask for user confirmation to avoid accidental logouts, and include both 'Confirm' and 'Cancel' options. The implementation should be tested and completed within 2 days.
[6 empty] | T044 | Develop the functionality that redirects users to the login screen upon successful logout. Ensure the transition is smooth and the login screen is ready to accept new login credentials. This task should be achieved within 2 days.
[6 empty] | T045 | Ensure all session data is cleared from the device upon logout. This includes removing any cached user credentials, session tokens, and any sensitive information stored temporarily. Include automated tests to verify that data clearance is thorough and secure. Expected completion time is 3 days.
[6 empty] | T046 | Conduct integration testing to ensure that the logout process works seamlessly and satisfies all acceptance criteria. This should include testing on multiple devices to ensure compatibility and should be completed within 2 days.
[6 empty] | T047 | Review the security standards applied to the logout process to ensure it complies with industry best practices for data protection and privacy. This review should be completed in 1 day and might involve consultation with a security expert.
E002 | AI-Powered Health Assessments | Provide a suite of AI-driven tools for patients to conduct self-assessments including general health, mental health, and quality of life assessments, with both written and voice input capabilities. | S007 | As a patient, I want to be able to register and create a profile using my mobile number and OTP so that I can securely access the health assessment tools. | Successful registration using mobile number and OTP Ability to create and edit a personal profile System verifies the user's identity before profile creation | T048 | Design a mobile-friendly registration form that includes fields for entering a mobile number and requesting an OTP. The design should ensure clarity and ease of use on various devices.
[6 empty] | T049 | Implement backend functionality to send an OTP to the mobile number entered by the user. This should include integration with an SMS gateway that can deliver OTPs effectively across different mobile carriers.
[6 empty] | T050 | Develop frontend functionality for users to enter the received OTP and submit for verification. This should include input validation to ensure OTP format is correct before submission.
[6 empty] | T051 | Create backend logic to verify the entered OTP against the one sent to the user's mobile phone. Upon successful verification, allow the user to proceed to profile creation.
[6 empty] | T052 | Implement a user profile creation interface post-OTP verification, allowing the user to enter personal information such as name, age, and contact details. Include input fields and appropriate validations for each.
[6 empty] | T053 | Set up database schemas to store user registration and profile information securely, ensuring data privacy and protection standards are met.
[6 empty] | T054 | Develop functionality for users to edit their profile after creation. This should include mechanisms to securely authenticate the user before allowing access to edit operations.
[6 empty] | T055 | Implement system checks to verify the user's identity using the mobile number and OTP before creating the profile, ensuring no duplicate profiles are created for the same mobile number.
[6 empty] | T056 | Conduct thorough testing of the registration and profile creation process, covering scenarios such as invalid inputs, failed OTP verification, and successful profile creation, to ensure system robustness and user data integrity.
[6 empty] | T057 | Prepare user documentation and help sections explaining how to register and create a profile, including troubleshooting tips for issues like OTP not received.
|  |  | S008 | As a patient, I want to complete a general health assessment using AI-driven tools so that I can understand my current health status and receive personalized health advice. | Ability to initiate and complete a general health assessment AI adapts questions based on previous answers Results are summarized and personalized health advice is provided | T058 | Design and implement a user interface for initiating a general health assessment. Include a start button and instructions. Ensure the interface is accessible and user-friendly. Completion expected within 1 week.
[6 empty] | T059 | Develop backend logic to handle the initiation and progression of health assessments. This includes session management and state saving to allow users to pause and resume the assessment. Target completion in 2 weeks.
[6 empty] | T060 | Integrate AI capabilities to adapt subsequent questions based on previous answers provided by the user. Use machine learning models that process user responses and dynamically generate follow-up questions. Aim to complete integration and initial testing within 3 weeks.
[6 empty] | T061 | Implement functionality to summarize assessment results at the end of the session. This should include a clear presentation of the user’s health status and any notable findings. Completion targeted within 1 week after AI integration.
[6 empty] | T062 | Create a system to provide personalized health advice based on the assessment results. This system should analyze the results and use a knowledge base to generate relevant health tips and recommendations. Expected to be ready for integration testing in 2 weeks.
[6 empty] | T063 | Conduct a thorough testing phase for the entire general health assessment feature, including unit tests, integration tests, and user acceptance testing. Allocate 2 weeks for this testing phase.
[6 empty] | T064 | Prepare and maintain documentation throughout the development process, detailing the architecture, code, and usage of the health assessment feature. Documentation should be updated in real-time with development.
[6 empty] | T065 | Setup a feedback mechanism post-assessment to gather user insights and areas for improvement. This should be incorporated into the system within 1 week after the testing phase.
|  |  | S009 | As a patient, I want to use voice input to answer health assessment questions so that I can complete assessments more naturally and conveniently. | System accurately transcribes spoken responses Voice input is available for all assessment questions Responses via voice are captured and processed correctly by the AI | T066 | Research and select a suitable voice recognition API or library that supports accurate transcription of spoken language into text. Ensure compatibility with the project's technical stack and user demographics. Deadline: 1 week.
[6 empty] | T067 | Integrate the selected voice recognition API into the existing health assessment platform. Set up initial configurations and ensure it can handle multiple languages if necessary. Deadline: 2 weeks.
[6 empty] | T068 | Develop a user interface component on the mobile app for voice input. This should include a microphone button that users can tap to start recording their responses. Ensure the design is accessible and easy to use. Deadline: 1 week.
[6 empty] | T069 | Implement functionality to activate and deactivate voice input during health assessments, allowing users to switch between voice and text input as needed. Deadline: 1 week.
[6 empty] | T070 | Create a testing protocol to evaluate the accuracy of the voice transcription in various environments and accents. Include a diverse group of test users to cover a wide range of voice patterns. Deadline: 3 weeks.
[6 empty] | T071 | Develop error handling strategies for cases where voice input is unclear or the API fails to transcribe accurately. Provide users with suggestions to repeat or type their response if transcription fails. Deadline: 1 week.
[6 empty] | T072 | Integrate the voice input data into the health assessment processing system. Ensure that responses are captured, processed by the AI, and stored securely. Deadline: 2 weeks.
[6 empty] | T073 | Implement privacy measures to ensure that all voice data is encrypted and handled according to compliance with data protection regulations. Deadline: 1 week.
[6 empty] | T074 | Conduct a pilot test to assess the functionality, user experience, and accuracy of the voice input feature in real-world conditions. Gather feedback and prepare for final adjustments. Deadline: 2 weeks.
[6 empty] | T075 | Optimize the system based on feedback and test results to improve transcription accuracy and user interface responsiveness. Deadline: 2 weeks.
[6 empty] | T076 | Prepare documentation for the voice input feature, including user help guides and technical support material. Deadline: 1 week.
[6 empty] | T077 | Launch the voice input feature as part of the health assessment tools in the app. Monitor performance and user adoption rates post-launch. Deadline: 1 week after completion of all preparatory tasks.
|  |  | S010 | As a patient, I want to perform a mental health screening using AI tools so that I can assess my mental wellbeing and get guidance on seeking further care if necessary. | Complete a mental health assessment AI flags potential areas of concern Guidance provided on how to seek further mental health resources | T078 | Design a user-friendly interface for the mental health assessment tool, ensuring it is accessible and easy to navigate. This includes creating a clear entry point from the main app dashboard, layout for questions, and submit buttons. Estimated completion time: 3 days.
[6 empty] | T079 | Develop the backend API to handle the submission of mental health assessments. This involves creating endpoints for receiving assessment data and storing it securely in the database. Include error handling for incomplete submissions. Estimated completion time: 5 days.
[6 empty] | T080 | Integrate AI capabilities to analyze mental health assessment responses in real-time. This includes setting up AI models to identify patterns or signals of mental health concerns based on user responses. Estimated completion time: 7 days.
[6 empty] | T081 | Implement logic to flag potential areas of concern based on AI analysis. If certain responses indicate a mental health risk, the system should flag these for further action. Estimated completion time: 4 days.
[6 empty] | T082 | Create a resource linkage system that provides users with information and contacts for mental health resources based on the AI's assessment. This involves mapping potential concerns to specific types of support or care. Estimated completion time: 5 days.
[6 empty] | T083 | Test the mental health assessment tool to ensure it correctly captures user inputs, the AI properly analyzes responses, flags are appropriately set, and guidance is accurately provided. This testing should cover both functional and non-functional requirements. Estimated completion time: 6 days.
[6 empty] | T084 | Prepare and conduct a user acceptance testing session with a select group of users to gather feedback on the usability of the mental health screening tool and the clarity of the guidance provided. Incorporate feedback into final adjustments. Estimated completion time: 4 days.
[6 empty] | T085 | Deploy the mental health screening tool to the production environment after passing all tests and final approval from the project stakeholders. Ensure that support documentation is updated and teams are briefed on the new features. Estimated completion time: 2 days.
[6 empty] | T086 | Monitor the tool post-launch to collect data on user engagement, effectiveness of AI analysis, and user feedback. Set up a monitoring dashboard to review performance metrics and user satisfaction. Estimated completion time: ongoing first month post-launch.
|  |  | S011 | As a patient, I want to evaluate my quality of life through an AI-powered interface so that I can monitor any changes over time and adjust my lifestyle or treatment as needed. | Ability to perform and review a Quality of Life (QoL) assessment AI analyzes responses to gauge wellbeing Assessment results are stored and can be tracked over time | T087 | Design a user interface for the Quality of Life (QoL) assessment tool, ensuring it is intuitive and user-friendly for patients to perform self-assessments. Include necessary input fields and instructions. Target completion in 2 weeks.
[6 empty] | T088 | Develop the backend service for handling the input and output of the Quality of Life assessments. This includes APIs to receive assessment data, process it through the AI module, and return results. Plan for completion in 3 weeks.
[6 empty] | T089 | Integrate an AI module capable of analyzing the Quality of Life assessment responses to gauge the patient's wellbeing. The AI should utilize machine learning models to interpret responses and provide insightful feedback. Expected to be functional and integrated within 4 weeks.
[6 empty] | T090 | Implement a database schema for storing results of the QoL assessments. Ensure data includes timestamps and can be linked to specific patient profiles for tracking changes over time. Completion targeted within 2 weeks.
[6 empty] | T091 | Create functionalities in the patient's mobile app for reviewing past Quality of Life assessments. This should include displaying the history of assessments and any noted changes in wellbeing over time. Scheduled for 3 weeks of development.
[6 empty] | T092 | Conduct a series of user acceptance tests (UAT) to ensure the QoL assessment tool meets the provided acceptance criteria and is user-friendly. Gather feedback and refine the system accordingly. Allocate 2 weeks for UAT and refinements.
[6 empty] | T093 | Ensure compliance with healthcare regulations and data privacy laws in handling patient data and AI analysis outputs. Review and adjust security measures as needed, aiming to finalize within 1 week.
[6 empty] | T094 | Prepare and deploy documentation and training materials for patients on how to use the Quality of Life assessment tool. This should be ready for release concurrently with the software launch, planned for 1 week before launch.
[6 empty] | T095 | Schedule the deployment of the Quality of Life assessment feature, including all necessary system updates and integrations. Final deployment is targeted in 8 weeks from project start.
|  |  | S012 | As a patient, I want the ability to view and edit my past health assessments so that I can update any changes in my health condition. | Access past assessment records Edit responses to past assessments Ensure edits are securely saved and reflected in the patient history | T096 | Create a user interface screen for accessing past health assessments, ensuring it is easy to navigate and accessible from the patient's profile menu. This task should be completed within 1 week.
[6 empty] | T097 | Implement backend API to fetch the list of past health assessments for a specific user, including details necessary for viewing and editing. Data privacy and security measures should be enforced. Task should be completed in 2 weeks.
[6 empty] | T098 | Develop a feature on the user interface that allows patients to select and view the detailed responses of a specific past assessment. Include functionalities like scroll, search, and filter to enhance user experience. This task should be completed within 1.5 weeks.
[6 empty] | T099 | Enable editing of responses in past health assessments. Ensure that each input field can be individually edited and provide a 'save' option to submit changes. Complete this task within 2 weeks.
[6 empty] | T100 | Implement functionality to securely save edits made to past assessments in the database. Use encrypted communication and ensure data integrity during the update operations. Aim to complete this within 1 week.
[6 empty] | T101 | Create a confirmation system that notifies the user upon successful saving of edits. This could include pop-up messages or email confirmations. Should be implemented within 3 days.
[6 empty] | T102 | Ensure all changes to health assessments are logged for audit purposes and reflected in the patient's history. Implement logging mechanisms that capture details like date, time, and nature of the edit. Task should be completed in 1 week.
[6 empty] | T103 | Conduct comprehensive testing to validate the functionality of viewing, editing, and saving health assessments. Include security testing to prevent unauthorized access and data breaches. Testing phase should last for 2 weeks.
[6 empty] | T104 | Prepare user help documentation and in-app guidance for accessing and editing past health assessments, ensuring clarity and ease of use for all patient demographics. This documentation should be ready in 1 week.
[6 empty] | T105 | Deploy the new features to the staging environment and conduct a pilot test with a select group of users to gather feedback on the usability and functionality of the edit features in past health assessments. Complete pilot testing in 2 weeks.
|  |  | S013 | As a patient, I want to access digital pamphlets and interact with an AI chatbot so that I can educate myself about health conditions and receive instant answers to my queries. | Access to digital pamphlets on various health topics Interact with an AI chatbot for immediate query resolution Chatbot responses are accurate and contextually relevant | T106 | Design the user interface for accessing digital pamphlets in the mobile app, ensuring it is intuitive and easy to navigate. Include a scrolling feature for various health topics. Completion of designs within 1 week.
[6 empty] | T107 | Develop the backend API to fetch digital pamphlets from the database. Ensure the API can handle requests efficiently and return the data in a structured format. Include error handling and security features. Development and testing to be completed within 2 weeks.
[6 empty] | T108 | Implement AI chatbot integration on the mobile app. Use a third-party service like Dialogflow or Microsoft Bot Framework to process natural language and deliver instant responses. Setup should be completed within 1 week, followed by integration testing.
[6 empty] | T109 | Create a database of FAQs and responses for the AI chatbot to pull from, ensuring the information is accurate and up-to-date with medical standards. Database creation and initial population to be completed within 2 weeks.
[6 empty] | T110 | Train the AI chatbot using machine learning techniques to improve the accuracy and relevance of the responses over time. Begin with a training dataset and plan to retrain the model every 3 months based on new data and user interactions.
[6 empty] | T111 | Develop a user feedback system to gather user experiences and chatbot performance data. Include options for rating the usefulness of the chatbot responses and providing textual feedback. Implementation should be completed within 1 week.
[6 empty] | T112 | Perform end-to-end testing of the digital pamphlet access and AI chatbot functionalities. This includes testing user interface interactions, API reliability, chatbot response accuracy, and overall system performance. Allocate 2 weeks for thorough testing.
[6 empty] | T113 | Deploy the digital pamphlet and AI chatbot features to the staging environment for beta testing. Gather user feedback to make necessary adjustments before final release. Plan for a 1-week beta test period followed by deployment adjustments.
[6 empty] | T114 | Prepare and conduct training sessions for the support team on managing the AI chatbot and updating the digital pamphlet content, ensuring they can handle common issues and update information as needed. Schedule training sessions 1 week before the app release.
[6 empty] | T115 | Launch the feature publicly with an official release announcement. Include detailed documentation on how to use the new features. Plan the launch event for 1 week after completing all testing and adjustments.
E003 | Patient Health Data Management | Allow patients to view, edit, and manage their health assessment data and medical history securely within the app. | S014 | As a Patient, I want to create and edit my profile so that I can keep my personal and health information up to date. | Patients can successfully register using their mobile number and OTP. Patients can update their profiles with information like age, gender, phone number, and profile picture. Patients can link their profiles with their chosen hospital using a secure code. Ensure the profile updating process is secure and compliant with privacy regulations. | T116 | Design a registration form interface on the mobile app that includes input fields for mobile number and OTP verification. Ensure the design is user-friendly and accessible.
[6 empty] | T117 | Implement backend logic to send an OTP to a user-specified mobile number. Use a reliable third-party service for SMS delivery and ensure it is capable of handling the expected volume of SMS messages.
[6 empty] | T118 | Develop a secure method for OTP verification that validates the OTP entered by the user against the server-stored value, with a timeout feature to ensure security.
[6 empty] | T119 | Create a user interface for profile editing that allows patients to update personal information such as age, gender, phone number, and profile picture. Include appropriate input validations to ensure data integrity.
[6 empty] | T120 | Implement functionality to save updated profile data to the backend. Use secure APIs and ensure that all data transmissions are encrypted.
[6 empty] | T121 | Develop a feature in the patient profile section for linking to a hospital using a secure code provided by the hospital. This should include a backend service to verify the code with the hospital’s database securely.
[6 empty] | T122 | Implement comprehensive security checks and data validation across all endpoints involved in the registration, profile updating, and hospital linking processes to adhere to privacy regulations.
[6 empty] | T123 | Conduct a security audit to ensure that the data handling and storage procedures comply with relevant privacy laws and best practices, particularly those concerning health information.
[6 empty] | T124 | Test the registration and profile update processes extensively. Include tests for normal operation, boundary conditions, and potential security breaches.
[6 empty] | T125 | Prepare documentation for the registration and profile management features, detailing the workflow, data fields, security measures, and any third-party services used.
[6 empty] | T126 | Deploy the new registration and profile management features to a staging environment to perform integration testing with other parts of the app, ensuring compatibility and smooth operation.
[6 empty] | T127 | Plan and conduct a user acceptance testing (UAT) phase with real users to gather feedback on the usability and functionality of the registration and profile updating features.
[6 empty] | T128 | Review feedback from UAT, make necessary adjustments, and prepare for final deployment, ensuring all features are polished and perform as expected under load.
[6 empty] | T129 | Schedule and execute deployment to the production environment, followed by a post-deployment monitoring phase to ensure system stability and performance.
|  |  | S015 | As a Patient, I want to input health assessment data using AI-powered forms so that I can efficiently update my health information. | Patients can initiate different health assessments via the app. AI assists in transcribing responses from speech to text where applicable. The system provides an intuitive UI for entering health data. Patients can review and confirm the accuracy of the AI-transcribed information before submission. | T130 | Design and implement a user interface (UI) for initiating health assessments in the patient app. The UI should have clear and accessible options for starting various types of health assessments.
[6 empty] | T131 | Integrate AI-powered speech-to-text capabilities to transcribe patient responses during health assessments. Ensure the AI module can handle medical terminology and patient-specific language nuances effectively.
[6 empty] | T132 | Develop and test the user interface for entering health data, ensuring it is intuitive and user-friendly. Include input fields, dropdowns, and other components that accommodate all necessary health data types.
[6 empty] | T133 | Implement functionality within the app to allow patients to review the AI-transcribed data before final submission. Provide options for editing and confirming accuracy, ensuring the patient's ability to make corrections if needed.
[6 empty] | T134 | Conduct usability testing with real users to validate the intuitiveness of the health data entry UI and the effectiveness of the speech-to-text transcription. Gather feedback and iterate on the design to improve the user experience.
[6 empty] | T135 | Ensure that all personal and health data entered and transcribed through the app is securely handled according to HIPAA regulations. Implement encryption for data in transit and at rest, and provide secure access controls.
|  |  | S016 | As a Patient, I want to view and edit my previously entered health assessments so that I can correct or update my health data. | Patients can view a list of all past assessments. Patients can select a specific assessment to view detailed responses. Patients can edit responses in their assessments. Ensure edits are saved correctly and the original data can be audited for changes. | T136 | Design and implement a user interface for viewing a list of all past health assessments. This interface should include sortable columns for dates and types of assessments. Ensure the UI is accessible and responsive. Estimated completion time: 3 days.
[6 empty] | T137 | Develop backend functionality to fetch and send a list of all past health assessments from the database to the frontend. Include caching strategies to optimize response times and reduce server load. Estimated completion time: 4 days.
[6 empty] | T138 | Create detailed assessment view functionality. When a patient selects an assessment from the list, this should pull detailed data from the backend and display it in a detailed view format on the frontend. Include fields shown in the original assessment form. Estimated completion time: 4 days.
[6 empty] | T139 | Implement edit functionality for health assessments. Patients should be able to modify their responses in this detailed view. Ensure fields are validated both on the client and server sides to maintain data integrity. Estimated completion time: 3 days.
[6 empty] | T140 | Ensure all edits are saved correctly by implementing a robust backend method to handle updates. This method should validate data consistency, prevent SQL injection, and return a success or error message to the frontend. Estimated completion time: 4 days.
[6 empty] | T141 | Implement an audit trail system to log changes made to health assessments. Each entry should include the user ID, timestamp, nature of the edit, and previous data state. This log should be immutable and stored securely. Estimated completion time: 5 days.
[6 empty] | T142 | Conduct comprehensive unit testing for both frontend and backend functionalities to ensure all new features work as expected and meet the acceptance criteria. Include tests for security and performance. Estimated completion time: 3 days.
[6 empty] | T143 | Plan and execute integration testing to verify that the new functionalities interact properly with existing features and the entire application remains stable. Estimated completion time: 2 days.
[6 empty] | T144 | Document all code changes, API endpoints, and user instructions. Ensure documentation is clear and accessible to support both the maintenance team and end-users. Estimated completion time: 2 days.
[6 empty] | T145 | Deploy the new features in a staging environment for real-world testing and user acceptance testing (UAT) to gather feedback and make necessary adjustments before final deployment. Estimated completion time: 3 days.
|  |  | S017 | As a Patient, I want to complete AI-powered mental health assessments so that I can monitor my mental health and get recommendations. | The app provides a mental health assessment module powered by AI. Patients can answer questions related to their mental health, with AI analyzing responses. The system provides feedback or suggestions based on AI analysis. Ensure the AI model complies with health standards for mental health assessments. | T146 | Design the user interface for the mental health assessment module, ensuring it is user-friendly and accessible within the app. Include elements to start the assessment, display questions, and show AI-generated feedback. (Measurable: UI mockups reviewed and approved by the design team, Achievable: 2 weeks for initial designs and revisions, Relevant: Aligns with the need for a module to administer AI-powered assessments)
[6 empty] | T147 | Develop the backend service to handle mental health assessment operations, including storing questions and recording responses. (Measurable: Fully functional service capable of storing and retrieving data, Achievable: 4 weeks for development and testing, Relevant: Essential for capturing and analyzing patient responses)
[6 empty] | T148 | Integrate artificial intelligence capabilities to analyze patient responses and generate insights on their mental health status. Use an existing AI service or develop a custom solution as per compliance needs. (Measurable: AI provides correct analysis on test data, Achievable: 6 weeks including integration and testing, Relevant: Directly relates to generating AI-powered feedback)
[6 empty] | T149 | Implement feedback mechanisms in the app where patients receive suggestions or mental health advice based on the AI's analysis of their assessment results. (Measurable: Feedback function tested with 95% accuracy, Achievable: 3 weeks for implementation and testing, Relevant: Addresses the criteria of providing feedback based on AI analysis)
[6 empty] | T150 | Conduct a compliance check to ensure the mental health assessment AI model adheres to health standards and regulations. (Measurable: Receive compliance certification, Achievable: 2 weeks for the compliance team to review and certify, Relevant: Ensures the AI model is safe and meets regulatory standards)
[6 empty] | T151 | Prepare and conduct a training session for the support team on how to assist patients in using the new mental health assessment feature, including troubleshooting common issues. (Measurable: Training completed, and support readiness assessed through a quiz, Achievable: 1 week for preparation and training session, Relevant: Supports patient engagement with the new feature)
[6 empty] | T152 | Plan and execute a beta testing phase involving a select group of patients to gather early feedback on the usability and efficacy of the mental health assessment tool. (Measurable: Collect and review feedback from at least 30 beta testers, Achievable: 3 weeks including recruitment, testing, and review, Relevant: Validates the assessment tool's performance and user satisfaction before full launch)
[6 empty] | T153 | Document the development process and create a user manual for the mental health assessment feature, detailing how to access and interpret the assessment results. (Measurable: Documentation reviewed and approved by project stakeholders, Achievable: 2 weeks for drafting and revisions, Relevant: Provides end-users with necessary guidance on using the feature)
|  |  | S018 | As a Patient, I want to securely log out of the healthcare app so that I can ensure my data is protected from unauthorized access. | Logout functionality is easily accessible from anywhere in the app. Upon logging out, ensure all sessions are terminated securely. Ensure that after logout, re-authentication is required to access the patient profile. | T154 | Design a logout button that is prominently accessible from the main navigation or menu of the app, ensuring visibility across all app screens. This should be completed by a UI/UX designer within 3 days.
[6 empty] | T155 | Implement the logout functionality on the client side by connecting the logout button to the user authentication service, which should initiate session termination. This task should be completed by a front-end developer within 2 days.
[6 empty] | T156 | Develop backend API to handle logout requests that will invalidate the current session token and clear any authentication cookies. The backend developer should complete this within 2 days.
[6 empty] | T157 | Ensure all user session data is cleared from the device upon logout to prevent unauthorized access. This includes cached data and any stored tokens. The mobile development team should address this within 2 days.
[6 empty] | T158 | Set up a re-authentication process that requires users to log in again after they have logged out. Modify the authentication flow to ensure it redirects to the login screen post-logout. A backend developer should set this up in 1 day.
[6 empty] | T159 | Perform comprehensive testing of the logout functionality to ensure it works as expected across different devices and user scenarios. Quality assurance should complete testing within 3 days.
[6 empty] | T160 | Create documentation for the logout feature detailing the design decisions, code implementations, and testing scenarios to maintain a record for future reference. The technical writer should prepare this document within 2 days.
|  |  | S019 | As a Patient, I want to be able to send feedback or request support so that I can communicate any issues or suggestions to improve the app. | Patients can access a feedback form from the app. Patients can categorize their feedback (e.g., bug report, feature request, general feedback). Submitted feedback is received by the admin and is actionable. Ensure patient privacy is maintained in feedback submissions. | T161 | Design a user-friendly feedback form interface within the app that includes fields for categorizing feedback (e.g., bug report, feature request, general feedback), and a submission button. Ensure the design complies with accessibility standards. Estimated time: 8 hours.
[6 empty] | T162 | Develop the backend API to handle the submission of feedback forms, including storage and categorization of the feedback. This task includes creating database schemas for storing feedback and ensuring robust security measures to protect patient data. Estimated time: 16 hours.
[6 empty] | T163 | Implement front-end functionality for the feedback form using React Native or a similar framework. This includes data binding, form validation, and handling submissions. Estimated time: 12 hours.
[6 empty] | T164 | Integrate the feedback form with the backend API, ensuring data is transmitted securely using HTTPS and other security protocols. Estimated time: 6 hours.
[6 empty] | T165 | Set up administrative alerts in the backend to notify system admins when new feedback is submitted, categorizing the urgency based on the feedback type (bug reports being high priority). Estimated time: 4 hours.
[6 empty] | T166 | Test the feedback submission process thoroughly with unit tests for backend logic and integration tests that simulate user interaction on the front end. Ensure that all categories of feedback can be submitted and received properly. Estimated time: 10 hours.
[6 empty] | T167 | Implement privacy measures to ensure that feedback submissions are anonymized before storage or provide clear disclaimers if personal information is included. Compliance checks with GDPR or HIPAA should be conducted. Estimated time: 5 hours.
[6 empty] | T168 | Develop a feature for admins to easily access and act on feedback within the admin panel, including filtering options based on category and status (new, in progress, resolved). Estimated time: 8 hours.
[6 empty] | T169 | Deploy changes to a staging environment for live testing with a select group of users to gather initial feedback on the usability and functionality of the feedback form. Estimated time: 3 hours.
[6 empty] | T170 | Conduct a security audit of the feedback handling process to ensure that there are no vulnerabilities through which patient data can be accessed or compromised. Estimated time: 8 hours.
[6 empty] | T171 | Prepare documentation for system administrators and users on how to use the new feedback form, including guidelines on privacy and data security. Estimated time: 4 hours.
[6 empty] | T172 | Plan and execute a roll-out of the feedback mechanism to all users, including an announcement and educational materials on how to use the feature effectively. Monitor user adoption and gather initial impressions for ongoing improvements. Estimated time: 8 hours.
|  |  | S020 | As a Patient, I want to use a QR code to share my assessment data with doctors so that my health information can be easily accessed during consultations. | Patients can generate a QR code within the app that encapsulates their health data. QR codes are generated in a secure manner, ensuring data privacy. Doctors can scan the QR code to access the patient's data quickly. | T173 | Design a QR code generation feature interface within the app for patients to generate QR codes of their health data. Ensure the interface is user-friendly and accessible within the patient's health data section. Duration: 3 days.
[6 empty] | T174 | Develop the backend logic to encapsulate patient's health data into a QR code. This involves selecting the relevant health data fields, encoding them, and generating the QR code image. Use secure encoding methods to protect data privacy. Duration: 5 days.
[6 empty] | T175 | Implement encryption for the data encapsulated within the QR code to ensure its security. Choose an industry-standard encryption algorithm and integrate it into the QR code generation process. Duration: 4 days.
[6 empty] | T176 | Create a testing protocol to ensure that the encrypted QR codes are generated correctly and can be read accurately by scanning. This should include tests for data integrity and decryption. Duration: 3 days.
[6 empty] | T177 | Develop a feature for doctors within their app version to scan and decrypt patient QR codes. Ensure compatibility and quick data access post-scan. Duration: 5 days.
[6 empty] | T178 | Conduct a security audit to review the QR code generation and scanning functionality to ensure there are no vulnerabilities in data handling and encryption processes. Duration: 2 days.
[6 empty] | T179 | Prepare and conduct a user training session for patients on how to generate and share their health data QR codes. Include best practices for privacy and data sharing. Duration: 2 days.
[6 empty] | T180 | Deploy the QR code functionality to a staging environment for integration testing with the existing patient app infrastructure to ensure system compatibility and performance under load. Duration: 3 days.
[6 empty] | T181 | Gather feedback from a patient focus group on the usability of the QR code generation feature and the clarity of the training provided. Use feedback to make necessary adjustments. Duration: 3 days.
[6 empty] | T182 | Release the QR code sharing feature to production after final approval and ensure that support documentation is updated to include instructions for both patients and doctors on using the new feature. Duration: 2 days.
E004 | AI-Powered Patient Support | Incorporate an AI chatbot that provides patients with information and answers queries about their condition, treatment options, and general health questions. | S021 | As a Patient, I want the AI chatbot to access my health profile so that I can receive personalized answers based on my medical history. | The chatbot must securely access patient health data. Patients receive responses tailored to their medical history. Responses must be generated within a few seconds of the query. | T183 | Design and implement a secure API for the AI chatbot to access patient health data, ensuring it uses authentication and encryption mechanisms. This task should be completed within two weeks.
[6 empty] | T184 | Configure the AI chatbot to fetch relevant patient data based on the query context and securely access the patient's health profile. Include error handling and logging capabilities. Estimated completion time is three weeks.
[6 empty] | T185 | Develop a personalized response generation logic for the AI chatbot that uses patient health data to tailor responses. This logic must handle various health data parameters and conditions. The development and initial testing should be done within four weeks.
[6 empty] | T186 | Implement a response timing mechanism to ensure that chatbot responses are generated and delivered within a few seconds. This includes optimizing query handling and server response times. Task should be completed in one week.
[6 empty] | T187 | Conduct a security audit of the AI chatbot interactions with the patient health data API to verify compliance with healthcare data protection regulations. The audit should be performed over one week, after the development tasks are completed.
[6 empty] | T188 | Perform comprehensive testing of the AI chatbot, focusing on its ability to securely access health data, generate personalized responses, and adhere to response time requirements. Schedule two weeks for testing, including unit, integration, and performance tests.
[6 empty] | T189 | Prepare documentation for the AI chatbot functionality that covers setup, configuration, and operational guidelines, with a focus on security practices and data handling. The documentation should be ready for review within one week after functionality is confirmed.
[6 empty] | T190 | Organize a training session for the support team on the new AI chatbot features, particularly focusing on the security aspects and the data access process. The session should be scheduled for one day and occur after the completion of all development and testing tasks.
|  |  | S022 | As a Patient, I want to ask general health questions and receive accurate information so that I can better understand health conditions without a doctor's visit. | The chatbot should provide medically accurate information. The content must be sourced from reliable health databases or literature. The chatbot should clarify that it doesn't replace professional medical advice. | T191 | Research and select a reliable health database or literature sources that will be used to feed information to the AI chatbot, ensuring they are current and widely recognized in the medical community. Completion due in 1 week.
[6 empty] | T192 | Develop algorithms for the AI chatbot to fetch relevant information from the selected databases or literature sources based on user queries. Include error handling and fallback mechanisms. Task to be completed within 3 weeks.
[6 empty] | T193 | Integrate the AI chatbot with the selected medical databases or literature sources using API or direct database access, with a focus on data security and privacy compliance. Integration to be tested and completed by the end of 4 weeks.
[6 empty] | T194 | Program the AI chatbot to provide responses that clearly state the information is for general understanding and does not replace professional medical advice. Include this disclaimer in all applicable responses. This task should be completed in 2 weeks.
[6 empty] | T195 | Implement functionality in the AI chatbot to maintain logs of the sources used for each piece of information provided, to ensure traceability and accountability. Complete this task within 3 weeks.
[6 empty] | T196 | Conduct a series of tests to validate the accuracy of the information provided by the AI chatbot, involving medical professionals to ensure the responses are correct and safe. Testing phase to last 3 weeks.
[6 empty] | T197 | Develop a user feedback system for the AI chatbot where users can rate the helpfulness of the information provided and submit corrections or suggestions. Implement this feature over 4 weeks.
[6 empty] | T198 | Set up a continuous update mechanism for the chatbot's knowledge base, ensuring the information remains current with ongoing medical research and findings. Plan for monthly review cycles with initial setup completed in 2 weeks.
[6 empty] | T199 | Prepare and deliver training sessions for the support team on managing and maintaining the AI chatbot, highlighting procedures for updating the information source and handling user feedback. Schedule training within 5 weeks from project start.
[6 empty] | T200 | Create documentation detailing the chatbot’s data sources, algorithms, integration methods, and operation protocols to assist with future maintenance and audits. Documentation to be completed within 6 weeks.
|  |  | S023 | As a Patient, I want to inquire about various treatment options for specific conditions so that I can be informed about possible treatments before consulting with a healthcare professional. | Treatment information provided must be up-to-date and based on the latest medical guidelines. The system should ask patients to confirm the condition they are inquiring about to ensure relevance. Provide links or references to detailed sources when available. | T201 | Research and integrate a medical database or API that includes up-to-date treatment options based on the latest medical guidelines. Set a deadline for selection and integration within four weeks.
[6 empty] | T202 | Design and implement a user interface component within the chatbot where patients can specify the medical condition they are inquiring about. Include autocomplete functionality to assist with spelling and recognition of medical terms. Complete this task within two weeks.
[6 empty] | T203 | Develop a system within the chatbot to verify the patient's input and confirm the condition they are inquiring about before providing treatment options. This validation should use existing medical data to ensure accuracy and relevance. Schedule to finalize this feature in three weeks.
[6 empty] | T204 | Create functionality in the chatbot to link treatment information to official medical resources or guidelines. This involves programming the chatbot to fetch and display URLs or references dynamically based on the treatment data provided. Aim to complete this in three weeks.
[6 empty] | T205 | Test the chatbot to ensure that the treatment information provided is accurate, up-to-date, and correctly linked to the medical condition specified by the user. Include unit tests and user acceptance tests to be completed over two weeks.
[6 empty] | T206 | Plan and execute a session to train the support team on the new chatbot features, focusing on how to guide users in using the chatbot to inquire about treatment options effectively. Arrange this training session to occur a week before the scheduled release.
[6 empty] | T207 | Set up continuous integration/continuous deployment (CI/CD) pipelines to automate the deployment of chatbot updates, ensuring that treatment information can be updated swiftly as new medical guidelines are published. This should be ready in four weeks.
[6 empty] | T208 | Organize a feedback mechanism for users to report inaccuracies or outdated information in the treatment options provided by the chatbot. Implement this feature within one week after the initial deployment.
|  |  | S024 | As a Patient, I want to ask about medications and receive details about dosages, side effects, and interactions so that I can safely manage my prescriptions. | The chatbot must provide information from a verified pharmaceutical database. Include a disclaimer about consulting with a healthcare provider for personal medical advice. Allow the user to specify the medication name accurately using text input. | T209 | Research and select a verified pharmaceutical database that provides comprehensive medication information including dosages, side effects, and interactions.
[6 empty] | T210 | Develop a secure API integration with the selected pharmaceutical database to retrieve medication information.
[6 empty] | T211 | Implement functionality in the AI chatbot to process user input for medication names and match it with database entries for accurate retrieval of medication information.
[6 empty] | T212 | Design and integrate a disclaimer message in the chatbot interface that advises users to consult with a healthcare provider for personal medical advice. Ensure the disclaimer is prominently displayed whenever medication information is provided.
[6 empty] | T213 | Create a user interface input field within the chatbot that allows users to type the name of the medication they wish to inquire about. Include autocomplete features to assist with entering medication names accurately.
[6 empty] | T214 | Conduct usability testing to ensure that the chatbot allows users to easily specify medication names and that the information retrieved is presented in a clear and understandable manner.
[6 empty] | T215 | Implement error handling in the chatbot to manage instances when the medication name does not match database entries or when the API fails to retrieve data.
[6 empty] | T216 | Deploy the updated AI chatbot to a test environment and perform integration testing to verify that the chatbot correctly interacts with the pharmaceutical database and handles user queries as expected.
[6 empty] | T217 | Prepare documentation for the chatbot functionality that explains how to query medication information and the limitations of the data provided.
[6 empty] | T218 | Schedule a training session for the support team on the new chatbot functionality to ensure they can assist users with any queries related to medication information.
[6 empty] | T219 | Launch the chatbot feature in a controlled rollout to monitor its performance and gather initial feedback from users on the medication information functionality.
[6 empty] | T220 | Analyze user feedback and usage data of the chatbot medication inquiry feature to identify any areas for improvement or additional user needs.
|  |  | S025 | As a Patient, I want to query the AI chatbot about hospital policies and procedures so that I can understand what to expect during hospital visits. | Chatbot responses must reflect the most current policies and procedures. Information should include visiting hours, admission processes, and patient services. Responses should be provided in an easy-to-understand format. | T221 | Gather the most current hospital policies and procedures data including visiting hours, admission processes, and patient services from each associated hospital's administrative team. Set a deadline for data collection within 1 week to ensure timely update in the system.
[6 empty] | T222 | Design and implement a database schema to store hospital policies and procedures information. Ensure the design supports quick retrieval and is scalable to accommodate data from multiple hospitals. Complete the schema design within 3 days of receiving hospital data.
[6 empty] | T223 | Develop an API that can fetch the most current policies and procedures from the database. Include endpoints to retrieve specific details such as visiting hours, admission processes, and patient services. Aim to complete the API development within 5 days from the completion of database schema.
[6 empty] | T224 | Integrate the newly developed API with the AI chatbot system to enable real-time fetching of hospital policies and procedures data when queried by users. Set the integration and initial testing phase to be completed within 2 days post API development.
[6 empty] | T225 | Implement natural language processing (NLP) capabilities to the AI Chatbot for understanding and processing user queries related to hospital policies and procedures. This task should be geared towards recognizing and responding to relevant keywords and phrases, with a completion goal within 7 days.
[6 empty] | T226 | Create a content management system (CMS) interface where hospital administrators can update their policies and procedures information as changes occur. This interface should be user-friendly and require minimal training. Schedule the completion of this interface within 10 days from the start.
[6 empty] | T227 | Develop a training program for hospital administrators to use the CMS effectively. Training materials should include video tutorials and written guides. Plan to have the training resources ready within 5 days after the CMS deployment.
[6 empty] | T228 | Conduct user acceptance testing with a focus group of patients to ensure the AI chatbot provides information in an easy-to-understand format. Collect feedback and make necessary adjustments over a period of 5 days.
[6 empty] | T229 | Set up a continuous integration/continuous deployment (CI/CD) pipeline for automated updates and testing of the AI chatbot system whenever changes are made in the database or the API. Aim to have the CI/CD pipeline operational within 7 days.
[6 empty] | T230 | Monitor and evaluate the AI chatbot's performance for a month to collect data on user interactions and satisfaction levels, making adjustments based on real user feedback to ensure the chatbot's responses remain relevant and easily understandable.
|  |  | S026 | As a Patient, I want to be able to provide feedback on the information provided by the AI chatbot so that I can report inaccuracies or excellent service. | Provide an easy-to-use feedback form linked to each chatbot response. Feedback should be categorized as positive, negative, or report an inaccuracy. The system should acknowledge receipt of feedback immediately. | T231 | Design a user interface for the feedback form that will be accessible directly from each AI chatbot response. Include fields for categorizing feedback as positive, negative, or reporting an inaccuracy. Ensure the form is intuitive and easy to use. Completion of the UI design should be done within 1 week.
[6 empty] | T232 | Develop the front-end functionality for the feedback form, enabling users to submit their feedback directly from the chatbot interface. This should include form validation to ensure all required fields are filled out before submission. Aim to complete this task within 2 weeks.
[6 empty] | T233 | Implement backend services to handle the reception of feedback from the form. This includes storing feedback in the database and categorizing it according to its nature (positive, negative, inaccuracy). The backend should be robust enough to handle multiple feedback submissions simultaneously. Completion expected within 3 weeks.
[6 empty] | T234 | Create an automated system to send immediate acknowledgment notifications to users once their feedback is received. This should include a thank-you message or confirmation alert. This task should be implemented and tested within 1 week.
[6 empty] | T235 | Integrate the feedback form with the AI chatbot responses ensuring that the form can be accessed easily whenever a user interacts with the chatbot. Include user testing to validate the integration works seamlessly. Scheduled completion within 2 weeks.
[6 empty] | T236 | Conduct comprehensive testing including unit, integration, and user acceptance tests to ensure the feedback mechanism works as expected across different devices and platforms. Allocate 2 weeks for thorough testing and allow for bug fixing.
[6 empty] | T237 | Prepare and update documentation on how to use the feedback system for both internal use (development and support teams) and external users (help documentation). Completion of documentation is expected within 1 week after final testing.
E005 | Digital Health Education | Enable patients to access and download digital pamphlets and educational materials through the app, enhancing their knowledge and understanding of health conditions. | S027 | As a Patient, I want to browse through a list of digital pamphlets and educational materials, so that I can learn about different health conditions and treatments. | List of digital pamphlets is accessible and scrollable. Each pamphlet has a clear title and short description. The app should load the initial list within 3 seconds of accessing the feature. Pamphlets are categorized by health condition for easy browsing. | T238 | Design the UI layout for the digital pamphlets list feature, ensuring it supports accessibility and scrollability.
[6 empty] | T239 | Implement a front-end component for displaying the list of digital pamphlets, incorporating infinite scroll to handle large sets of data efficiently.
[6 empty] | T240 | Develop a backend API to fetch digital pamphlets data, including titles and short descriptions from the database.
[6 empty] | T241 | Optimize the performance of the pamphlet list loading to ensure the initial content loads within 3 seconds.
[6 empty] | T242 | Categorize digital pamphlets by health conditions in the database to facilitate easier browsing and access in the UI.
[6 empty] | T243 | Integrate a search and filter functionality in the UI to allow users to easily find pamphlets by category or keywords.
[6 empty] | T244 | Implement caching strategies both on the client-side and server-side to enhance the speed of content delivery.
[6 empty] | T245 | Conduct user testing to ensure the digital pamphlets list is easy to navigate, understand, and use on various devices.
[6 empty] | T246 | Set up monitoring and logging tools to assess the load time of the pamphlets list and identify any performance bottlenecks.
[6 empty] | T247 | Review and ensure compliance with accessibility standards to make the feature usable for all patients, including those with disabilities.
|  |  | S028 | As a Patient, I want to view detailed information about a specific pamphlet, so that I can understand more about the health topic it covers. | Detailed view includes full content of the pamphlet. Images and charts within the pamphlet are properly formatted and visible. Users can return to the main list from the detailed view with a single action. | T248 | Design the UI layout for the detailed view of a pamphlet that includes sections for full content, images, and charts. Ensure that the design is responsive and visually appealing. Deadline: 2 days from now.
[6 empty] | T249 | Implement the frontend interface for the pamphlet's detailed view according to the UI design, using HTML/CSS/JavaScript. Ensure that text, images, and charts are properly formatted and align with design specifications. Deadline: 4 days from now.
[6 empty] | T250 | Develop backend API to retrieve the full content of the pamphlet, including text, images, and chart data from the database. Ensure API security with appropriate authentication and data validation. Deadline: 3 days from now.
[6 empty] | T251 | Integrate the frontend detailed view with the backend API to dynamically display the content of the pamphlets. Test for data loading times and correct rendering of content. Deadline: 2 days after backend completion.
[6 empty] | T252 | Implement a 'Back to List' button on the detailed view page that allows users to easily navigate back to the main list of pamphlets. Ensure the button is prominently placed and tested for functionality. Deadline: 1 day after frontend integration.
[6 empty] | T253 | Conduct a comprehensive QA session to ensure that all elements in the detailed view are accessible, properly formatted, and function correctly across different devices and browsers. Deadline: 2 days after all implementations are completed.
[6 empty] | T254 | Prepare user documentation and help sections that explain how to navigate the detailed view of the pamphlets. Include troubleshooting tips for common issues users might encounter. Deadline: 1 day after QA completion.
|  |  | S029 | As a Patient, I want to download digital pamphlets to my device, so that I can read them offline or share them with family and friends. | Download option is clearly visible on the pamphlet detail page. Pamphlet is saved to the device's local storage. Users receive a confirmation message once download is successful. Downloaded pamphlet maintains its formatting and content integrity. | T255 | Design a user interface for the pamphlet detail page that includes a clearly visible 'Download' button. This task should be completed by the UX/UI team by the end of the week.
[6 empty] | T256 | Implement the functionality to save the pamphlet to the device's local storage when the 'Download' button is clicked. This involves file handling operations and should be handled by a mobile application developer within 3 days.
[6 empty] | T257 | Develop a confirmation message popup or notification that appears once the pamphlet download is successful. This task should include creating a small, reusable component by the front-end team, to be completed within 2 days.
[6 empty] | T258 | Ensure that the downloaded pamphlet maintains its formatting and content integrity. This requires testing various formats across different devices, which should be led by the QA team and completed within 1 week.
[6 empty] | T259 | Create a test plan to ensure that the download functionality works under different network conditions and device storage statuses. The QA team should execute this in a span of 4 days.
[6 empty] | T260 | Set up monitoring and logging for the download transactions to help troubleshoot any issues users encounter during the download process. The backend team should implement this within 3 days.
[6 empty] | T261 | Review app permissions related to storage access to ensure compliance with mobile operating system guidelines. This should be reviewed by a compliance officer and adjusted by developers within 5 days.
|  |  | S030 | As a Patient, I want to search for pamphlets by keywords, so that I can quickly find materials relevant to my specific health concerns. | Search bar is accessible from the main pamphlet list screen. Results update in real-time as the user types. Search results display pamphlets that contain the search keywords in the title or description. No results found message is displayed if there are no matches. | T262 | Design and implement a UI component for a search bar on the main pamphlet list screen. This task includes creating a mockup, getting it approved by the UI/UX team, and coding the frontend component. Estimated completion time: 2 days.
[6 empty] | T263 | Develop the backend API to handle search queries for pamphlets. This should support partial text search and return results in real-time as the user types. Implement indexing on the pamphlet title and description fields to improve search performance. Estimated completion time: 3 days.
[6 empty] | T264 | Integrate the search bar UI with the backend search API. This involves setting up the AJAX calls to fetch data dynamically as input is received and updating the UI without needing to reload the page. Estimated completion time: 2 days.
[6 empty] | T265 | Implement logic to display search results dynamically as the user types in the search bar. This includes handling and rendering data returned from the backend API. Ensure that the UI updates immediately with the relevant pamphlet titles and descriptions. Estimated completion time: 2 days.
[6 empty] | T266 | Create a 'No results found' message UI component that gets displayed when the search results are empty. This component should be clear and user-friendly, informing users that no pamphlets match their search criteria. Estimated completion time: 1 day.
[6 empty] | T267 | Conduct thorough testing on the search functionality to ensure that it meets all acceptance criteria: accessibility from the main screen, real-time updates, accurate display of results, and proper handling when no results are found. Estimated completion time: 2 days.
|  |  | S031 | As a Patient, I want to rate and review the pamphlets I read, so that I can provide feedback and help other patients gauge the usefulness of the materials. | Rating and review option available on each pamphlet’s detail page. Users can submit a star rating from 1 to 5. Users can write a text review up to 500 characters. Submitted ratings and reviews are immediately visible to the user and saved to their profile. | T268 | Design a UI component on the pamphlet detail page for rating and review submission, including a star rating system (1-5 stars) and a text box for reviews up to 500 characters. Estimated completion: 2 days.
[6 empty] | T269 | Implement front-end functionality for the rating and review system using React/Angular to handle user interactions and local state management for immediate UI updates. Estimated completion: 3 days.
[6 empty] | T270 | Develop API endpoints to handle the submission of ratings and reviews. This includes POST endpoints for submitting new ratings and reviews and GET endpoints to retrieve existing ones. Estimated completion: 2 days.
[6 empty] | T271 | Integrate the front-end components with the backend API to ensure that user submissions for ratings and reviews are processed and stored in the database. Use Axios or Fetch API for HTTP requests. Estimated completion: 2 days.
[6 empty] | T272 | Write unit tests for both front-end and back-end components to verify that the rating and review system works as expected, including input validation and API response handling. Use Jest for frontend and Mocha for backend. Estimated completion: 2 days.
[6 empty] | T273 | Implement functionality to display submitted ratings and reviews immediately on the user interface after submission, ensuring real-time feedback is visible to users. Include error handling for failed submissions. Estimated completion: 1 day.
[6 empty] | T274 | Configure database schema to store user ratings and reviews, ensuring data integrity with appropriate fields for user ID, pamphlet ID, rating, review text, and timestamps. Estimated completion: 1 day.
[6 empty] | T275 | Develop a system to aggregate and display average ratings on each pamphlet’s detail page, updating dynamically as new reviews are added. Estimated completion: 2 days.
[6 empty] | T276 | Ensure compliance with data privacy laws by implementing proper security measures on the handling and storing of user feedback. Include user authentication to verify identity before submission. Estimated completion: 1 day.
[6 empty] | T277 | Perform integration testing to ensure that the new rating and review system works seamlessly with existing features like user authentication, pamphlet viewing, and downloading. Estimated completion: 2 days.
[6 empty] | T278 | Prepare a change management plan for deploying the rating and review system, including rollback steps, monitoring strategies, and user communication. Estimated completion: 1 day.
|  |  | S032 | As a Patient, I want to access a FAQ section related to each pamphlet, so that I can quickly find answers to common questions regarding the health topics covered. | FAQ section is available at the bottom of each pamphlet detail page. FAQs are presented in a collapsible format to enhance readability. Each FAQ can be expanded or collapsed with a single tap. The most common questions are listed first. | T279 | Design the UI layout for the FAQ section at the bottom of each pamphlet detail page, ensuring it is visible and accessible. Include placeholders for collapsible FAQ items. (Time-bound: 2 days)
[6 empty] | T280 | Implement the collapsible functionality for FAQ items using JavaScript or a suitable framework to enable expand/collapse actions with a single tap. Ensure this is tested across different device types for responsiveness and ease of use. (Time-bound: 3 days)
[6 empty] | T281 | Develop the backend service to fetch and serve FAQ content, ensuring data is structured to support sorting with the most common questions listed first. This service must handle requests efficiently and securely. (Time-bound: 4 days)
[6 empty] | T282 | Integrate the FAQ display in the app with the newly developed backend service, ensuring FAQs are loaded dynamically at the bottom of each pamphlet detail page. Include error handling for failed data fetching. (Time-bound: 2 days)
[6 empty] | T283 | Conduct usability testing for the FAQ section to ensure that the collapsible elements and overall readability meet the user experience standards. Gather feedback and make necessary adjustments. (Time-bound: 3 days)
[6 empty] | T284 | Prepare and update the app documentation to include details about the FAQ section functionality, its usage, and troubleshooting common issues. Ensure documentation is clear and easy to understand. (Time-bound: 1 day)
E006 | Secure Data Sharing | Facilitate secure sharing of patient health data with doctors through QR codes, enhancing the efficiency of medical consultations and patient data portability. | S033 | As a Patient, I want to generate a QR code that securely encapsulates my health data, so that I can easily share it with doctors during medical consultations. | The QR code generation feature must be easily accessible in the patient app interface. The generated QR code should encrypt the patient data to ensure security. Doctors should be able to scan the QR code using their app and immediately access the patient's health data. The patient must be able to regenerate a QR code for each new consultation for enhanced security. | T285 | Design a user interface element on the patient app homepage for easy access to the QR code generation feature. Ensure this design is intuitive and clearly labeled, to be completed within 3 days.
[6 empty] | T286 | Implement end-to-end encryption for the QR code data payload. Use a secure algorithm suitable for health data, such as AES-256. Complete the implementation and testing within 5 days.
[6 empty] | T287 | Develop functionality in the patient app to generate a QR code based on the encrypted health data. Ensure the QR code generation process is fast and secure, to be completed within 4 days.
[6 empty] | T288 | Create an API in the doctor's app to scan and decrypt the QR code. Ensure compatibility with common mobile device cameras and test for accuracy in various lighting conditions, to be finished within 5 days.
[6 empty] | T289 | Ensure that the patient can regenerate a QR code for each new consultation by adding a 'Regenerate QR Code' button in the app. Include logic to invalidate the old QR code when a new one is generated, task to be done within 2 days.
[6 empty] | T290 | Conduct end-to-end testing of the QR code generation and scanning feature to confirm that doctors can access the health data immediately after scanning. Schedule user acceptance testing within 7 days.
[6 empty] | T291 | Optimize the QR code regeneration feature to ensure enhanced security, making sure each new QR code is usable for only one consultation. This should include backend validation mechanisms, to be completed within 3 days.
[6 empty] | T292 | Prepare documentation for the QR code feature, detailing the generation, encryption, and scanning processes for both patient and doctor side applications. Complete documentation within 4 days.
[6 empty] | T293 | Implement logging and monitoring for the QR code generation and scanning activities to track usage statistics and potential security issues. Set up the monitoring tools and define alert criteria within 4 days.
|  |  | S034 | As a Patient, I want to link my profile with a hospital by scanning a QR code, so that my health data and hospital records are synchronized for better healthcare management. | Patients must be able to scan a QR code provided by the hospital to link their profiles. Upon successful linking, the patient’s app should display confirmation of the hospital linkage. The system must ensure that all patient data remains secure and only shareable with the linked hospital’s system. The patient should have the ability to unlink from the hospital via the app, requiring re-authentication. | T294 | Develop a QR code scanning feature within the patient mobile app to facilitate the linking of patient profiles with hospital systems. Ensure the scanner is compatible with standard QR code formats used by hospitals.
[6 empty] | T295 | Implement a secure backend API that receives the QR code data from the patient app, verifies it against hospital records, and establishes a link if verified.
[6 empty] | T296 | Create a user interface update that confirms the successful linking of a patient's profile to a hospital once the QR code has been verified and the backend linkage is complete.
[6 empty] | T297 | Enhance data security by implementing encryption for all data transmitted between the patient app and the hospital system during the QR code linkage process.
[6 empty] | T298 | Develop functionality within the patient app that allows a patient to unlink their profile from a hospital. This should include a re-authentication process to ensure that the request is legitimate.
[6 empty] | T299 | Set up automated tests to validate the QR code scanning and linking process, including edge cases where QR codes are invalid or the hospital ID does not match.
[6 empty] | T300 | Conduct a security audit to ensure that the linkage via QR code does not expose patient data to unauthorized access or breaches.
[6 empty] | T301 | Provide a clear and intuitive user interface for patients to manage their linked hospital records, including the ability to view the current linked hospital and an option to unlink.
[6 empty] | T302 | Document the QR code linking process and provide in-app help or tutorials for patients on how to use the QR code feature to link or unlink their profiles with hospitals.
|  |  | S035 | As a Patient, I want to view a history of all the doctors and hospitals with whom I have shared my health data via QR code, so that I can keep track of who has accessed my information. | The app must provide a dedicated section for viewing the history of shared data. The history should include the name of the doctor or hospital and the date of access. Patients should be able to remove old entries from their shared data history. The feature should be protected by additional security measures within the app to prevent unauthorized access. | T303 | Design a user interface for viewing the history of shared health data. The interface should include sections for the names of the doctors or hospitals and the dates of access. Estimated design time: 3 days.
[6 empty] | T304 | Implement the backend logic to retrieve and display the history of shared data from the database. This includes fetching names of doctors or hospitals and the dates they accessed the patient’s data. Estimated development time: 5 days.
[6 empty] | T305 | Develop front-end functionality for the new user interface that allows patients to view the shared data history. This task will involve connecting the front-end with the backend services to fetch and display the data. Estimated development time: 4 days.
[6 empty] | T306 | Implement the functionality to allow patients to remove old entries from their shared data history. This includes front-end options to delete specific entries and backend logic to remove these entries from the database securely. Estimated development time: 4 days.
[6 empty] | T307 | Enhance app security for the section that displays shared data history. Implement additional authentication checks to ensure only the authorised patient can access their data history. Consider using encryption or secure access tokens. Estimated implementation time: 3 days.
[6 empty] | T308 | Conduct a security audit of the new features to ensure data protection standards are met and that there are no vulnerabilities in accessing the shared data history. Estimated time for security audit: 2 days.
[6 empty] | T309 | Integrate and test the new functionality with the existing patient app to ensure compatibility and stability of the application. This includes end-to-end testing and user acceptance testing. Estimated testing phase: 4 days.
[6 empty] | T310 | Prepare documentation for the new data history viewing feature, detailing how patients can access, view, and manage their shared health data history. Include security measures and instructions for deleting history entries. Estimated documentation time: 2 days.
[6 empty] | T311 | Deploy the new features to the staging environment for a pilot test with a select group of users to gather feedback and ensure the features meet user needs before full deployment. Estimated pilot test duration: 5 days.
[6 empty] | T312 | Review feedback from pilot testing, make necessary adjustments to the feature based on user input, and finalize the feature for production deployment. Estimated time for feedback review and final adjustments: 3 days.
|  |  | S036 | As a Patient, I want to be able to revoke access to the data I have shared via QR code, so that I can control the continuity of my data accessibility by doctors. | Patients must be able to select a particular doctor or hospital from their shared history and revoke access to their data. Upon revocation, the system should immediately invalidate the previously shared QR code’s data access. The app should notify the user upon successful revocation of access. The system should log all revocation actions for security audits. | T313 | Design a user interface component in the patient app that displays a list of all previously shared QR codes, including the details of the doctor or hospital each code was shared with. Include a date and time for each sharing instance. This task directly supports the acceptance criteria that patients must be able to select a particular doctor or hospital from their shared history.
[6 empty] | T314 | Implement a feature in the patient app that allows users to select and revoke access to their data via a previously shared QR code. This will include an interactive button or link labeled 'Revoke Access' next to each listed QR code shared history entry. This supports the acceptance criteria for patient-initiated revocation of data access.
[6 empty] | T315 | Develop backend functionality to invalidate a QR code's data access immediately after a patient triggers revocation. This will involve modifying the QR code's status in the database to ensure it can no longer be used for data access, thus aligning with the criteria that the system should immediately invalidate the previously shared QR code’s data access.
[6 empty] | T316 | Create a notification system in the app to alert the patient when the revocation of a QR code has been successfully processed. This should include a confirmation message displayed in the app, satisfying the criterion that the app should notify the user upon successful revocation of access.
[6 empty] | T317 | Set up a logging mechanism to record all QR code revocation actions. Each log entry should include the user ID, the QR code ID, the timestamp of the revocation, and the identifier (doctor or hospital) with whom the QR code was shared. This task is essential for meeting the acceptance criteria of logging all revocation actions for security audits.
|  |  | S037 | As a Patient, I want the QR code generation for sharing my data to be secure, ensuring that my health information remains confidential and only accessible to authorized medical personnel. | The QR code must encrypt patient data using up-to-date and strong encryption standards. Only authorized medical personnel with the appropriate app and permissions can decrypt and view the data. The app must generate a new QR code for each sharing action to prevent reuse of old codes. The system should perform regular security audits to ensure the encryption methods remain secure against new vulnerabilities. | T318 | Research and select encryption algorithms that meet industry standards for securing QR code data. Ensure the chosen algorithms are current and robust against known attack vectors. This task aligns with the acceptance criteria that the QR code must encrypt patient data using up-to-date and strong encryption standards. Expected completion within 1 week.
[6 empty] | T319 | Develop a module within the app for generating QR codes. This module should integrate the selected encryption algorithm to encrypt patient health data before encoding it into the QR code. This task aligns with the acceptance criteria regarding the encryption of patient data. Expected to be completed within 2 weeks after encryption algorithm selection.
[6 empty] | T320 | Implement access controls within the app to ensure that only authorized medical personnel can decrypt and view the data from the QR code. This task involves setting up authentication and authorization checks based on user roles and permissions, aligning with the criteria that only authorized personnel can view the data. Completion expected within 1 week following the QR code generation module development.
[6 empty] | T321 | Modify the QR code generation logic to ensure a new QR code is generated for each sharing action. This includes adjusting the data payload to include a timestamp or a unique identifier to differentiate each code, meeting the criteria to prevent reuse of old codes. Scheduled for 1 week of development time.
[6 empty] | T322 | Schedule and implement regular security audits to review and assess the encryption methods used in QR code data protection. This task aligns with the acceptance criteria to regularly check the security of encryption methods. Plan for the first audit to occur one month after deployment, with subsequent quarterly audits.
[6 empty] | T323 | Develop unit tests and integration tests to validate the encryption, generation, and decryption functionalities of the QR codes. This ensures all components work as expected and comply with security requirements. Aim to complete testing concurrently with development tasks to maintain development speed.
[6 empty] | T324 | Prepare documentation detailing the process and protocols for QR code data encryption and access control, providing guidelines for future maintenance and compliance checks. Documentation to be completed in the final week of the development sprint.
E001 | Admin Dashboard Management | Develop a comprehensive dashboard for system administrators to monitor user activity, manage doctor and patient accounts, and view system statistics to ensure smooth operation of the healthcare platform. | S001 | As a System Administrator, I want to monitor user activity so that I can ensure the system is used appropriately and identify any unusual behavior. | Ability to view a log of user activities including logins, logouts, and critical actions. Activity log should include timestamps, user IDs, and descriptions of actions. The system should update the activity log in real time. Administrators can filter the activity log by user, date, or type of activity. | T001 | Design the database schema for the activity log, ensuring fields for user IDs, timestamps, descriptions of actions, and critical flags are included. Estimated time: 2 days.
[6 empty] | T002 | Implement backend APIs to handle the creation and real-time updating of user activity logs. This includes logins, logouts, and critical actions. Ensure APIs are secure and can handle concurrent requests efficiently. Estimated time: 3 days.
[6 empty] | T003 | Develop a real-time data streaming mechanism using technologies like WebSockets or server-sent events to update the admin dashboard in real-time as activities occur. Estimated time: 3 days.
[6 empty] | T004 | Create frontend functionality on the admin dashboard to display the activity log. This should include a real-time feed and historical data access. Use a responsive table with columns for user ID, timestamp, action description, and status (critical or normal). Estimated time: 4 days.
[6 empty] | T005 | Implement filtering capabilities in both the frontend and backend. Admins should be able to filter logs by user ID, date range, and type of activity (e.g., login, logout, critical actions). Estimated time: 2 days.
[6 empty] | T006 | Conduct comprehensive testing of the user activity logging system, including stress testing the real-time updates and verifying the accuracy of the filters. Document all test cases and outcomes. Estimated time: 3 days.
[6 empty] | T007 | Prepare documentation for the user activity monitoring feature, detailing how to view and interpret the logs, and how to use the filtering features. Include screenshots and examples for clarity. Estimated time: 1 day.
[6 empty] | T008 | Deploy the user activity monitoring feature to the staging environment and conduct integration testing with existing systems to ensure compatibility and performance standards are met. Estimated time: 2 days.
[6 empty] | T009 | Schedule a training session for system administrators to educate them on using the new dashboard features, focusing on the real-time activity log monitoring and filtering capabilities. Prepare training materials and a Q&A session. Estimated time: 1 day.
[6 empty] | T010 | Collect feedback from system administrators after two weeks of using the new features and plan adjustments or improvements based on their inputs. Estimated time for initial feedback collection: 1 day.
|  |  | S002 | As a System Administrator, I want to manage doctor accounts so that I can control access to sensitive information and maintain the integrity of the healthcare platform. | Ability to create, update, and deactivate doctor accounts. Each doctor account should have associated credentials including a unique MD ID, hospital affiliation, and contact details. Changes to accounts should be logged and visible in the user activity monitor. Provide a secure mechanism for password resets and account recovery. | T011 | Design a user interface for the administrative dashboard that includes functionalities to create, update, and deactivate doctor accounts. The design should be completed by a UX/UI designer within 2 weeks.
[6 empty] | T012 | Develop backend API services to handle the creation, updating, and deactivation of doctor accounts. This includes validation of input data such as MD ID and hospital affiliations. The backend development should be completed within 3 weeks.
[6 empty] | T013 | Implement frontend integration for the administrative dashboard that connects with the backend API services, enabling the user interface to perform account management tasks. This task should be completed by a frontend developer in 2 weeks.
[6 empty] | T014 | Set up a database schema to store doctor account details including MD ID, hospital affiliation, and contact details. This task should be handled by a database administrator and completed within 1 week.
[6 empty] | T015 | Develop a secure mechanism for password resets and account recovery. This includes implementing email verification and secure token generation, to be completed by a security specialist within 2 weeks.
[6 empty] | T016 | Create logging functionality in the backend that records all changes made to doctor accounts, including account creation, updates, and deactivations. This should include a timestamp, user ID of the administrator making the change, and a description of the change. The logging feature should be completed within 1 week.
[6 empty] | T017 | Integrate the logging functionality with the user activity monitor dashboard to make these logs visible to system administrators. This integration should be completed by a full-stack developer within 1 week.
[6 empty] | T018 | Conduct comprehensive testing of the doctor account management functionalities including creating, updating, and deactivating accounts, as well as password resets and logging. This testing phase should be completed by a QA engineer over a period of 2 weeks.
[6 empty] | T019 | Prepare documentation for the newly implemented doctor account management features, detailing the process for managing accounts and securing password resets. The documentation should be prepared by a technical writer and completed within 1 week.
[6 empty] | T020 | Schedule a training session for system administrators to familiarize them with the new dashboard functionalities specifically related to managing doctor accounts. The training should be arranged within 1 week following the completion of all development tasks.
|  |  | S003 | As a System Administrator, I want to manage patient accounts to ensure accurate and up-to-date information is available for healthcare services. | Ability to view and edit non-health related patient profile information. System should log all changes made to patient accounts for audit purposes. Administrators can deactivate or re-activate patient accounts based on compliance and user requests. Provide a mechanism to link patient accounts to hospital records securely. | T021 | Design a user interface component for the dashboard that allows system administrators to view non-health related patient profile information. This should include fields like name, contact details, and account status. The design should be completed within 1 week.
[6 empty] | T022 | Implement the user interface component for viewing patient profiles as designed. Ensure the component integrates seamlessly with the existing system dashboard. Complete implementation within 2 weeks.
[6 empty] | T023 | Develop backend functionality to fetch and display non-health related patient profile information from the database. Ensure data fetching is optimized for performance. Task to be completed within 2 weeks.
[6 empty] | T024 | Create functionality that allows system administrators to edit non-health related patient profile information. This includes input validation and error handling mechanisms. Schedule completion within 3 weeks.
[6 empty] | T025 | Implement logging for all changes made to patient accounts. This includes capturing the editor's identity, time of edit, and nature of the data changed. Develop this within 1 week.
[6 empty] | T026 | Develop a feature for administrators to deactivate or reactivate patient accounts. Include appropriate security checks and confirmation prompts to prevent accidental changes. Completion targeted within 2 weeks.
[6 empty] | T027 | Create a secure mechanism to link patient accounts to hospital records. This mechanism should verify the legitimacy of the link request and log the action for audit purposes. Develop and test this feature within 3 weeks.
[6 empty] | T028 | Integrate comprehensive testing to ensure that new dashboard functionalities work as expected with the existing system components. This includes integration testing and user acceptance testing. Schedule 2 weeks for this task.
[6 empty] | T029 | Organize a training session for system administrators to familiarize them with the new dashboard features, focusing on managing patient accounts. Plan and execute this within 1 week after development completion.
[6 empty] | T030 | Prepare documentation for the newly developed features, detailing the use cases, functionalities, and troubleshooting steps. This documentation should be ready for review and publishing within 1 week after feature development.
|  |  | S004 | As a System Administrator, I want to view system statistics so that I can assess the overall health of the platform and make informed decisions on resource allocation and system improvements. | Display real-time statistics on number of active users, system load, and transaction volumes. Statistics should include historical data comparison to identify trends. Provide alerts for any anomalies detected in system performance metrics. Ensure the data presented is secure and accessible only to authorized administrators. | T031 | Design a system statistics module for the administrator dashboard that can display real-time data on active users, system load, and transaction volumes. This task includes creating wireframes and UI components that accommodate the required statistics. Estimated completion time: 1 week.
[6 empty] | T032 | Develop back-end functionalities to fetch real-time data from the server related to user activity, system load, and transaction volumes. This includes setting up API endpoints and ensuring efficient data retrieval mechanisms. Estimated completion time: 2 weeks.
[6 empty] | T033 | Implement a data caching strategy to optimize the performance of the statistics dashboard, ensuring that frequent data fetches do not significantly impact system performance. Estimated completion time: 1 week.
[6 empty] | T034 | Integrate historical data comparison features by developing functionalities to fetch, process, and display trends based on past statistical data. Include date range selectors for administrators to customize views. Estimated completion time: 2 weeks.
[6 empty] | T035 | Set up an alert system within the dashboard to notify administrators of any anomalies detected in system performance metrics such as unexpected spikes in load or transaction volumes. This task involves creating alert rules and notification mechanisms. Estimated completion time: 1.5 weeks.
[6 empty] | T036 | Ensure data security for the statistics dashboard by implementing role-based access controls and data encryption for data in transit and at rest. Additionally, review and apply best security practices related to data visibility. Estimated completion time: 1 week.
[6 empty] | T037 | Conduct a series of performance tests to evaluate the responsiveness and accuracy of the real-time statistics display features. This testing should also include security penetration tests to ensure that data access is securely controlled. Estimated completion time: 1 week.
[6 empty] | T038 | Prepare documentation that details the functionalities of the system statistics module, including screenshots and guidelines on how to interpret the data and manage notifications. Estimated completion time: 3 days.
[6 empty] | T039 | Organize a training session for system administrators to familiarize them with the new statistics dashboard, focusing on how to interpret the data, set alert parameters, and utilize historical data comparison tools. Estimated completion time: 1 day.
|  |  | S005 | As a System Administrator, I want to manage feedback and track issues so that I can address user concerns promptly and improve system reliability. | Ability to receive, categorize, and respond to user feedback. Track issue resolution progress and communicate updates to relevant stakeholders. Provide a dashboard for visualizing feedback trends and common issues. Ensure that all feedback and issue data is secure and compliant with privacy regulations. | T040 | Design and implement a feedback reception form in the system dashboard where users can submit their feedback. Include fields to categorize feedback (e.g., bug, feature request, general feedback). This form should validate input data to ensure security and compliance. Estimated time: 4 days.
[6 empty] | T041 | Develop a backend system to receive, store, and categorize user feedback securely. Ensure that the storage complies with privacy regulations such as GDPR or HIPAA by implementing encryption and secure access controls. Estimated time: 6 days.
[6 empty] | T042 | Create a feedback management interface for administrators to view and categorize feedback received. This interface should allow administrators to filter feedback by category, urgency, or date. Estimated time: 3 days.
[6 empty] | T043 | Implement functionality for administrators to respond to feedback directly from the dashboard. Include an automated notification system to inform users once feedback has been addressed. Estimated time: 5 days.
[6 empty] | T044 | Develop a dashboard widget to track and display issue resolution progress. This should include visual indicators such as progress bars or graphs and the ability to update and view resolution status in real-time. Estimated time: 4 days.
[6 empty] | T045 | Set up a communication system to update relevant stakeholders about the progress of issue resolutions. This system should support both automated updates based on issue status changes and manual updates by administrators. Estimated time: 3 days.
[6 empty] | T046 | Design and implement a comprehensive dashboard for visualizing feedback trends and common issues. This should include data aggregation tools that compile feedback into actionable insights and visualizations like charts and heat maps. Estimated time: 5 days.
[6 empty] | T047 | Conduct a security review of all new functionalities to ensure that feedback and issue data management complies with relevant privacy regulations. Implement necessary security measures such as data encryption and access controls. Estimated time: 2 days.
[6 empty] | T048 | Prepare and execute a system integration test to verify that all new dashboard features work seamlessly with existing systems and that they meet all functional and security requirements. Estimated time: 3 days.
[6 empty] | T049 | Document all development processes, changes, and configurations for the new feedback management and issue tracking functionalities. Ensure that documentation is compliant with regulatory standards and accessible to authorized personnel only. Estimated time: 2 days.
E002 | Security and Access Control | Implement robust security measures including role-based access controls and authentication systems to secure sensitive health data and provide system administrators with tools to manage these features effectively. | S006 | As a System Administrator, I want to configure role-based access controls so that appropriate access levels can be maintained for different user roles within the system. | Ability to define distinct roles (e.g., patient, doctor, admin). Administrators can assign and modify roles to users. System correctly restricts access based on user role. Comprehensive testing to ensure no unauthorized access is possible. | T050 | Design a role-based access control (RBAC) model. Define roles such as patient, doctor, and administrator, along with their respective permissions and limitations within the system. Ensure that the design details all necessary actions each role can perform and the access level each should have.
[6 empty] | T051 | Develop a user interface on the administrative dashboard for defining and modifying user roles. This interface should allow administrators to easily create new roles, edit existing roles, and assign or change user roles.
[6 empty] | T052 | Implement backend functionality to support role assignment and modification. This includes creating APIs to update the user role information in the database based on inputs from the administrative dashboard.
[6 empty] | T053 | Develop and integrate access control logic in the system that enforces role-based access restrictions across all functionalities. This should include middleware or services that check user permissions before allowing access to sensitive operations or data.
[6 empty] | T054 | Conduct comprehensive testing to verify that the role-based access control system works as expected. This should include unit tests for individual components and integration tests that simulate real-world usage scenarios to ensure there is no unauthorized access.
[6 empty] | T055 | Prepare and maintain documentation detailing the role-based access control system and how to manage it through the administrator dashboard. Include guidelines on how to assign roles, modify access levels, and troubleshoot common issues.
|  |  | S007 | As a System Administrator, I want to implement a two-factor authentication system so that the security of user logins is enhanced. | Integration of a two-factor authentication system using SMS or email verification. Successful login only after the second factor of authentication is verified. Rate limiting to prevent brute force attacks. Logging of all login attempts. | T056 | Research and select a two-factor authentication (2FA) service provider that supports integration via SMS and email, ensuring compatibility with the current system architecture. This task should be completed within 1 week.
[6 empty] | T057 | Develop a module to integrate the selected 2FA service into the existing login system. This includes API integration for sending OTP via SMS or email. Target completion within 2 weeks.
[6 empty] | T058 | Implement the user interface changes needed to accommodate two-factor authentication on the login page, such as additional fields for OTP input. This should be designed, reviewed, and implemented within 1.5 weeks.
[6 empty] | T059 | Configure the 2FA module to require successful verification of the second factor (OTP) after the initial password is deemed correct. This logic should be implemented and tested within 1 week.
[6 empty] | T060 | Setup rate limiting mechanisms to limit the number of OTP requests a user can make within a specified time frame to prevent brute force attacks. Complete the setup and testing within 1 week.
[6 empty] | T061 | Develop and integrate a comprehensive logging mechanism that records all login attempts, including successful and unsuccessful 2FA attempts, with timestamps and user identifiers. This should be implemented and tested thoroughly within 2 weeks.
[6 empty] | T062 | Conduct security testing to ensure that the two-factor authentication mechanism is secure and functional, which includes penetration testing and vulnerability scanning. Allocate 2 weeks for thorough testing.
[6 empty] | T063 | Prepare documentation that outlines the new login process with two-factor authentication, including troubleshooting steps for common issues related to 2FA. This documentation should be prepared and reviewed within 1 week.
[6 empty] | T064 | Organize a training session for the support team on the new two-factor authentication system to ensure they can assist users effectively. Plan and execute the training session within 1 week after system implementation.
[6 empty] | T065 | Deploy the two-factor authentication update to a staging environment for live testing with a select group of users to gather feedback and make adjustments as necessary. Set aside 2 weeks for this testing phase.
[6 empty] | T066 | Plan and execute a full system rollout of the two-factor authentication feature, including communication to users about changes to the login process. Rollout should be completed within 1 week after successful staging tests.
|  |  | S008 | As a System Administrator, I want to have an audit logging system so that all user activities can be tracked and reviewed for security compliance. | All user actions within the system are logged with timestamps. Logs include user ID, action taken, and time of action. Logs are immutable and stored securely. System administrators can easily retrieve and view logs. | T067 | Design and implement an audit log schema that includes fields for user ID, action taken, timestamps, and additional metadata necessary to track user activities. Ensure the schema supports the required immutability and security features. Estimated duration: 2 days.
[6 empty] | T068 | Develop a logging mechanism that captures all user actions across the system, including logins, logouts, and other significant activities. This mechanism should adhere to the designed schema and include real-time logging capabilities. Estimated duration: 3 days.
[6 empty] | T069 | Implement server-side functionality to ensure all logs are stored securely and are immutable. This might involve configuring file permissions, using write-once read-many storage, or integrating with a secure log management service. Estimated duration: 2 days.
[6 empty] | T070 | Create an administrative interface to allow system administrators to view and search through the audit logs. The interface should include filters for user ID, date range, and type of activity. Ensure the interface is user-friendly and accessible within the existing system’s admin dashboard. Estimated duration: 3 days.
[6 empty] | T071 | Conduct thorough testing of the audit logging system to ensure that it captures all required actions, logs are immutable, securely stored, and that the viewing interface works correctly across different devices and browsers. Estimated duration: 2 days.
[6 empty] | T072 | Prepare and update system documentation to include details about the new audit logging features, usage guidelines, and troubleshooting steps for system administrators. Also, ensure to provide training to administrators on how to effectively use the new audit log system. Estimated duration: 1 day.
|  |  | S009 | As a System Administrator, I want a user management interface so that I can easily manage user accounts, roles, and statuses. | Interface allows viewing, adding, editing, and disabling user accounts. Changes in the interface reflect immediately in the system’s operation. Secure access to the user management interface itself. Capability to filter and search user list. | T073 | Design the user interface for the user management system, ensuring it includes views for adding, editing, and disabling user accounts. Task to be completed by a UX designer within 1 week.
[6 empty] | T074 | Develop backend APIs to support viewing, adding, editing, and disabling user accounts. This task includes creating database procedures and necessary security measures to handle these operations securely. Task to be completed by a backend developer in 2 weeks.
[6 empty] | T075 | Implement real-time updating functionality in the user management interface to ensure that any changes in the interface (add, edit, disable) reflect immediately in the system's operation. Task to be completed by a frontend developer in 1.5 weeks.
[6 empty] | T076 | Develop authentication and authorization measures to secure access to the user management interface. This includes setting up roles and permissions for system administrators. Task to be completed by a security specialist in 1 week.
[6 empty] | T077 | Integrate filtering and search capabilities in the user management interface to allow administrators to easily locate user accounts. This task involves both frontend UI components and backend APIs for search functionality. Task to be completed by a full-stack developer in 2 weeks.
[6 empty] | T078 | Conduct a security audit of the user management interface to ensure it meets compliance and security standards. This audit will check for vulnerabilities and ensure that data handling practices are secure. Task to be conducted by a security auditor in 1 week after the development phase is complete.
[6 empty] | T079 | Set up system logging for all user management activities to ensure changes can be traced and audited. This includes logging add, edit, and disable actions performed through the interface. Task to be completed by a backend developer in 1 week.
[6 empty] | T080 | Prepare documentation for the user management interface, detailing functionality, user roles, security measures, and usage instructions. This task is to be completed by a technical writer in 1 week.
[6 empty] | T081 | Implement unit and integration tests for the new user management features to ensure stability and functionality across the system. This includes tests for API endpoints, security features, and user interface elements. Task to be completed by a QA engineer in 1.5 weeks.
[6 empty] | T082 | Plan and execute a training session for system administrators to familiarize them with the new user management interface. This includes preparing instructional materials and conducting a live tutorial. Task to be completed by a training coordinator in 1 week after the deployment.
|  |  | S010 | As a System Administrator, I want all sensitive data to be encrypted both at rest and in transit so that data breaches can be prevented. | Implementation of industry-standard encryption protocols. Regular security audits to ensure encryption is unbroken. Training for developers on secure data handling practices. Automated data integrity checks. | T083 | Research and select industry-standard encryption protocols suitable for both data at rest and data in transit. Ensure that the chosen protocols meet current security standards and are widely recognized for effectiveness. Completion of this task should be documented with a technical selection report by the end of the first week.
[6 empty] | T084 | Implement encryption using the selected protocols in the system. This includes encrypting all sensitive data stored in databases (data at rest) and data being transmitted over networks (data in transit). The implementation should be tested in a development environment and reviewed by the security team to ensure correctness. This task should be completed within two weeks from the start date.
[6 empty] | T085 | Schedule and conduct regular security audits to ensure that the encryption implementation remains unbroken and effective against new vulnerabilities. Develop a routine audit plan that includes monthly checks and a comprehensive semi-annual review. The initial setup of the audit schedule should be completed by the end of the third week.
[6 empty] | T086 | Develop and deliver a training program for developers on secure data handling practices, focusing on the importance of encryption and the specific protocols used. The training should include practical examples and best practices. The completion of the first training session should be within one month of project initiation.
[6 empty] | T087 | Implement automated data integrity checks that run at specified intervals to ensure that the encrypted data has not been tampered with or corrupted. This includes setting up alerts for any anomalies detected during these checks. The implementation and testing of this system should be completed within five weeks.
E003 | Feedback and Issue Tracking System | Create a system for collecting, tracking, and addressing feedback and issues reported by users. This system should allow administrators to tag and categorize issues, respond to tickets, and track resolution progress. | S011 | As a System Administrator, I want to be able to tag feedback and issues with categories like 'Support', 'Feature Request', or 'Bug', so that I can organize and prioritize the requests more efficiently. | Ability to add tags to new and existing tickets Tags should be visible in the ticket overview Administrators should be able to filter tickets based on tags | T088 | Design the database schema for ticket tagging, which includes fields for ticket id, tag type (e.g., 'Support', 'Feature Request', 'Bug'), and timestamp. This task should be completed within 3 working days.
[6 empty] | T089 | Develop an API endpoint to add tags to new and existing tickets. Include validation to ensure only valid tags are submitted. Expected development time is 4 days.
[6 empty] | T090 | Implement a user interface component on the ticket management dashboard where tags can be added or edited. This should be user-friendly and integrate seamlessly with the existing system. Completion targeted within 5 days.
[6 empty] | T091 | Update the ticket overview UI to display tags associated with each ticket. Ensure that the tags are visually distinct and readable. This should be completed within 2 days.
[6 empty] | T092 | Create a feature allowing administrators to filter tickets by tags on the ticket overview dashboard. This includes adding UI components for selecting tags and updating the backend to support filtering logic. Scheduled for completion within 5 days.
[6 empty] | T093 | Conduct a testing phase where the tagging system is assessed for functionality and usability. This should include creating test cases, executing them, and fixing any identified issues. Allocate 3 days for this task.
[6 empty] | T094 | Prepare documentation for the newly developed ticket tagging feature covering how to add, edit, and filter by tags. Aim to complete this within 2 days.
[6 empty] | T095 | Plan and conduct a training session for the system administrators to familiarize them with the new tagging and filtering functionalities. This session should be scheduled for 1 day and occur after the testing phase is successfully completed.
|  |  | S012 | As a System Administrator, I want the ability to respond directly to tickets from within the platform, so that I can effectively communicate with users regarding their issues or feedback. | Response functionality integrated into each ticket Users receive notifications when their ticket is responded to All responses are logged and viewable in ticket history | T096 | Design and implement a response input field within the ticket management system, allowing administrators to enter and submit responses directly associated with specific tickets. This task includes creating UI/UX designs and integrating the input field with the backend system. Ensure that the design is user-friendly and accessible. Expected completion: 3 days.
[6 empty] | T097 | Develop the backend functionality to capture and store responses from system administrators to tickets within the database. This includes setting up database schemas for storing responses with references to the corresponding tickets and user IDs. Ensure data integrity and security. Expected completion: 4 days.
[6 empty] | T098 | Implement a notification system to alert users via email or in-app notifications when a response has been made to their tickets. This system should leverage existing notification services or require the setup of a new service if necessary. Include options for immediate or batch processing of notifications based on system load. Expected completion: 5 days.
[6 empty] | T099 | Create a logging system to record all responses made by system administrators, including timestamp, administrator ID, ticket ID, and response content. Ensure logs are immutable and secure. This involves modifying existing logging mechanisms or building a new component. Expected completion: 4 days.
[6 empty] | T100 | Integrate the response functionality into the existing ticket management dashboard. This includes adding the response field, submit button, and ensuring that responses are displayed in the ticket's history in chronological order. Conduct integration testing to ensure the new feature works seamlessly with existing functionalities. Expected completion: 3 days.
[6 empty] | T101 | Conduct a complete system test to ensure that the response functionality works as expected. This includes testing UI elements, database integration, notification delivery, and log entry creation. Prepare a testing protocol that covers all aspects of the functionality. Expected completion: 2 days.
[6 empty] | T102 | Prepare and update system documentation to include details on the new response functionality, notification setup, and logging. Ensure the documentation is clear and provides enough detail for future maintenance and scalability considerations. Expected completion: 2 days.
[6 empty] | T103 | Conduct a training session for system administrators to familiarize them with the new response functionality. Include best practices for responding to tickets and overview of the logging and notification systems. Expected completion: 1 day.
|  |  | S013 | As a System Administrator, I want to track the progress of issue resolutions, so that I can ensure issues are resolved in a timely manner and keep stakeholders informed. | Progress tracker integrated into each ticket Ability to update and view status (e.g., Open, In Progress, Resolved) Visual indicators or dashboards showing overall progress of tickets | T104 | Design the progress tracking module for the issue resolution system. This includes creating wireframes and defining user interactions for updating and viewing the status of each ticket. Deadline: 7 days from task assignment.
[6 empty] | T105 | Implement the back-end logic to support the progress tracker in the issue resolution system. This should include functions to update the status, retrieve current status, and store changes in the database. Deadline: 10 days from completion of design.
[6 empty] | T106 | Develop the front-end user interface for the progress tracker based on approved designs. This should include dropdown menus or buttons to change status (Open, In Progress, Resolved), and views to display current ticket status. Deadline: 10 days from backend completion.
[6 empty] | T107 | Integrate visual indicators and dashboards into the existing ticket management system to show the progress of tickets. This should include real-time updates and possibly color-coded statuses to easily distinguish between different stages. Deadline: 5 days after frontend setup.
[6 empty] | T108 | Conduct a testing phase for the progress tracking feature, including unit tests, integration tests, and user acceptance testing (UAT) to ensure that the system meets the defined acceptance criteria. Deadline: 7 days after integration completion.
[6 empty] | T109 | Deploy the updated ticket tracking system to the production environment after successful testing and review. Plan for potential downtimes and notify all stakeholders of the upcoming changes. Deployment deadline: 3 days after successful testing.
[6 empty] | T110 | Provide training for system administrators on how to use the new progress tracking features. Include documentation on how to update, view, and understand the progress indicators in the ticket management system. Training completion: 5 days after deployment.
|  |  | S014 | As a System Administrator, I want the ability to categorize issues and feedback when they are logged, so that they can be directed to the appropriate departments or personnel. | A dropdown menu of categories for assigning during the ticket creation Categorization data should be editable post ticket creation Reports available based on categorization for analytics purposes | T111 | Design a user interface for the feedback and issue tracking system with a dropdown menu for categorization. This menu should include predefined categories like 'Support', 'Feature Request', or 'Bug'. Ensure the design allows for the addition of new categories as needed. Completion target: 1 week.
[6 empty] | T112 | Develop the backend functionality to support dynamic categorization of feedback and issues. This includes database schema design for storing categories and linking them to each feedback or issue entry. Ensure the system supports CRUD operations on categories. Completion target: 2 weeks.
[6 empty] | T113 | Implement frontend functionality for the categorization dropdown menu in the feedback and issue tracking system. This includes populating the dropdown from the database and making it interactive for users to select during the ticket creation. Completion target: 1 week.
[6 empty] | T114 | Create backend services to enable editing of categorization data post ticket creation. This should include API endpoints for updating the category of an existing ticket in the database. Ensure proper authentication and authorization checks are in place. Completion target: 1 week.
[6 empty] | T115 | Develop reporting functionality that utilizes the categorization data. This should include generating reports based on ticket categories, which can help in analytics and directing resources appropriately. Reports should be accessible from the admin dashboard. Completion target: 2 weeks.
[6 empty] | T116 | Conduct integration testing to ensure that the new categorization features work seamlessly with existing components of the feedback and issue tracking system. This includes testing the dropdown functionality, post-creation edits, and reporting features. Completion target: 1 week.
[6 empty] | T117 | Prepare documentation for the new categorization features, detailing how system administrators can use these features to manage feedback and issues more effectively. Include screenshots and examples of reports. Completion target: 3 days.
[6 empty] | T118 | Plan and execute a training session for system administrators on how to use the new categorization features in the feedback and issue tracking system. Include practical demonstrations and Q&A sessions. Completion target: 1 day.
|  |  | S015 | As a System Administrator, I want the system to automatically route tickets based on the tags and categories assigned, so that the right team or person can address them quickly. | Automated routing rules setup based on tags or categories Notifications sent to designated team members when a ticket is routed to them Ability to manually override automated routing if necessary | T119 | Design and document the workflow for ticket routing, including identifying necessary tags and categories that trigger routing rules. Completion due in 3 days.
[6 empty] | T120 | Develop the backend logic to automatically route tickets based on predefined tags or categories. This includes coding conditional statements and routing algorithms. Expected to complete within 5 days.
[6 empty] | T121 | Implement a notification system to alert designated team members via email or in-app notification when a ticket is routed to them. Target completion within 4 days.
[6 empty] | T122 | Create a manual override feature in the ticket routing system, allowing administrators to reroute tickets as needed. Include a user interface button and the backend logic to support manual changes. Scheduled for completion in 4 days.
[6 empty] | T123 | Conduct unit testing on the automated ticket routing functionality to ensure that tickets are routed correctly based on tags/categories and that notifications are sent as expected. Plan for 2 days of testing.
[6 empty] | T124 | Set up an integration testing phase to verify that the new routing system interacts correctly with the existing ticketing system, ensuring no disruptions in other functionalities. Allow 3 days for this task.
[6 empty] | T125 | Prepare and deliver a training session for system administrators to educate them on using the new routing features, including how to set up tags/categories and how to manually override the system. Schedule the session within 7 days post-implementation.
[6 empty] | T126 | Deploy the updated ticket routing system to the production environment after successful testing and training, aiming for minimal downtime. Plan deployment for off-peak hours and complete within 1 day.
[6 empty] | T127 | Monitor the system post-deployment to ensure the automated routing and notification systems are functioning as intended. Continuous monitoring for the first week after launch.
|  |  | S016 | As a System Administrator, I want a user-friendly form for feedback and issue reporting, so that users can easily submit their concerns and suggestions. | Form should be accessible from the main user interface Fields to capture detailed information (e.g., description, category, urgency level) Confirmation message or email upon successful submission | T128 | Design a user-friendly web form interface accessible from the main dashboard of the system's user interface. The design should prioritize simplicity and clarity to encourage user engagement. Estimated completion: 3 days.
[6 empty] | T129 | Implement input fields in the web form to capture essential information such as description of the feedback or issue, category (e.g., bug, feature request, support), and urgency level (e.g., low, medium, high). Use dropdown menus for categories and urgency levels to standardize responses. Estimated completion: 2 days.
[6 empty] | T130 | Develop backend functionality to handle form submissions, including data validation to ensure all required fields are filled and data formats are correct. Ensure this process includes error handling to manage incomplete or incorrect submissions. Estimated completion: 4 days.
[6 empty] | T131 | Integrate an email notification system that sends a confirmation message to the user's registered email address upon successful form submission. The message should include a summary of the submitted information and a thank you note or acknowledgment. Estimated completion: 2 days.
[6 empty] | T132 | Conduct a series of tests to ensure the form is accessible, user inputs are correctly captured, and confirmation emails are sent as expected. This should include cross-browser testing to ensure compatibility and responsiveness. Estimated completion: 3 days.
[6 empty] | T133 | Deploy the feedback form to the production environment and monitor the system for any issues during the initial release phase. Provide immediate technical support to address any user concerns or bugs reported. Estimated completion: 1 day.
[6 empty] | T134 | Gather initial user feedback on the usability of the form and make adjustments based on suggestions and user behavior observations. This may involve UI/UX tweaks to improve form interaction. Estimated review and update completion: 5 days post-launch.
|  |  | S017 | As a System Administrator, I want a dashboard that provides a quick overview of all current feedback and issues, so that I can quickly assess overall system health and user satisfaction. | Dashboard displays real-time data Key metrics include number of open tickets, resolution time, and user satisfaction rate Ability to drill down into specific tickets from the dashboard | T135 | Design the user interface for the dashboard that provides a quick overview of all current feedback and issues. Include sections for real-time data, key metrics, and drill-down capabilities. Ensure the design is intuitive and user-friendly. Estimated completion: 3 days.
[6 empty] | T136 | Develop backend API to fetch real-time data including number of open tickets, resolution time, and user satisfaction rate. Ensure data is updated in real-time and can handle concurrent requests efficiently. Estimated completion: 5 days.
[6 empty] | T137 | Implement frontend functionality for the dashboard using the designed UI. Use frameworks like React or Angular for efficient rendering and state management. Integrate with backend APIs to display real-time data. Estimated completion: 4 days.
[6 empty] | T138 | Create a database schema to store and manage tickets with fields for status, resolution time, and user satisfaction metrics. Ensure the schema supports efficient queries for real-time data fetching. Estimated completion: 2 days.
[6 empty] | T139 | Set up a real-time analytics engine using tools like Elasticsearch or similar to calculate and update key metrics dynamically as data changes. Estimated completion: 3 days.
[6 empty] | T140 | Develop functionality to allow system administrators to drill down into specific tickets from the dashboard. This should include filtering and sorting capabilities to manage a large volume of tickets effectively. Estimated completion: 4 days.
[6 empty] | T141 | Integrate user feedback mechanisms on the dashboard to collect and analyze user satisfaction data. Implement features to capture user ratings and comments directly from the dashboard interface. Estimated completion: 2 days.
[6 empty] | T142 | Conduct thorough testing of the dashboard to ensure all features function correctly and real-time data is accurately displayed. Include unit tests, integration tests, and user acceptance testing. Estimated completion: 3 days.
[6 empty] | T143 | Deploy the dashboard to a production environment ensuring secure access for system administrators only. Set up monitoring and logging to observe system performance and catch potential issues early. Estimated completion: 2 days.
[6 empty] | T144 | Train system administrators on how to use the new dashboard effectively. Prepare training materials and conduct live training sessions to cover all functionalities, including real-time data monitoring and ticket drill-down. Estimated completion: 2 days.
E004 | User Account Management | Provide functionalities for system administrators to create, manage, and deactivate user accounts for doctors, ensuring appropriate access and data security. | S018 | As a System Administrator, I want to create user accounts for doctors so that they can access the system and manage patient data securely. | System should allow creation of doctor accounts with required fields such as MD ID, name, hospital affiliation. Input validation for all fields must ensure data integrity. A success message should be displayed after a successful account creation. The system logs the account creation action for audit purposes. | T145 | Design a user interface for creating doctor accounts. The interface should include input fields for MD ID, name, and hospital affiliation. This task should be completed within 3 days by the UI/UX team.
[6 empty] | T146 | Implement input validation for the doctor account creation form. Validation rules should ensure that the MD ID is numeric, the name is alphanumeric, and the hospital affiliation is selected from a predefined list. This task should be completed within 2 days by the front-end development team.
[6 empty] | T147 | Develop the backend service for processing doctor account creation. This service should receive data from the form, validate input server-side, and store the information in the database. This task should be completed within 5 days by the back-end development team.
[6 empty] | T148 | Integrate a success message in the UI that triggers upon successful account creation. The message should be clear and user-friendly. This task must be tested and completed within 1 day by the front-end team.
[6 empty] | T149 | Implement logging functionality that records all account creation actions. The log should include user ID, timestamp, and a description of the action. This task requires 3 days for the back-end team to complete.
[6 empty] | T150 | Conduct a security audit on the new account creation feature to ensure data integrity and compliance with privacy standards. Prepare a report with findings and recommendations. This task should be completed within 5 days by the IT security team.
[6 empty] | T151 | Prepare documentation for the system administrators to manage doctor accounts, detailing the process and controls in place. Include screenshots and step-by-step instructions. The documentation team should complete this task within 3 days.
[6 empty] | T152 | Set up a testing phase where system administrators can test the new account creation functionalities in a controlled environment. Collect feedback and make necessary adjustments. This testing phase should last for 2 weeks with ongoing support from the development team.
|  |  | S019 | As a System Administrator, I want to update and manage doctor accounts to ensure the information remains accurate and relevant. | System provides an interface to view all doctor accounts in a list with edit options. Administrator can update name, hospital affiliation, and other details. Each update operation must be logged and traceable. A confirmation message is displayed after successful updates. | T153 | Design a user interface for administrators to view all doctor accounts in a list format. Include sort and filter options to facilitate easy navigation. Estimated completion time: 3 days.
[6 empty] | T154 | Implement backend API endpoints to retrieve doctor account data from the database. Ensure endpoints support pagination, sorting, and filtering based on parameters such as name and hospital affiliation. Estimated completion time: 3 days.
[6 empty] | T155 | Develop front-end functionality to connect with the backend API and display the list of doctor accounts. Implement dynamic loading and error handling. Estimated completion time: 3 days.
[6 empty] | T156 | Create an edit form for each doctor account listed. The form should include fields for name, hospital affiliation, and other pertinent details. Ensure fields have proper validation rules. Estimated completion time: 3 days.
[6 empty] | T157 | Implement backend logic to handle the submission of updated doctor account details. Ensure that the API checks for proper authorization and validates all input before updating the database. Estimated completion time: 4 days.
[6 empty] | T158 | Create a logging mechanism to record each update operation made to doctor accounts. Include details such as the administrator's user ID, timestamp, and nature of the changes. Estimated completion time: 2 days.
[6 empty] | T159 | Integrate a confirmation message pop-up in the UI that triggers after successful updates. The message should confirm the successful update and display any relevant information or errors. Estimated completion time: 1 day.
[6 empty] | T160 | Conduct unit testing to ensure that the interface functions correctly and all data handling is secure. Test cases should include tests for API security, data validation, and user feedback mechanisms. Estimated completion time: 3 days.
[6 empty] | T161 | Arrange a review session with the stakeholders to demonstrate the updated management interface and gather feedback. Implement any necessary adjustments based on the feedback received. Estimated completion time: 2 days.
|  |  | S020 | As a System Administrator, I want the ability to deactivate doctor accounts to restrict access when necessary for security or administrative reasons. | System allows the administrator to deactivate an account from the manage accounts page. Deactivated accounts should no longer be able to access the system. A success message should confirm the deactivation. The deactivation action must be logged for audit purposes. | T162 | Design a UI component in the admin dashboard to list all active doctor accounts with options to deactivate. Include a 'Deactivate' button next to each account entry. Estimated completion: 2 days.
[6 empty] | T163 | Implement backend service to handle deactivation requests. This service should change the account status to 'inactive' and prevent any further system access. Estimated completion: 3 days.
[6 empty] | T164 | Develop a confirmation mechanism that prompts the administrator to confirm the deactivation before proceeding. This prevents accidental deactivation. Estimated completion: 1 day.
[6 empty] | T165 | Upon successful deactivation, display a success message to the administrator confirming that the account has been deactivated. Estimated completion: 1 day.
[6 empty] | T166 | Create a logging mechanism to record all deactivation actions. This log should include the administrator's user ID, timestamp, and the doctor's account ID affected by the deactivation. Estimated completion: 2 days.
[6 empty] | T167 | Perform integration testing to ensure that deactivated accounts cannot log in or access the system post-deactivation. Estimated completion: 2 days.
[6 empty] | T168 | Conduct security testing to validate that the deactivation feature is secure and that logs are written correctly and stored securely. Estimated completion: 2 days.
|  |  | S021 | As a System Administrator, I want to reset passwords for doctor accounts to assist with account recovery and maintain account security. | System allows administrators to initiate a password reset for any doctor account. A temporary password is generated and emailed to the doctor’s registered email address. The system logs the password reset action. Doctor is prompted to change the password upon next login. | T169 | Design a password reset feature within the system's administration interface that allows administrators to initiate password resets for doctor accounts. Include a clear 'Reset Password' button next to each doctor's account listing. Estimated completion time: 2 days.
[6 empty] | T170 | Develop the backend functionality to generate a temporary, secure, and random password when an administrator initiates a password reset. Ensure the temporary password meets security standards (e.g., length, complexity). Estimated completion time: 3 days.
[6 empty] | T171 | Implement email integration to automatically send the temporary password to the doctor’s registered email address. The email should include instructions for logging in and changing the password. Estimated completion time: 2 days.
[6 empty] | T172 | Update the system's logging mechanism to record password reset actions, including the administrator's user ID, the affected doctor’s account, and the timestamp of the action. Ensure that the log is secure and only accessible to authorized personnel. Estimated completion time: 2 days.
[6 empty] | T173 | Modify the doctor's login workflow to prompt for a password change upon login with a temporary password. This should include a user interface for entering a new password and confirming it. Estimated completion time: 3 days.
[6 empty] | T174 | Conduct comprehensive testing of the password reset functionality to ensure it works as expected under various scenarios like incorrect email addresses, security breaches, and network failures. Include both automated and manual testing approaches. Estimated completion time: 3 days.
[6 empty] | T175 | Prepare and update system documentation to include details about the new password reset process, covering steps for both administrators and doctors. Ensure clear instructions are provided for secure password creation. Estimated completion time: 1 day.
[6 empty] | T176 | Schedule a training session for system administrators to educate them on how to manage the password reset process, including understanding the log data and handling user inquiries related to password resets. Estimated completion time: 1 day.
|  |  | S022 | As a System Administrator, I want to view logs of all account-related activities to monitor and audit usage and modifications by other administrators. | System provides a secure section to view logs of account activities including creation, updates, deactivation, and password resets. Logs should include date, time, user ID of the admin who performed the action, and the nature of the action. Logs should be searchable by date range and type of activity. System should display logs in a readable and organized manner. | T177 | Design and implement a database schema for logging account-related activities including account creation, updates, deactivation, and password resets. Include fields for date, time, user ID, nature of action, and other relevant metadata. Set up indexing to optimize search operations.
[6 empty] | T178 | Develop a secure backend API that captures account-related activities and stores them in the logging database. Ensure all relevant actions within the account management module trigger appropriate logging with detailed information.
[6 empty] | T179 | Create a user interface in the admin dashboard for viewing logs of account-related activities. This interface should include filters for date range and type of activity, and display results in a readable and organized manner.
[6 empty] | T180 | Implement search functionality in the log viewing interface that allows administrators to search logs based on custom criteria such as date range, user ID, and type of activity.
[6 empty] | T181 | Ensure security measures are in place to restrict access to the logs, allowing only authorized system administrators to view them. Implement authentication checks and encryption as necessary.
[6 empty] | T182 | Conduct thorough testing of the logging system to ensure accuracy of the data captured, effectiveness of the search functionality, and compliance with security requirements.
[6 empty] | T183 | Prepare documentation on how to use the logging system within the admin dashboard, including details on how to perform searches and interpret log entries.
E005 | System Health Monitoring | Develop tools for monitoring the health and performance of the system, including real-time analytics and automated alerts to notify administrators of potential issues or downtimes. | S023 | As a System Administrator, I want a dashboard that displays real-time analytics of the system's health so that I can monitor performance metrics and system statuses continuously. | Dashboard updates in real-time. Displays key performance metrics such as CPU usage, memory usage, network status, and disk space. Has a section for viewing the current status of all servers and critical services. Accessible via web interface on multiple devices. | T184 | Research and select real-time monitoring tools and libraries compatible with the existing system architecture that can monitor CPU usage, memory usage, network status, and disk space. Completion target: 3 days from start date.
[6 empty] | T185 | Design a schema for the dashboard that includes sections for each of the key performance metrics (CPU usage, memory usage, network status, disk space) and a separate section for the current status of all servers and critical services. Completion target: 5 days from approval of tools.
[6 empty] | T186 | Develop front-end components for the dashboard using a responsive web design to ensure accessibility via multiple devices. Incorporate data visualization libraries for metric displays. Completion target: 10 days from schema approval.
[6 empty] | T187 | Implement back-end services to continuously fetch and push real-time data to the front-end dashboard components. Ensure that data fetching processes are optimized for minimal latency. Completion target: 15 days from front-end components completion.
[6 empty] | T188 | Set up a testing environment to simulate real-time data updates on the dashboard and validate the performance of the dashboard under varying loads. Completion target: 5 days from back-end service implementation.
[6 empty] | T189 | Conduct cross-device compatibility testing to ensure the dashboard is accessible and functional across different web-capable devices. Address any UI/UX issues that arise during testing. Completion target: 5 days from initial testing phase completion.
[6 empty] | T190 | Prepare and deliver a training session for the system administrators on how to use the new dashboard, emphasizing the real-time updates and sections specific to server status and critical services. Completion target: 3 days after passing all testing phases.
[6 empty] | T191 | Deploy the dashboard to the production environment after obtaining approval from the project stakeholders. Include rollback procedures in case of deployment issues. Completion target: 2 days after training completion.
[6 empty] | T192 | Monitor the dashboard performance post-deployment and collect feedback from system administrators to identify any potential improvements or necessary adjustments. Ongoing for 30 days post-deployment.
|  |  | S024 | As a System Administrator, I want to receive automated alerts when the system detects failures or abnormalities so that I can respond promptly to potential issues. | Alerts are triggered by predefined conditions such as service downtime, performance degradation, or error rates exceeding normal thresholds. Alerts are delivered via email and SMS. Provides a clear description of the issue within the alert. Includes time of detection and affected components in the alert. | T193 | Define the list of system failures and abnormalities that should trigger alerts, including service downtime, performance degradation, and abnormal error rates. Deadline: 1 week from project start.
[6 empty] | T194 | Develop a monitoring system capable of detecting the predefined conditions. This includes integrating or enhancing existing monitoring tools to capture real-time data on system performance, error rates, and service status. Deadline: 3 weeks from project start.
[6 empty] | T195 | Implement an alert system using a reliable third-party service or in-house solution that supports multi-channel notifications, including email and SMS. Evaluate multiple services for reliability and integration ease. Deadline: 2 weeks from project start.
[6 empty] | T196 | Set up the mechanics for the alert notifications to include concise, clear descriptions of the issue detected, the time of detection, and the affected system components. Ensure the alerts contain actionable information for quick resolution. Deadline: 2 weeks after the monitoring system is in place.
[6 empty] | T197 | Integrate the alert system with the monitoring tools to automatically trigger alerts when predefined conditions are met. Include data points like time of detection and affected components in the alert messages. Deadline: 3 weeks after the monitoring system is in place.
[6 empty] | T198 | Test the complete alert system to ensure that it works as expected under different scenarios such as simulated service downtime, performance degradation, and high error rates. This should verify both detection and notification functionalities. Deadline: 1 week after alert system integration.
[6 empty] | T199 | Deploy the alert system to the production environment and monitor its performance for the initial month, tweaking thresholds and parameters as needed based on the alerts generated and feedback from system administrators. Deadline: 1 month after system deployment.
[6 empty] | T200 | Prepare and deliver training sessions for system administrators on how to respond to alerts, including steps for further investigation and resolution. Include guidelines on logging and documenting incidents arising from alerts. Deadline: 2 weeks after system deployment.
|  |  | S025 | As a System Administrator, I want a centralized log management tool that aggregates logs from all system components so that I can troubleshoot and analyze issues efficiently. | Supports aggregation of logs from various sources including servers, applications, and databases. Allows filtering and searching of log data by time range, severity, or keywords. Provides options to download logs for offline analysis. Real-time log updates and display. | T201 | Design and develop a centralized log aggregation system that collects logs from various sources including servers, applications, and databases. Allocate 3 weeks for completion.
[6 empty] | T202 | Implement filtering capabilities in the log aggregation system to allow users to filter logs by time range, severity, or keywords. Schedule 1 week for this task.
[6 empty] | T203 | Develop functionality within the log management tool that provides options for users to download logs for offline analysis. Estimate 1 week for development.
[6 empty] | T204 | Ensure that the log management tool updates and displays logs in real-time. This task should include setup of the necessary backend services and UI updates, with a timeframe of 2 weeks.
[6 empty] | T205 | Conduct a testing phase to ensure that all functionalities of the log management tool, including aggregation, filtering, download, and real-time display, work according to the requirements. Allocate 2 weeks for thorough testing.
[6 empty] | T206 | Prepare and deliver a training session for system administrators to demonstrate how to use the new log management tool effectively. Plan for a 1-day training session after the deployment of the tool.
[6 empty] | T207 | Deploy the log management tool to the production environment and monitor its performance for 1 week to ensure stability and proper operation.
|  |  | S026 | As a System Administrator, I want a tool that analyzes and displays performance trends over time so that I can identify potential issues before they become critical. | Generates reports on performance metrics over customizable time frames. Identifies and highlights performance degradation trends. Supports visualization of data through graphs and charts. Allows for automated weekly or monthly performance reporting. | T208 | Design a data model for storing performance metrics with attributes for timestamps, metric types, and values.
[6 empty] | T209 | Develop a backend service to collect and store performance metrics from various system components at configurable intervals.
[6 empty] | T210 | Implement a metrics aggregation logic that compiles data across different time frames (hourly, daily, weekly, monthly) for reporting.
[6 empty] | T211 | Create algorithms to analyze collected data and identify trends of performance degradation over time.
[6 empty] | T212 | Develop a front-end component for visualizing performance metrics using graphs and charts, integrating with existing system dashboards.
[6 empty] | T213 | Implement a reporting feature that allows administrators to generate and download performance reports in various formats (e.g., PDF, Excel).
[6 empty] | T214 | Schedule and automate the generation of weekly and monthly performance reports, with email notifications to administrators upon completion.
[6 empty] | T215 | Conduct a testing phase to ensure the accuracy of performance trends and the reliability of automated reporting features.
[6 empty] | T216 | Prepare documentation for system administrators on how to use the new performance trend analysis tool and interpret the reports generated.
|  |  | S027 | As a System Administrator, I want a feature to monitor user activities and access within the system to ensure security and compliance with policies. | Tracks and records all user login sessions and activities. Provides alerts on unauthorized access attempts. Allows administrators to view reports of user activities. Supports filtering activity logs by user, date, and type of activity. | T217 | Design and implement a database schema to store user activity logs, including fields for user ID, action type, timestamp, and description. Ensure the database supports efficient querying by user, date, and action type. Estimated completion time: 3 days.
[6 empty] | T218 | Develop a backend service to capture and record user activities in real-time. This service should hook into existing user actions across the system to log all login sessions, modifications, and other significant activities. Estimated completion time: 5 days.
[6 empty] | T219 | Implement a secure API endpoint for fetching activity logs from the database. The endpoint should require system administrator authentication and support filtering parameters such as user ID, date range, and action type. Estimated completion time: 4 days.
[6 empty] | T220 | Create an alert system to notify system administrators of unauthorized access attempts. This should include real-time monitoring of login attempts and triggers alerts if suspicious patterns are detected, such as multiple failed login attempts. Estimated completion time: 4 days.
[6 empty] | T221 | Develop a user-friendly dashboard interface for system administrators to view and filter user activity logs. The dashboard should allow administrators to easily sort and filter activities by user, date, and type, and view detailed information about each activity. Estimated completion time: 5 days.
[6 empty] | T222 | Integrate the user activity tracking system with existing system logs to provide a comprehensive view of all user interactions with the system, enhancing the ability to monitor and secure the platform. Estimated completion time: 3 days.
[6 empty] | T223 | Conduct a security review and testing phase to ensure that the user activity logging and alert system is secure from external threats and meets compliance requirements. This includes penetration testing and code review. Estimated completion time: 4 days.
[6 empty] | T224 | Prepare documentation for the system administrators on how to use the new dashboard and alerts system, including details on how to interpret the logs and respond to alerts. Estimated completion time: 2 days.
E006 | Regulatory Compliance Management | Ensure that the platform remains compliant with HIPAA and other relevant health data regulations, providing system administrators with the tools needed to audit, update, and maintain compliance. | S028 | As a System Administrator, I want an audit log feature so that I can track all user activities related to data access and modifications within the system to ensure compliance with HIPAA regulations. | Each user action related to data access or modification must be logged with a timestamp. Logs should include user ID, action type, date/time, and affected data fields. The system must provide a secure way to access and search through these logs. Logs cannot be modified or deleted by any user. | T225 | Design and implement a secure logging system that captures all user actions related to data access or modification in the healthcare platform. Each entry must include a timestamp, user ID, action type, date/time, and affected data fields. Ensure that the logging functionality is integrated with existing data access mechanisms to automatically capture this information.
[6 empty] | T226 | Develop a role-based access system for the audit logs to ensure only authorized system administrators can access this sensitive information. Implement strict authentication and authorization checks before granting access to the logs.
[6 empty] | T227 | Create a user interface for the audit log that allows system administrators to easily search through and filter logs by user ID, action type, date/time, and data fields. The interface should be intuitive and provide advanced search capabilities to quickly locate specific log entries.
[6 empty] | T228 | Implement security measures to protect the integrity and immutability of the audit logs. Use cryptographic techniques to ensure that logs cannot be modified or deleted by any users, including administrators. Regularly test these security measures through penetration testing and security audits.
[6 empty] | T229 | Set up automated alerts and notifications for system administrators when critical data access or modifications are logged. These alerts should help in proactively monitoring potential compliance issues or data breaches.
[6 empty] | T230 | Schedule and conduct regular training sessions for all new and existing system administrators about the importance of audit logs and how to effectively use the audit log system to monitor and ensure compliance with HIPAA regulations.
[6 empty] | T231 | Integrate the audit log system with the existing healthcare platform's back-end architecture, ensuring minimal impact on system performance and user experience.
[6 empty] | T232 | Document the audit log system's design, functionalities, user manual, and best practices in the system's knowledge base to assist system administrators in using the system effectively.
|  |  | S029 | As a System Administrator, I want to receive notifications about changes in HIPAA regulations so that I can ensure the platform updates its compliance measures in a timely manner. | The system should integrate with an external HIPAA compliance notification service. Notifications about compliance updates must be automatically pushed to administrators. The system should log all received compliance updates and actions taken by administrators. | T233 | Research and select a reliable HIPAA compliance notification service to integrate with the platform. Ensure the service provides real-time updates on HIPAA regulations. Set a deadline for selection and integration plan within 2 weeks.
[6 empty] | T234 | Develop an integration module to connect the chosen HIPAA compliance notification service with the platform. This should include API integration that pulls compliance updates and pushes them into the platform's notification system. Aim to complete the development and initial testing within 3 weeks.
[6 empty] | T235 | Implement a notification system within the platform to automatically alert administrators of any HIPAA compliance updates received from the service. Notifications should be visible on the admin dashboard and optionally sent via email. Schedule implementation to be completed in 1 week.
[6 empty] | T236 | Create a logging system to record all received HIPAA compliance updates and the actions taken by administrators in response to these updates. This system must ensure that logs are secure, immutable, and searchable. Plan to complete the logging system within 2 weeks.
[6 empty] | T237 | Conduct a comprehensive testing phase to ensure that the integration works seamlessly, notifications are correctly pushed to administrators, and logging functions as required. This testing should cover edge cases and failure scenarios. Allocate 1 week for complete testing.
[6 empty] | T238 | Prepare and deliver training sessions for administrators on how to use the new features for monitoring HIPAA compliance updates. Include guidelines on how to respond to notifications and the importance of logging actions. Schedule training sessions to be completed within 1 week after system deployment.
[6 empty] | T239 | Set up a feedback mechanism to collect insights from administrators on the usability and effectiveness of the HIPAA compliance notification integration. Use this feedback to make iterative improvements. Initiate feedback collection to start immediately after training and continue for 4 weeks.
|  |  | S030 | As a System Administrator, I want the ability to manage user roles and permissions so that access to sensitive health data is strictly controlled according to HIPAA standards. | The system must support different user roles with specific access permissions. Administrators should be able to add, remove, or modify user roles and permissions without system downtime. Role changes should be logged in the audit trail. | T240 | Design a user role management module capable of creating, viewing, and editing roles with specific permissions. Include roles like System Administrator, Doctor, and Patient, each with unique access permissions.
[6 empty] | T241 | Implement a user interface in the admin dashboard for managing user roles and permissions, ensuring it allows adding, removing, or modifying roles seamlessly.
[6 empty] | T242 | Develop backend logic to support dynamic changes in user roles and permissions without causing system downtime. This includes API endpoints to handle requests for creating, deleting, or updating user roles.
[6 empty] | T243 | Set up an audit trail system to log all changes made to user roles and permissions. Ensure that each log entry includes user ID, action taken, timestamp, and the previous and new values of the role or permission changed.
[6 empty] | T244 | Perform comprehensive testing on the user role management functionality to ensure it operates without system downtime and logs actions accurately in the audit trail.
[6 empty] | T245 | Conduct security testing to verify that the role changes do not inadvertently grant unauthorized access and that all changes are properly authenticated and authorized.
[6 empty] | T246 | Prepare documentation for the user role management system detailing how to use the interface, the impact of each role and permission, and guidelines for secure management of roles according to HIPAA standards.
[6 empty] | T247 | Organize a training session for system administrators to familiarize them with the new user role management tools, focusing on how to handle role assignments compliantly with HIPAA regulations.
[6 empty] | T248 | Deploy the user role management functionality to the staging environment and perform end-to-end testing with simulated real-world scenarios to ensure all features work as expected and comply with HIPAA standards.
|  |  | S031 | As a System Administrator, I want to configure data encryption so that all stored and transmitted patient data is secure against unauthorized access. | All patient data stored in the database must be encrypted at rest. All data transmissions must be encrypted using industry-standard protocols. Administrators should have tools to verify and modify encryption settings. | T249 | Research and select industry-standard encryption protocols suitable for encrypting patient data at rest and in transit, ensuring compatibility with existing systems. Completion expected within 1 week.
[6 empty] | T250 | Develop and implement encryption mechanisms for all patient data stored in the database (at rest encryption). This includes implementing encryption libraries and configuring database encryption settings. Task to be completed within 2 weeks.
[6 empty] | T251 | Integrate secure transmission protocols (such as TLS) to ensure that all data sent over the network is encrypted (in transit encryption). The task should be executed and tested within 2 weeks.
[6 empty] | T252 | Create a user interface for administrators in the admin dashboard to monitor and configure encryption settings. Include features such as viewing current encryption status and updating encryption protocols if needed. This should be ready for initial review in 3 weeks.
[6 empty] | T253 | Conduct a series of tests to verify the security and effectiveness of the new encryption implementations. This includes penetration testing and vulnerability scanning. Complete testing phase by the end of the 4th week.
[6 empty] | T254 | Prepare and conduct a training session for system administrators to educate them on how to use the new tools for verifying and modifying encryption settings. Schedule the session for the end of the 5th week.
[6 empty] | T255 | Document the encryption protocols implemented and the procedures for managing these settings in the system administrator's manual. Documentation to be completed and reviewed by end of the 6th week.
[6 empty] | T256 | Set up an automated alert system to notify administrators of any encryption failures or unauthorized attempts to modify encryption settings. Implementation should be completed within 3 weeks.
|  |  | S032 | As a System Administrator, I want to implement compliance training modules so that all new and existing users are regularly trained on HIPAA compliance requirements. | The system must provide modules that cover all relevant aspects of HIPAA. Training progress and completion must be tracked for each user. Administrators should be able to assign, schedule, and monitor training sessions. Reminders for training should be automatically generated by the system. | T257 | Research and document key aspects of HIPAA compliance that must be covered in the training modules. Ensure coverage is comprehensive and up-to-date. This task should be completed within 1 week by the compliance officer.
[6 empty] | T258 | Develop an interactive training module that includes multimedia elements such as videos, quizzes, and downloadable content covering all identified aspects of HIPAA. Assign this task to the content development team with a deadline of 3 weeks.
[6 empty] | T259 | Implement a tracking system in the training platform that records each user's progress and completion of the training modules. The tracking system should be developed by the IT team and completed within 2 weeks.
[6 empty] | T260 | Create functionalities for administrators to assign training modules to users, schedule training sessions, and monitor completion. This should include an administrative dashboard with user progress indicators and should be developed within 4 weeks by the software development team.
[6 empty] | T261 | Develop an automated reminder system that notifies users of scheduled training sessions and sends follow-up reminders for incomplete modules. This system should integrate with the existing email and notification services and be completed within 2 weeks by the software development team.
|  |  | S033 | As a System Administrator, I want to schedule and conduct regular compliance audits so that the platform adheres to all necessary HIPAA requirements consistently. | The system should allow administrators to schedule audits at regular intervals. Audit results must be logged and accessible to authorized administrators. The system should provide a checklist of HIPAA compliance measures to assess during each audit. | T262 | Design and implement a scheduling mechanism within the system that allows administrators to configure and automate the timing of compliance audits. Ensure that the scheduling feature supports various intervals such as monthly, quarterly, and yearly audits. Completion due within 3 weeks.
[6 empty] | T263 | Develop a logging system for audit results. This system should capture comprehensive details of each audit, including the date, time, scope, and findings. The log should be immutable to ensure data integrity and be stored in a secure manner. Aim to complete this task within 4 weeks.
[6 empty] | T264 | Create a comprehensive checklist of HIPAA compliance measures. This checklist will be used during each audit to assess the platform's adherence to regulations. The checklist should be dynamically updateable to accommodate changes in HIPAA regulations. Task to be finalized in 2 weeks.
[6 empty] | T265 | Implement role-based access control for the audit logs to ensure that only authorized administrators can access the sensitive data. Include capabilities for administrators to view, search, and filter the audit logs based on various parameters such as date range and type of audit. Expected to complete within 3 weeks.
[6 empty] | T266 | Set up automated notifications for administrators to alert them of upcoming and completed audits. These notifications should be configurable according to the preferences of individual administrators. Target to implement this feature within 1 week.
[6 empty] | T267 | Conduct a security review of the newly developed features, especially focusing on the logging mechanism and access controls, to ensure they meet industry standard security practices. Plan for this review to be completed within 2 weeks after all features are developed.
[6 empty] | T268 | Prepare documentation for the new compliance audit features, detailing operation, configuration, and troubleshooting steps. Ensure the documentation is clear and accessible to system administrators. Completion targeted within 1 week after feature completion.
E007 | Integration and Third-party Management | Enable system administrators to manage and configure settings for third-party integrations such as OpenAI and Twilio, ensuring seamless operation and integration reliability. | S034 | As a System Administrator, I want to configure settings for OpenAI integration so that I can manage how AI features interact with our healthcare platform. | Ability to access the OpenAI API configuration panel from the admin dashboard. Functionality to update API keys and manage usage limits. Provide a testing interface to validate the integration's operation. Changes should be logged and traceable for auditing purposes. | T269 | Design and implement an API configuration panel for OpenAI integration within the admin dashboard. This panel should allow administrators to view and change API settings. Ensure that the design phase is completed within one week to meet project timelines.
[6 empty] | T270 | Develop functionality in the OpenAI API configuration panel to update API keys. This includes fields for entering new keys and saving these updates. Task must be completed and tested within two days after the design phase.
[6 empty] | T271 | Add features to manage usage limits for OpenAI API calls from the configuration panel. This should include options to set limits based on daily, weekly, or monthly usage, and an interface to view current usage statistics. Implementation should be done within three days following the API key update task.
[6 empty] | T272 | Create a testing interface connected to the OpenAI configuration panel to validate the integration's operation. This interface should include simulated API calls and display the outputs to verify connectivity and response accuracy. Complete this within two days of completing the usage limits functionality.
[6 empty] | T273 | Implement logging for all changes made through the OpenAI API configuration panel. This should include storing old and new values of the API keys and usage limits, along with timestamps and administrator identifiers. Ensure logs are immutable and implement this feature within three days of the testing interface completion.
[6 empty] | T274 | Conduct a full security audit on the OpenAI API configuration panel to ensure that data integrity and security standards are maintained. This includes validating data encryption for API keys and proper access controls for modifying settings. Schedule the audit to be completed within one week after all development tasks are finished.
[6 empty] | T275 | Prepare documentation for the OpenAI API configuration panel to assist system administrators in using the new features. Documentation should include user guides on updating API keys, setting usage limits, and navigating the testing interface. This should be ready for review within two days after the security audit.
|  |  | S035 | As a System Administrator, I want to configure settings for the Twilio SMS gateway so that I can manage SMS-based communications efficiently. | Access to Twilio SMS settings through the system admin interface. Options to update Twilio API keys and manage SMS templates. Ability to set thresholds for SMS usage and alerts for potential overages. Ensure that configuration changes are recorded in an audit log. | T276 | Design and implement an admin interface section for Twilio SMS settings, ensuring it is intuitive and accessible from the main admin dashboard. Include forms for viewing and modifying API keys and SMS templates. Estimated completion: 2 weeks.
[6 empty] | T277 | Develop backend API endpoints to handle fetching and updating Twilio SMS settings including API keys and SMS templates. Ensure these endpoints are secured and accessible only to authorized system administrators. Estimated completion: 1 week.
[6 empty] | T278 | Create functionality in the admin interface to set and manage SMS usage thresholds. This includes UI elements for setting threshold values and the backend logic to store and enforce these thresholds. Estimated completion: 1 week.
[6 empty] | T279 | Implement a notification system to alert administrators when SMS usage approaches or exceeds set thresholds. Alerts should be sent via email and visible on the admin dashboard. Estimated completion: 1.5 weeks.
[6 empty] | T280 | Integrate audit logging functionality that records all changes made to the Twilio SMS settings. Each log entry should include the timestamp, administrator user ID, and a description of the change. Estimated completion: 1 week.
[6 empty] | T281 | Conduct a security review of the new Twilio SMS settings interface and related APIs to ensure data protection and compliance with organizational security policies. Estimated completion: 1 week.
[6 empty] | T282 | Prepare and execute a series of tests to verify that the Twilio SMS settings interface functions as expected, including unit tests, integration tests, and user acceptance testing with a focus group of system administrators. Estimated completion: 2 weeks.
[6 empty] | T283 | Develop comprehensive documentation for the Twilio SMS settings management feature, detailing the user interface, features, and guidelines for system administrators. This documentation should be accessible from within the admin dashboard. Estimated completion: 1 week.
|  |  | S036 | As a System Administrator, I want to monitor the health and performance of third-party integrations like OpenAI and Twilio so that I can ensure reliable operation. | Dashboard features to display real-time health status of all integrations. Alerts and notifications for any integration failures or degraded performance. Logs of integration issues and the steps taken to resolve them. Capability to quickly disable an integration in case of failure. | T284 | Design and develop a real-time monitoring dashboard to display the health status of third-party integrations such as OpenAI and Twilio. This dashboard should update automatically and display critical metrics relevant to each service.
[6 empty] | T285 | Implement alert systems within the dashboard to notify system administrators of any integration failures or performance degradations. Define conditions for alerts based on performance thresholds and ensure alerts are actionable and informative.
[6 empty] | T286 | Develop a logging system to record all events related to third-party integration issues. Ensure logs capture detailed information including timestamp, nature of the issue, steps taken to resolve, and the status of the integration after resolution.
[6 empty] | T287 | Create functionality within the dashboard for administrators to quickly disable failing integrations. Ensure that disabling an integration does not affect the overall operation of other systems and that the process is reversible.
[6 empty] | T288 | Conduct testing of the dashboard functionality to ensure accuracy in real-time status reporting, effectiveness of alert notifications, and the ability to log and retrieve integration issues accurately and promptly.
[6 empty] | T289 | Plan and execute a training session for system administrators to familiarize them with the new dashboard and its functionalities. Include guidance on how to interpret the health metrics, respond to alerts, and manage integration failures.
|  |  | S037 | As a System Administrator, I want to manage permissions for different user roles regarding their access to third-party integrations so that I can ensure data security and compliance. | Interface to define and modify role-based access controls for each integration. Functionality to apply changes immediately across the platform. Audit trails for all permission changes. | T290 | Design an intuitive user interface for administrators to define and modify role-based access controls for each third-party integration. Include options for setting permissions by user role. Ensure the design is finalized and reviewed by the project team within 2 weeks.
[6 empty] | T291 | Develop the backend functionality to support dynamic role-based access control settings for third-party integrations. This includes creating APIs to handle CRUD operations on permissions. Aim to complete development and initial testing within 4 weeks.
[6 empty] | T292 | Implement the interface as designed, ensuring administrators can easily navigate through the settings and modify permissions as needed. The interface should be fully integrated into the existing system’s admin dashboard with complete functionality deployment in 3 weeks.
[6 empty] | T293 | Set up a real-time application of changes across the platform, ensuring that any changes to permissions are immediately propagated without system restarts. This should be completed and live within 2 weeks after the interface implementation.
[6 empty] | T294 | Develop an audit trail system that logs all changes to permissions including who made the change, what was changed, and the time of change. Ensure the log is immutable and secure. Schedule for completion and review within 3 weeks.
[6 empty] | T295 | Conduct comprehensive testing of the new role-based access control settings, including user acceptance testing and security auditing, to ensure that the system functions correctly and is secure against unauthorized access. Plan to spend 2 weeks on this phase.
[6 empty] | T296 | Prepare and deliver training sessions for system administrators on how to use the new permission management features. Include documentation on procedures and best practices. Training should be conducted within 1 week after system deployment.
[6 empty] | T297 | Schedule and execute a phased rollout of the new functionality, monitoring the system for any issues and gathering feedback from users for further refinement. Complete the rollout within 1 week.
|  |  | S038 | As a System Administrator, I want to update the documentation for third-party integrations whenever configuration changes occur so that the system documentation remains accurate and helpful. | A section in the admin dashboard to manage documentation. Features to edit, save, and publish the updated documentation directly from the dashboard. Version control for documentation to track changes over time. Notification to relevant users when important changes are made. | T298 | Design a documentation management section within the admin dashboard. Include capabilities for viewing, editing, and organizing documentation files. Estimated completion: 3 days.
[6 empty] | T299 | Implement features in the documentation section to edit and save changes to integration documentation. Ensure that the editor supports both text and multimedia content. Estimated completion: 5 days.
[6 empty] | T300 | Develop a publishing feature that allows updated documentation to be pushed live from the dashboard, following any necessary approval processes. Estimated completion: 4 days.
[6 empty] | T301 | Integrate version control for the documentation to track and manage changes over time. This should include options to revert to previous versions. Estimated completion: 4 days.
[6 empty] | T302 | Set up a notification system to alert relevant users when important changes are made to the documentation. Include customizable settings for notification preferences. Estimated completion: 3 days.
[6 empty] | T303 | Perform comprehensive testing of the new documentation management features, including user acceptance testing with actual system administrators to gather early feedback. Estimated completion: 5 days.
[6 empty] | T304 | Prepare and conduct a training session for system administrators to familiarize them with the new documentation management functionalities. Estimated completion: 2 days.
[6 empty] | T305 | Create detailed user guides and help articles on how to use the new documentation management features effectively, to be included within the system help section. Estimated completion: 3 days.
E008 | Data Backup and Recovery | Implement a robust data backup and recovery plan that system administrators can manage, ensuring data integrity and availability in case of system failures. | S039 | As a System Administrator, I want to configure automated data backups, so that data is regularly saved without manual intervention. | Ability to schedule backup frequency (e.g., hourly, daily, weekly). Confirmation messages post successful backup. Automated backup process logs for auditing. | T306 | Design a user interface for system administrators to schedule automated data backups, including options for setting frequency (hourly, daily, weekly). Ensure the UI is intuitive and accessible within the system admin dashboard. Timeline: 1 week.
[6 empty] | T307 | Develop backend functionality to support setting and modifying backup schedules. This includes creating API endpoints to handle requests for updating backup frequencies. Timeline: 2 weeks.
[6 empty] | T308 | Implement logic to trigger backup processes based on the defined schedules. This should operate seamlessly in the background without affecting system performance. Timeline: 1 week.
[6 empty] | T309 | Create a confirmation system that sends messages to the system administrator post each successful backup. This should include details of the backup and timestamp. Timeline: 1 week.
[6 empty] | T310 | Develop a logging mechanism that records each backup action, including time, scope, and any errors. Ensure logs are secure, immutable, and easily accessible for auditing purposes. Timeline: 1.5 weeks.
[6 empty] | T311 | Integrate the backup scheduling system with the existing system admin dashboard, ensuring stability and security. Timeline: 1 week.
[6 empty] | T312 | Conduct integration testing to verify that the backup system works correctly with different settings and handles failures gracefully. Timeline: 1 week.
[6 empty] | T313 | Prepare documentation for the backup configuration system, detailing how to set schedules, monitor confirmations, and access logs. Timeline: 3 days.
[6 empty] | T314 | Plan and conduct a training session for system administrators on how to use the new backup configuration system. Include practical demonstrations and Q&A sessions. Timeline: 1 week.
|  |  | S040 | As a System Administrator, I want to set up real-time data replication, so that all data is immediately copied to a backup server, ensuring no data loss. | Real-time replication with minimal latency. Failover to backup server in case of primary server failure with seamless transition. Regular status reports on replication health. | T315 | Assess and select replication technology: Review available replication technologies that support real-time data replication. Consider factors like compatibility, security features, support, and performance. Complete this task within 1 week.
[6 empty] | T316 | Develop a replication architecture plan: Design a detailed architecture plan for the real-time data replication process, including primary and backup server configurations, data flow diagrams, and failover mechanisms. This should be completed within 2 weeks.
[6 empty] | T317 | Set up primary and backup servers: Configure the necessary hardware and software on both the primary and backup servers as per the architecture plan. Ensure that both servers are equipped with adequate resources to handle the load. Task to be finished in 2 weeks.
[6 empty] | T318 | Implement replication software: Install and configure the chosen replication software on the primary server. Ensure the setup supports real-time data replication with minimal latency. Complete this task within 1 week.
[6 empty] | T319 | Test the replication setup: Conduct initial tests to ensure that data is being replicated in real-time from the primary to the backup server without significant latency. Check that data integrity is maintained during replication. Task to be completed in 1 week.
[6 empty] | T320 | Develop a failover mechanism: Implement automated scripts or configurations that enable a seamless transition to the backup server during a primary server failure. This includes ensuring that the backup server can fully take over without data loss or service interruption. Complete within 2 weeks.
[6 empty] | T321 | Test failover functionality: Simulate various scenarios of server failures to validate the effectiveness of the failover mechanisms. Adjust configurations as necessary based on test results. Complete testing within 2 weeks.
[6 empty] | T322 | Implement monitoring tools: Set up monitoring tools to provide regular status reports on the health of the replication process. Ensure that alerts are set up for any anomalies or failures in the replication. Complete setup within 1 week.
[6 empty] | T323 | Document the replication process: Create comprehensive documentation on the real-time data replication setup, including step-by-step guides, architecture diagrams, and failover processes. Finish documentation within 1 week.
[6 empty] | T324 | Conduct a training session for the IT team: Organize a training session to educate system administrators and IT staff about managing and troubleshooting the real-time data replication system. Schedule and conduct the training session within 1 week after completing all setups.
|  |  | S041 | As a System Administrator, I want to perform regular recovery tests, so that I can ensure the recovery processes are effective and can be relied upon in emergency scenarios. | Ability to initiate a recovery test without affecting the live environment. Detailed report generation on recovery performance and any issues encountered. Checklist and procedures updated based on test results. | T325 | Design and implement a recovery test simulation module that can be triggered without impacting the live environment. Ensure the module simulates various failure scenarios to validate the effectiveness of the recovery processes. The task should be completed in 4 weeks with weekly progress reviews.
[6 empty] | T326 | Develop a comprehensive reporting system for documenting the performance of each recovery test. This system should automatically generate detailed reports highlighting the duration, actions taken, and any issues encountered during the recovery tests. Target to have a prototype ready for initial review in 3 weeks.
[6 empty] | T327 | Create a dynamic checklist and procedure document that can be updated based on the results and learnings from each recovery test. Implement version control and change logs to track updates over time. Aim to have the initial version ready within 2 weeks from the start of the task, with updates as necessary post each recovery test.
[6 empty] | T328 | Establish a regular testing schedule for performing recovery tests, ideally on a monthly basis. Include preparations for test, execution, review, and feedback phases. Set up reminders and automated scheduling within the system to enforce the testing routine. Task should be operational by the end of the 5th week.
[6 empty] | T329 | Conduct a training session for the system administrators to familiarize them with the recovery test procedures, how to initiate tests, and how to interpret the report data. Plan for a 2-hour training session to be executed after the recovery simulation module goes live.
[6 empty] | T330 | Set up a review process for after each recovery test to evaluate the recovery performance, update procedures, and refine the checklist as needed. This process should be integrated into the testing routine and should be outlined and ready for implementation by the 6th week.
|  |  | S042 | As a System Administrator, I want to implement integrity checks for backups, so that the reliability and usability of backed-up data can be assured. | Automated integrity check after each backup process. Alerts for any integrity issues detected. Log entries for integrity checks for audit purposes. | T331 | Design and implement an automated integrity check system for data backups that executes immediately after each backup process. Set a deadline for the completion of the system design phase within 2 weeks.
[6 empty] | T332 | Develop alert mechanisms that notify system administrators immediately via email and SMS when integrity issues are detected in backup data. Plan to complete this task within 3 weeks.
[6 empty] | T333 | Create detailed log entries for each integrity check performed. These logs should include the date, time, outcome, and any errors or warnings detected during the integrity check. Ensure that the logging system is designed and deployed within 1 week.
[6 empty] | T334 | Conduct a testing phase to validate the effectiveness of the automated integrity checks, ensuring that it correctly identifies and logs issues. Schedule and complete the testing phase within 1 week following the development of the integrity check system.
[6 empty] | T335 | Integrate the new integrity check system with the existing backup infrastructure to ensure seamless operation and minimal disruption. Set a goal to complete the integration process within 2 weeks after the testing phase is successfully completed.
[6 empty] | T336 | Document the entire process and system configurations for the integrity check mechanism, providing clear guidelines and operational procedures for system administrators. Aim to complete the documentation within 1 week after the system integration.
[6 empty] | T337 | Schedule a training session for system administrators to familiarize them with the new integrity check procedures and alert systems. Plan to conduct this training within 1 week after documentation is finalized.
[6 empty] | T338 | Implement monitoring tools to continuously assess the performance of the automated integrity checks and gather feedback from system administrators for potential improvements. Complete the implementation of monitoring tools within 2 weeks post-deployment.
|  |  | S043 | As a System Administrator, I want to use a dashboard to monitor backup and recovery statuses, so that I can easily understand the system's backup health and address issues promptly. | Dashboard displays real-time backup and recovery statuses. Alerts and notifications for failed backups or recoveries. Ability to access historical backup and recovery logs. | T339 | Design a user-friendly dashboard UI that displays real-time backup and recovery statuses. Include key metrics such as the last backup time, next scheduled backup, and the status of the last recovery test. Ensure the design is completed by end of the next sprint.
[6 empty] | T340 | Develop backend services to fetch and aggregate real-time data related to backup and recovery processes from the system database. This includes data fetching mechanisms for the most recent backup status, next backup schedule, and recovery test outcomes. Aim to have a prototype ready for review in two weeks.
[6 empty] | T341 | Implement a notification system within the dashboard that triggers alerts for failed backups or recoveries. Ensure alerts are prominent and provide sufficient information to quickly understand the issue. Include a detailed log view for troubleshooting. Schedule completion in three weeks.
[6 empty] | T342 | Set up secure API endpoints to allow the dashboard to access historical backup and recovery logs. Ensure these endpoints support filtering, sorting, and pagination to handle large volumes of data. Plan for initial API deployment and testing within four weeks.
[6 empty] | T343 | Integrate the front-end dashboard with the backend services using secure, authenticated API calls. Ensure data integrity and security by implementing proper authentication and authorization checks. Target complete integration and testing by the end of the fifth week.
[6 empty] | T344 | Conduct comprehensive end-to-end testing of the dashboard to verify that all components work as expected and meet the acceptance criteria. Include tests for real-time data display, alert functionality, and historical data access. Schedule testing to be completed before the next release cycle.
[6 empty] | T345 | Prepare and deliver a training session for system administrators on how to use the new dashboard. Include instructions on how to interpret the data presented, respond to alerts, and access historical logs. Plan the training session to coincide with the dashboard launch.