## Sheet
Stakeholder | EpicID | EPIC TITLE | EPIC DESCRIPTION | Story ID | Story Title | Story Description | Story Acceptance Criteria | Task ID | Task Description
Developer | E001 | Image Upload and Processing | Develop a function to upload images in Base64 format and analyze their resolution and size, initiating the process for further image processing steps. | S001 | Image Upload Feature | As a Developer, I want to upload images in Base64 format so that I can process them to identify UI elements. | Image upload endpoint accepts Base64 encoded images. Uploaded images are decoded to a usable format for processing. A confirmation is returned upon successful upload and decoding. | T001 | Design and implement an API endpoint to accept image uploads. The endpoint should specifically handle POST requests and accept images encoded in Base64 format.
[8 empty] | T002 | Develop a function to decode Base64 encoded images to a standard image format (e.g., JPEG, PNG). This function should handle errors in encoding gracefully and log any issues encountered during the decoding process.
[8 empty] | T003 | Implement a mechanism within the image upload flow to confirm successful decoding of the image. This should include both server-side confirmations of decoding success and a user-friendly message or signal to the client.
[8 empty] | T004 | Integrate the image decoding function with the API endpoint to ensure that images are automatically decoded after they are uploaded. The integration should be seamless and handle high volumes of requests efficiently.
[8 empty] | T005 | Create unit tests to verify that the API endpoint correctly handles Base64 encoded images, including tests for handling improper formats or corrupted data.
[8 empty] | T006 | Develop logging for the upload and decoding process to capture detailed information about the image data received, any decoding errors, and the system's responses to these events.
[8 empty] | T007 | Set up a system for feedback to the user after an upload attempt. This should include both successful uploads and detailed error messages in cases where the upload or decoding fails.
|  |  |  | S002 | Image Resolution and Size Analysis | As a Developer, I want to analyze the resolution and size of the uploaded images so that I can ensure they meet the required standards for processing. | Function exists to calculate the resolution and size of the image. Resolution and size data is logged and verified against predetermined acceptable parameters. A response is generated that returns the resolution and size analysis. | T008 | Create a Python function `calculate_image_resolution_size` that takes a decoded image as input and computes its resolution (width x height) and file size in bytes.
[8 empty] | T009 | Implement logic within the `calculate_image_resolution_size` function to log the calculated resolution and size data to a file or database for auditing and verification purposes.
[8 empty] | T010 | Define acceptable resolution and size parameters in a configuration file or database that can be easily updated as requirements change.
[8 empty] | T011 | Enhance the `calculate_image_resolution_size` function to verify if the image’s resolution and size meet the predefined acceptable parameters and log the verification result.
[8 empty] | T012 | Develop a response mechanism in the `calculate_image_resolution_size` function that returns a JSON object containing the resolution, size, and verification result (pass or fail based on acceptable parameters).
|  |  |  | S003 | Image Segmentation | As a Developer, I want to segment the uploaded images so that smaller regions can be individually analyzed for specific UI elements. | Ability to segment the image into defined parts. Each segment retains its coordinates relative to the original image. Segments are stored or handled to facilitate further processing. | T013 | Develop a function to accept an uploaded image in Base64 format and decode it into a usable image format, such as PNG or JPEG.
[8 empty] | T014 | Implement an image segmentation algorithm that can divide the decoded image into defined parts as specified in the requirements.
[8 empty] | T015 | Create a mechanism to calculate and retain the coordinates of each image segment relative to the original image, ensuring each segment's position is trackable.
[8 empty] | T016 | Design a data structure or schema to store the segments along with their metadata, including coordinates and segment identifiers, in a way that facilitates easy retrieval and processing.
[8 empty] | T017 | Develop functionality to save the segmented image data either in memory or on disk, depending on the system architecture and requirements, to ensure data persistence during the processing phase.
[8 empty] | T018 | Write unit tests to validate each function of the image segmentation process, including image decoding, segmenting, coordinate tracking, and data storage.
[8 empty] | T019 | Integrate the developed segmentation function into the existing image processing pipeline, ensuring seamless data flow and compatibility with other processing steps.
[8 empty] | T020 | Document the API endpoints or function calls involved in the image segmentation process, including input parameters and expected outputs, to be used by other developers or for future references.
|  |  |  | S004 | Integration with OpenAI API | As a Developer, I want to integrate the image processing system with OpenAI's API so that I can use advanced algorithms to identify UI elements within image segments. | API integration is configured to send image data to OpenAI. The API returns data that indicate whether the desired UI element is present in a segment. Handle the API responses to extract meaningful data for further processing. | T021 | Design and implement a function to configure the integration with OpenAI's API. This function should include parameters for API keys, endpoint URLs, and any necessary headers for authentication.
[8 empty] | T022 | Develop a function to serialize image segment data into the format required by OpenAI's API. Ensure this function can handle various image data structures and convert them into a JSON or other required format for the API call.
[8 empty] | T023 | Create a function to send image data to OpenAI's API. This function should take serialized image data as input, make an HTTP POST request to the API, and handle any network errors or exceptions that may occur during the request.
[8 empty] | T024 | Implement response handling logic to parse the data returned from OpenAI's API. This function should verify that the response contains the necessary information to determine the presence of UI elements and handle any data anomalies or errors in the response.
[8 empty] | T025 | Write a function to extract and process meaningful data from the API's response. It should identify whether the desired UI elements are present in the image segments and prepare this information for further processing.
[8 empty] | T026 | Set up a logging mechanism to track requests sent to OpenAI's API and their responses. This should include information such as request timestamps, response status codes, and any error messages received.
[8 empty] | T027 | Ensure the entire API integration process is encapsulated in a Python class or module, allowing for easy maintenance and scalability. Include methods for configuration, sending requests, and processing responses.
[8 empty] | T028 | Test the API integration thoroughly with unit tests to ensure that the image data is correctly formatted, sent to the API, and that the responses are correctly handled and parsed. Include tests for error handling scenarios.
|  |  |  | S005 | Complete UI Element Construction | As a Developer, I want to handle cases where a UI element is only partially identified in image segments so that I can reconstruct a complete view of the UI element. | Implement logic to detect partial UI elements within the segments. Combine adjacent segments as necessary to form a complete UI element. Validate the completeness of UI elements after reconstruction. | T029 | Design and implement a function to detect partial UI elements within image segments. This function should analyze segments to identify markers or characteristics indicative of an incomplete UI element, and flag these segments for further processing.
[8 empty] | T030 | Develop a function to combine adjacent image segments based on flags from the partial UI detection function. This function should retrieve adjacent segments that potentially contain the continuation of the flagged partial UI elements and merge them to form a complete UI element.
[8 empty] | T031 | Create a validation function to check the integrity and completeness of UI elements after reconstruction. This function should compare the reconstructed UI element against a set of predefined completeness criteria to ensure that the UI element is correctly formed.
[8 empty] | T032 | Integrate the partial UI element detection, combining adjacent segments, and validation functions into the main image processing workflow. Ensure these functions interact seamlessly, with error handling to manage any failures in the detection or combination processes.
[8 empty] | T033 | Write unit tests for each function (partial UI detection, segment combination, and validation) to ensure that they perform as expected under various scenarios. Include tests for edge cases such as very minimal partial elements and multiple adjacent segments needing combination.
[8 empty] | T034 | Document the functions and their integration into the workflow, detailing the inputs, outputs, and expected behavior. This documentation should serve as a guide for future developers and maintainers of the system.
|  |  |  | S006 | Coordinate Calculation | As a Developer, I want to calculate the X, Y coordinates of the identified UI elements so that I can use these coordinates to automate interactions with the UI. | Coordinates of the center of the identified UI element are calculated accurately. Coordinates are mapped correctly to the original image's scale. Coordinates are outputted in a usable format for further processing or interaction. | T035 | Design a function to take as input the image data and metadata about UI elements (location and size). This function should calculate the center coordinates of each UI element based on the provided metadata.
[8 empty] | T036 | Implement a calculation method within the function that accurately determines the center X, Y coordinates of a UI element given its bounding box. Ensure the method adheres to image's pixel scale.
[8 empty] | T037 | Create unit tests to verify that the center coordinates are calculated accurately. Tests should include scenarios with different image resolutions and sizes.
[8 empty] | T038 | Develop a mapping system within the function to translate the calculated coordinates back to the scale of the original image, ensuring they remain accurate and true to the original's dimensions.
[8 empty] | T039 | Add functionality to format the calculated coordinates into a JSON structure, making them ready for output. Ensure the JSON output includes key metadata such as element ID and its original position.
[8 empty] | T040 | Create integration tests to ensure that the coordinate calculation function works correctly within the broader image processing pipeline.
[8 empty] | T041 | Document the function specifying inputs, outputs, and the algorithm used for coordinate calculation. Include examples of input data and expected output.
|  |  |  | S007 | Output Generation | As a Developer, I want to generate outputs for the X, Y coordinates of UI elements so that they can be used to automate tasks. | Output includes X, Y coordinates of all identified UI elements. Outputs are logged or stored in a structured format. Outputs are readily accessible for further use in automation scripts. | T042 | Create a Python function `generate_coordinates_output` that takes a list of dictionaries, where each dictionary contains the X, Y coordinates and identifier of a UI element, and outputs a JSON object containing these coordinates.
[8 empty] | T043 | Implement logging within the `generate_coordinates_output` function to record each step of the data processing, including any failures or errors that occur during the generation of the output.
[8 empty] | T044 | Design a file storage system that saves the output JSON object from the `generate_coordinates_output` function to a structured directory path, ensuring that the output is organized by date and time for easy retrieval.
[8 empty] | T045 | Develop a mechanism for accessing the stored JSON output files through a simple API or function call, allowing other parts of the system or external scripts to retrieve and use the coordinate data as needed.
|  |  |  | S008 | Error Handling for Image Processing | As a Developer, I need robust error handling for the image processing steps to ensure reliability and accuracy in detecting UI elements. | Errors in image upload, processing, or API integration are caught and logged. Appropriate error messages are returned to help in debugging and maintenance. System remains stable and responsive even when encountering errors. | T046 | Develop a function to validate the format of the uploaded Base64 image. The function should check if the image is properly encoded in Base64 and reject any uploads that do not meet this criterion.
[8 empty] | T047 | Implement a try-except block around the image decoding process to catch and log any errors that occur during the decoding of Base64 encoded images. This includes catching exceptions related to incorrect formatting or corrupted data.
[8 empty] | T048 | Create a logging mechanism to record all errors encountered during the image upload, decoding, and API integration processes. This log should include timestamps and error descriptions to aid in debugging.
[8 empty] | T049 | Design error messages that are informative and provide guidance on how to resolve issues encountered during the image processing steps. These messages should be returned to the user or system that initiated the upload.
[8 empty] | T050 | Set up a monitoring system to ensure that the image processing service maintains high availability and responsiveness. Use health checks and performance metrics to monitor the system.
[8 empty] | T051 | Implement retry logic in the function that handles communication with the OpenAI API. This should include mechanisms to attempt re-sending the request a specified number of times before logging an error if all attempts fail.
[8 empty] | T052 | Ensure that the entire system, including image upload, processing, and API integration, is encapsulated in a robust error handling framework that maintains system stability and prevents crashes.
| E002 | Image Segmentation | Implement a feature to segment the uploaded image into smaller parts, maintaining a record of each segment’s position relative to the original image to assist in precise UI element localization. | S009 | Upload and Decode Base64 Image | As a Developer, I want to upload and decode a Base64 image so that I can process it further for UI element identification. | The system allows uploading of Base64 encoded images. The system decodes the Base64 image to its original format. A confirmation is shown once the image is successfully uploaded and decoded. | T053 | Create a function named `upload_base64_image` that accepts a string parameter representing a Base64 encoded image. This function should handle HTTP POST requests to enable the uploading of Base64 encoded images.
[8 empty] | T054 | Implement validation within `upload_base64_image` to verify that the input string is a valid Base64 encoded image. If the validation fails, return a suitable error message.
[8 empty] | T055 | Develop a function named `decode_base64_image` that takes a Base64 encoded string as an input and decodes it into its original image format. Ensure the function can handle different image formats embedded in the Base64 string.
[8 empty] | T056 | Incorporate error handling in `decode_base64_image` to manage and log decoding failures, returning an appropriate error response to the caller.
[8 empty] | T057 | After successful decoding, modify the `upload_base64_image` function to call `decode_base64_image` and pass the uploaded Base64 data for decoding.
[8 empty] | T058 | Create a confirmation message within the `upload_base64_image` function that triggers after the successful upload and decoding of the image. This message should confirm the successful processing of the image.
[8 empty] | T059 | Integrate the image upload and decoding functions with existing backend infrastructure, ensuring that the functions are accessible via the established API endpoints.
[8 empty] | T060 | Write unit tests for both `upload_base64_image` and `decode_base64_image` functions to ensure they handle both typical and edge cases correctly, such as incorrect Base64 strings, large image sizes, and unsupported image formats.
[8 empty] | T061 | Document the API endpoints and function usage in the project's API documentation, detailing the expected inputs, outputs, and error messages for developers' reference.
|  |  |  | S010 | Image Resolution Detection | As a Developer, I want the system to automatically detect and record the resolution of the uploaded image so that I can ensure the image is segmented accurately based on its dimensions. | The system detects the resolution immediately after the image is decoded. The detected resolution is recorded and can be accessed for segmenting the image. The system handles different image resolutions without errors. | T062 | Develop a function to decode the uploaded Base64 image to its original format. The function should accept a Base64 encoded string as input and return the decoded image.
[8 empty] | T063 | Implement a module to detect the resolution of the decoded image. The module should take a decoded image as input and output the resolution details such as width and height in pixels.
[8 empty] | T064 | Create a data storage mechanism to record the detected resolution. Ensure that the resolution data is stored in a format that can be easily accessed for use in image segmentation.
[8 empty] | T065 | Design unit tests to verify that the resolution detection works accurately across images of various resolutions. Include tests to ensure that the module correctly identifies resolution and handles errors without crashing.
[8 empty] | T066 | Integrate the resolution detection module into the existing image upload and processing workflow. Ensure that the module interacts seamlessly with other components, specifically the image segmentation module.
[8 empty] | T067 | Document the API and internal functions related to resolution detection, including input requirements, output format, and error handling procedures.
|  |  |  | S011 | Image Segmentation | As a Developer, I want the system to segment the uploaded image into smaller, manageable parts while keeping track of each segment's position relative to the original image so that I can accurately identify UI elements. | The image is segmented into predefined smaller parts. Each segment’s position relative to the original image is recorded. The system provides visual or data feedback showing the segmentation and positions. | T068 | Design a function `segment_image` that accepts an image in its original format. This function should handle the logic to segment the image into predefined smaller parts based on input parameters such as segment dimensions or number of segments.
[8 empty] | T069 | Implement a method within `segment_image` to calculate and record each segment's position relative to the original image. Ensure this includes capturing coordinates such as top-left corner and dimensions of each segment.
[8 empty] | T070 | Develop a data structure to store the segmented parts along with their positional data. This structure should be accessible for further processing of individual segments.
[8 empty] | T071 | Create a visualization tool within the `segment_image` function to generate an overlay on the original image showing the segmented areas. This tool should be able to visually represent the segmented boundaries and their corresponding labels or identifiers.
[8 empty] | T072 | Incorporate error handling within the `segment_image` function to manage and log errors related to image processing, segmentation faults, or data recording inaccuracies.
[8 empty] | T073 | Write unit tests for the `segment_image` function to test various cases such as different image sizes, formats, and segmentation parameters to ensure robustness and reliability.
[8 empty] | T074 | Document the `segment_image` function detailing its purpose, inputs, outputs, and any side effects. Include examples of usage and expected results.
[8 empty] | T075 | Integrate the `segment_image` function into the main image processing workflow, ensuring that segmented images and their metadata are correctly passed to subsequent processing steps.
|  |  |  | S012 | Partial UI Element Handling | As a Developer, I want the system to handle scenarios where a UI element is only partially present in the segments, by reassembling the necessary segments to form a complete view of the UI element so that accurate UI localization can be achieved. | The system identifies segments containing partial UI elements. Adjacent segments are automatically considered and added if needed to form a complete UI element view. The system updates the UI element's position data based on the newly formed segment. | T076 | Design and implement a function to detect partial UI elements in image segments. The function should scan each segment and use predefined criteria to determine whether a UI element is only partially visible. Input: Image segments; Output: List of segments with partial UI elements.
[8 empty] | T077 | Develop a function to identify and select adjacent segments that need to be considered for forming a complete UI element view. This function should take the list of segments containing partial UI elements and determine potential adjacent segments that could contain the continuation of these elements. Input: List of segments with partial UI elements; Output: List of adjacent segments.
[8 empty] | T078 | Create a function to merge segments. This function should be capable of taking the main segment and its adjacent segments (if any) that are determined to contain parts of the same UI element, and merge them to form a single, reconstructed segment. Input: Main segment and its adjacent segments; Output: Reconstructed segment.
[8 empty] | T079 | Implement a function to update the UI element's position data based on the newly formed segment. After merging, the system needs to calculate the new coordinates of the UI element within the reconstructed segment relative to the original image. Input: Reconstructed segment; Output: Updated position data for the UI element.
[8 empty] | T080 | Integrate the developed functions into the existing image processing pipeline. Ensure that the detection, selection, merging, and updating functions are properly called in sequence. This integration must handle the data flow between functions and maintain the accuracy of the segment information.
[8 empty] | T081 | Develop unit tests for each function to verify their functionality and correctness. Tests should cover various scenarios including edge cases where segments may not perfectly align or when no adjacent segments are found.
[8 empty] | T082 | Document the solution design and development process, focusing on explaining how the functions interact, data flow, and how edge cases are handled. This documentation will assist in future maintenance and scaling of the feature.
|  |  |  | S013 | Coordinate Calculation of UI Element | As a Developer, I want the system to calculate the X, Y coordinates of the center of the identified UI element relative to the original image so that I can use these coordinates to automate interactions with the UI. | Upon identifying a complete UI element, the system calculates the center coordinates. Coordinates are relative to the original image's dimensions. Coordinates are outputted in a clear and accessible format. | T083 | Design a function named 'calculate_center_coordinates' that accepts parameters for the dimensions of the identified UI element and its position relative to the original image. This function calculates the center X and Y coordinates of the UI element.
[8 empty] | T084 | Implement logic within 'calculate_center_coordinates' to ensure that the coordinates calculated are relative to the dimensions of the original image, not just the segment or UI element.
[8 empty] | T085 | Develop a mechanism within the function to output the calculated coordinates in a JSON format. This output should include keys for 'centerX', 'centerY', and 'elementID' to uniquely identify each UI element.
[8 empty] | T086 | Create unit tests for 'calculate_center_coordinates' to verify that the coordinates are accurately calculated for various dimensions and positions of UI elements relative to different original image sizes.
[8 empty] | T087 | Set up error handling within the function to manage and log calculation errors, ensuring the function fails gracefully and provides meaningful error messages.
[8 empty] | T088 | Document the function 'calculate_center_coordinates' clearly, detailing its purpose, inputs, outputs, and any errors it handles. Include examples of input and expected output in the documentation.
|  |  |  | S014 | Output Generation of Coordinates | As a Developer, I want the system to output the calculated X, Y coordinates after processing so that I can use them for further automation tasks. | Coordinates are displayed or stored immediately after calculation. The output format is consistent and parsable for subsequent processes. The system confirms when coordinates have been successfully generated and stored. | T089 | Design the coordinate calculation function that accepts image segment data, processes it to extract or calculate the X, Y coordinates of UI elements, and prepares the data for output.
[8 empty] | T090 | Implement the coordinate calculation function in Python. The function should calculate the central coordinates of identified UI elements relative to the original image and ensure precision in alignment with specified requirements.
[8 empty] | T091 | Develop a data structure to store and manage the output coordinates in a consistent format that includes identifiers for each UI element and its corresponding coordinates.
[8 empty] | T092 | Create a function to serialize the coordinate data into a JSON format which can be parsed easily by subsequent systems or processes. This function should handle data integrity and format consistency.
[8 empty] | T093 | Integrate the coordinate output function with the existing image processing workflow to ensure coordinates are captured immediately after their calculation is completed.
[8 empty] | T094 | Implement an automated verification system to check the integrity and accuracy of the output data against predefined standards and parameters to confirm that the output remains consistent.
[8 empty] | T095 | Develop a logging mechanism to log the successful generation and storage of coordinate data. This log should also capture timestamps, process identifiers, and status messages to aid in debugging and tracking system operations.
[8 empty] | T096 | Setup a notification or confirmation mechanism that is triggered once coordinates have been successfully generated and stored, confirming the completion of the operation to the user or subsequent system processes.
[8 empty] | T097 | Conduct thorough unit tests to ensure that each part of the system from coordinate calculation, data serialization, to output generation meets the acceptance criteria and functions correctly under different scenarios.
[8 empty] | T098 | Document the API and usage of the functions involved in calculating and outputting coordinates, including examples of input data and expected output formats, to assist other developers and stakeholders in understanding and using the system.
| E003 | UI Element Identification | Create functionality using OpenAI API to analyze segments and determine the presence of specified UI elements based on input instructions. | S015 | Image Upload and Base64 Conversion | As a Developer, I want to upload screenshots in Base64 format so that they can be processed to identify UI elements. | The system accepts image uploads in Base64 format. Uploaded images are verified for format integrity. An error message is displayed if the format is incorrect. | T099 | Create a Python function named `upload_base64_image` that accepts a Base64 encoded string as an input parameter. This function should be capable of handling POST requests if implemented in a web context.
[8 empty] | T100 | Implement checks within the `upload_base64_image` function to verify that the input string is a valid Base64 encoded image. Use Python's base64 library to attempt decoding the string.
[8 empty] | T101 | If the Base64 string is invalid (i.e., it does not decode properly or does not represent an image file), the function should return an appropriate error message in a JSON format, stating that the format is incorrect. Ensure the error message is clear and understandable.
[8 empty] | T102 | Upon successful decoding of the Base64 string, convert it into an image file format (e.g., JPEG, PNG) and temporarily store it in memory or a secure temporary storage depending on system requirements.
[8 empty] | T103 | Create unit tests for `upload_base64_image` to ensure the function correctly accepts valid Base64 strings, rejects invalid strings, and returns the correct error messages. Use a Python testing framework like pytest for this purpose.
[8 empty] | T104 | Document the `upload_base64_image` function including details on input parameters, output format, and any exceptions handled. This documentation should be accessible to other developers in the team via a shared repository or documentation system.
|  |  |  | S016 | Image Resolution Detection | As a Developer, I want the system to automatically determine the resolution of uploaded images so that accurate image processing can be performed. | Image resolution is determined upon upload. Correct resolution parameters are stored for use in processing. System handles varying image resolutions without errors. | T105 | Create a function to parse and extract image data from uploaded Base64 encoded images, ensuring that the system can handle various image formats such as JPG, PNG, and BMP.
[8 empty] | T106 | Develop a module to analyze the resolution of the extracted image data, calculating dimensions such as width and height in pixels.
[8 empty] | T107 | Implement a function to store the determined resolution parameters (width, height) in a structured format (e.g., JSON) that can be accessed by other parts of the system for further processing.
[8 empty] | T108 | Design and integrate a method to handle different image resolutions by adjusting processing parameters dynamically based on the resolution data.
[8 empty] | T109 | Create unit tests to verify that the image resolution detection handles various image resolutions correctly without errors and stores the resolution data accurately.
[8 empty] | T110 | Set up error handling within the image resolution determination process to manage and log errors such as unsupported image formats or corrupt image data.
|  |  |  | S017 | Image Segmentation | As a Developer, I want the system to segment uploaded images so that detailed analysis on smaller sections can be conducted to identify UI elements. | Images are segmented into smaller parts post-upload. Each segment's relative position to the original image is tracked. Segmentation errors must be less than 5%. | T111 | Design a function to accept an uploaded image in a supported format, such as PNG or JPEG, and ensure compatibility for Base64 encoded images.
[8 empty] | T112 | Implement a function to decode Base64 encoded images to their native format prior to processing to ensure integrity and usability of the image data.
[8 empty] | T113 | Develop an image segmentation algorithm that can divide an image into smaller parts based on predefined sizes or resolution criteria.
[8 empty] | T114 | Create a data structure to store metadata for each image segment, including its relative position to the original image, ensuring that each segment can be individually referenced.
[8 empty] | T115 | Implement error handling within the segmentation function to catch and log any issues during the segmentation process, with a special focus on maintaining error rates below 5% as per the acceptance criteria.
[8 empty] | T116 | Write unit tests to validate that the image segmentation function correctly divides images into segments and accurately tracks each segment's relative position to the original image.
[8 empty] | T117 | Integrate the segmentation function into the existing image processing pipeline, ensuring that segmented images are queued for further analysis or stored as required.
[8 empty] | T118 | Document the functionality, parameters, and outputs of the segmentation function, ensuring clarity for future maintenance or integration efforts.
|  |  |  | S018 | Integration with OpenAI for Image Analysis | As a Developer, I want to integrate with the OpenAI API to analyze image segments to determine the presence of specified UI elements based on input instructions. | Successful API call to OpenAI with image segment data. API responses are received and correctly interpreted. System retries API call upon failure up to three times. | T119 | Develop a function to encode image data into the format required by OpenAI API. This includes preparing image segments, ensuring they are in the correct format, and encoding them as needed for API compatibility.
[8 empty] | T120 | Implement an API integration module that manages the communication between the system and OpenAI's API. This module should handle constructing the request, sending it to the API, and receiving the response.
[8 empty] | T121 | Ensure that the API integration module includes error handling that detects communication or processing failures and automatically retries the request up to three times.
[8 empty] | T122 | Create a function to parse and interpret the response from the OpenAI API. This function should be able to determine if the response indicates the presence of a UI element.
[8 empty] | T123 | Integrate the OpenAI API response interpretation with the system's existing data structures, updating the system's state with the new information obtained from the API response.
[8 empty] | T124 | Set up logging for all API interactions to ensure that requests, successful responses, and errors are adequately recorded for debugging and auditing purposes.
[8 empty] | T125 | Develop unit tests for each function related to the OpenAI API integration to verify that each part functions correctly individually and in combination with the other system components.
|  |  |  | S019 | Partial UI Element Handling | As a Developer, I want the system to handle cases where the UI element is only partially present in the segments and reconstruct the complete UI element. | The system identifies partial UI elements. Adjacent segments are incorporated to form a complete UI element view. Reconstructed UI elements are accurately represented. | T126 | Develop a function named `detect_partial_ui_elements` that scans image segments to identify and flag the segments containing partial UI elements. The function should accept an array of image segments as input and return a list of segment identifiers that contain partial UI elements.
[8 empty] | T127 | Create a function called `identify_adjacent_segments` that takes as input the list of segment identifiers containing partial UI elements and the full array of image segments. It should return a list of groups of adjacent segments that need to be merged to form complete UI elements.
[8 empty] | T128 | Implement a function named `merge_segments` that accepts a list of groups of adjacent image segments (from the output of `identify_adjacent_segments`) and merges them into single segments. This function should return a new list of image segments where each segment represents a complete UI element.
[8 empty] | T129 | Develop a validation module named `validate_reconstructed_elements` that takes the merged image segments from `merge_segments` and checks each against predefined criteria to ensure they accurately represent the intended UI elements. This function should return a list of validated segments and a report of any discrepancies.
[8 empty] | T130 | Integrate `detect_partial_ui_elements`, `identify_adjacent_segments`, `merge_segments`, and `validate_reconstructed_elements` into a main processing pipeline function called `handle_partial_ui_elements` which coordinates the flow from detection to validation. The function should handle all inputs and outputs internally and log all significant events and results.
|  |  |  | S020 | Coordinate Calculation | As a Developer, I want the system to calculate and return the X, Y coordinates of the center of the identified UI element so that I can use these coordinates for further processing. | Coordinates are calculated with accuracy up to the nearest pixel. Calculated coordinates correctly represent the center of the UI element. Coordinates are output in a standard format accessible for further use. | T131 | Develop a function to extract the center coordinates of a UI element from an image segment. This function should take image segment data as input and output the XY coordinates of the center of the identified UI element.
[8 empty] | T132 | Implement pixel-level precision in the coordinate extraction function to ensure that the output coordinates are accurate to the nearest pixel.
[8 empty] | T133 | Create a validation module to compare calculated coordinates against the actual center of the UI element in the segment, ensuring that the coordinates correctly represent the center.
[8 empty] | T134 | Develop a function to format the coordinates into a JSON output. This function should ensure that the coordinates data structure is consistent and conforms to the defined standard for further use.
[8 empty] | T135 | Write unit tests for the coordinate calculation function to verify that the coordinates are accurately calculated and meet the precision requirements.
[8 empty] | T136 | Write integration tests to check the data flow from the image segment analysis to the coordinate output, ensuring all components work seamlessly together.
[8 empty] | T137 | Document the API of the coordinate calculation module, detailing input requirements, output format, and any dependencies or exceptions.
[8 empty] | T138 | Implement error handling within the coordinate calculation function to manage any potential errors in image analysis or data formatting, with appropriate logging for troubleshooting.
|  |  |  | S021 | Bounding Box and Tagging | As a Developer, I want the system to automatically generate a bounding box around identified UI elements and tag them for easy reference. | Bounding boxes are accurately drawn around identified UI elements. UI elements are tagged with a unique identifier. Tags and boxes are visible and correct on review. | T139 | Design a function 'draw_bounding_box' that accepts image data and coordinates of identified UI elements. This function should apply bounding boxes around these elements and return modified image data with boxes drawn.
[8 empty] | T140 | Implement a tagging system within the 'draw_bounding_box' function. Each UI element within the bounding box should receive a unique identifier tag. Ensure tags are associated with the corresponding UI element data.
[8 empty] | T141 | Create a verification procedure to ensure bounding boxes and tags align correctly with the identified UI elements within the image. This should include visual confirmation and data integrity checks against the input coordinates.
[8 empty] | T142 | Develop a user interface or a visualization tool that allows developers to review and confirm that bounding boxes and tags are correctly applied and visible on the image. This tool should allow zooming and panning for detailed inspection.
[8 empty] | T143 | Write unit tests for the 'draw_bounding_box' function to check the accuracy of bounding boxes and the uniqueness and visibility of tags. Tests should cover various scenarios including edge cases with multiple overlapping UI elements.
| E004 | Coordinate Calculation and Output | Calculate the X, Y coordinates of the UI element’s center from the identified image segment and output these coordinates. | S022 | Image Segmentation | As a Developer, I want the software to segment the uploaded Base64 image into smaller, manageable parts while keeping track of their positions in relation to the original image, so that each segment can be individually analyzed for the presence of UI elements. | Function must accept Base64 encoded image as input. Image is segmented into defined sizes without losing the reference to the original image. The output must include metadata about each segment's original position within the image. | T144 | Design a Python function `upload_base64_image` that accepts a Base64 encoded image string as its parameter. This function should validate the format of the Base64 string to ensure it encodes a valid image file.
[8 empty] | T145 | Implement decoding functionality within the `upload_base64_image` function to convert the Base64 string into an image object. Use libraries such as PIL (Pillow) to handle the decoding.
[8 empty] | T146 | Create a utility function `segment_image` which takes an image object and segmentation parameters (e.g., segment size or number of segments) as inputs. This function should divide the image into segments based on the provided parameters without altering the original dimensions of the image.
[8 empty] | T147 | Implement a method within `segment_image` to store metadata for each segment. This metadata should include information about each segment's position relative to the original image (e.g., top-left corner coordinates, width, and height of the segment).
[8 empty] | T148 | Develop a data structure, preferably a list of dictionaries, where each dictionary contains the segmented image data along with its metadata. This structure will facilitate processing and accessing segments based on their metadata.
[8 empty] | T149 | Ensure that `segment_image` returns the list of segmented images along with their metadata in a structured format, making it easy to handle in subsequent processing steps.
[8 empty] | T150 | Write unit tests for `upload_base64_image` to check that it correctly rejects invalid Base64 strings, decodes valid strings to the correct image format, and handles different image formats (e.g., JPG, PNG).
[8 empty] | T151 | Write unit tests for `segment_image` to ensure it accurately segments images according to specified parameters, retains the original image's dimensions, and correctly generates and associates metadata with each image segment.
[8 empty] | T152 | Document the functions using docstrings and comments to explain the purpose, inputs, outputs, and any exceptions that can be raised during the execution of these functions.
|  |  |  | S023 | Element Identification within Segments | As a Developer, I want the system to analyze each image segment to detect if the specified UI element is present using the OpenAI API, so that I can determine whether further processing is required on the segment. | Each segment must be sent to the OpenAI API for element detection. The system should log and handle API responses indicating the presence or absence of the UI element. Partial detections should be flagged for further processing. | T153 | Develop a function to segment an image into manageable parts. The function should accept a Base64 encoded image as input, decode it, and segment it into predefined sizes. Ensure each segment retains metadata about its position relative to the original image. Output must include metadata about each segment's original position within the image.
[8 empty] | T154 | Implement a function to encode each image segment into Base64 format suitable for API transmission. This function must take an image segment as input and return a Base64 encoded string.
[8 empty] | T155 | Develop an API integration module to send each Base64 encoded image segment to the OpenAI API. The module should handle HTTP requests, including setting appropriate headers and managing payload. Capture and log the API's response for further processing.
[8 empty] | T156 | Create a logging mechanism to record each API request and response. Log details should include timestamp, segment identifier, API response status, and any error messages received. This will assist in debugging and maintaining the system.
[8 empty] | T157 | Design and implement a function to analyze API responses to determine the presence or absence of the specified UI elements within each segment. The function should flag segments with partial UI elements for further processing. Store the results in a structured format such as JSON, including segment identifiers and detection results.
[8 empty] | T158 | Implement error handling for API interactions to manage scenarios such as timeouts, rate limits, and unexpected response formats. The system should retry the API call up to three times in case of failure before logging an error and moving to the next segment.
[8 empty] | T159 | Develop a user interface or command-line interface to display or log the progress of image processing, showing details like total segments processed, number of segments with detected UI elements, and any errors encountered.
[8 empty] | T160 | Write unit tests for each component of the system, including image segmentation, API integration, response analysis, and error handling. Tests should verify that each component functions correctly independently and when integrated.
[8 empty] | T161 | Set up a continuous integration/continuous deployment (CI/CD) pipeline to automate the testing and deployment of the codebase. This pipeline should run the unit tests and report any failures before deployment.
|  |  |  | S024 | Handling Partial Elements | As a Developer, I want the system to intelligently handle cases where the UI element is only partially detected in an image segment, by combining adjacent segments to form a complete view of the UI element, ensuring accurate coordinate calculation. | System identifies and flags segments with partial UI elements. Adjacent segments are automatically analyzed and merged if needed to form a complete UI element. The merged segment must correctly represent the full UI element as intended. | T162 | Develop a function to identify and flag image segments that contain partial UI elements. This function will analyze each segment's characteristics and compare against expected UI element patterns to determine if the segment contains a partial element.
[8 empty] | T163 | Create a function to analyze adjacent segments once a partial UI element is flagged. This function should retrieve neighboring segments and use pattern matching algorithms to check if these segments, when combined with the flagged segment, form a complete UI element.
[8 empty] | T164 | Implement a merging algorithm to combine identified adjacent segments with the original partial UI element segment. Ensure that the merging process maintains image quality and alignment, resulting in a single cohesive image segment that correctly represents the full UI element.
[8 empty] | T165 | Incorporate error handling within the functions to manage scenarios where merging does not result in a correct UI element representation. This includes logging errors, providing informative error messages, and reverting to the best possible state before the error occurred.
[8 empty] | T166 | Design unit tests for each function to validate the correct identification of partial UI elements, the accurate analysis of adjacent segments, and the successful merging of image segments. Test cases should cover various scenarios including edge cases where segments might not align perfectly.
[8 empty] | T167 | Integrate these functions into the existing image processing workflow, ensuring that they are triggered during the appropriate processing stage and that the output is passed to subsequent processing steps, such as coordinate calculation.
|  |  |  | S025 | Calculate Center Coordinates | As a Developer, I want the system to calculate the X, Y coordinates of the center of the identified UI element relative to the original image, so that these can be used to guide automated interactions. | Coordinates are calculated only after a full UI element is identified. Calculation conforms to the geometrical center of the UI element within the segment. Coordinates must be relative to the entire original image, not just the segment. | T168 | Develop a function to verify the completeness of a UI element in an image segment before proceeding with coordinate calculation. The function should accept the image segment as input and return a boolean indicating whether the UI element is fully identified.
[8 empty] | T169 | Create a function to calculate the geometric center of the UI element within an image segment. The function should accept the coordinates of the UI element's boundaries as input and return the X, Y coordinates of the center.
[8 empty] | T170 | Implement a function to convert local segment coordinates to coordinates relative to the entire original image. This function should take the segment's relative position and the center coordinates as input and output global coordinates.
[8 empty] | T171 | Integrate the functions into the main workflow where the system first checks if a UI element is fully identified, then calculates the local center, and finally converts these to global coordinates relevant to the original image.
[8 empty] | T172 | Set up unit tests to verify that the coordinate calculation only occurs after a UI element is fully identified, ensuring compliance with the specified acceptance criteria.
[8 empty] | T173 | Create logging for each step of the coordinate calculation process to assist with debugging and ensure values are being correctly calculated and transformed.
|  |  |  | S026 | Output Generation | As a Developer, I want the system to output the calculated X, Y coordinates in a standard format, so that they can be easily integrated into other parts of the system or workflow. | Output is in a JSON format containing the coordinates. Coordinates should be clearly labeled and include reference to the original UI element's identification. The output must be logged or stored as per the system's specifications. | T174 | Design a JSON schema for outputting X, Y coordinates. The schema should include fields for coordinates, labels for UI elements, and metadata about the image segment from which the coordinates were derived.
[8 empty] | T175 | Implement a function in Python to generate a JSON object based on the designed schema. This function takes the calculated coordinates and the label of the UI element as inputs and outputs a JSON object.
[8 empty] | T176 | Ensure the JSON output function includes error handling to manage cases where input data might be missing or malformed. Provide meaningful error messages to aid in debugging.
[8 empty] | T177 | Develop unit tests to validate the JSON output function. Tests should check for correctness of the output format, adherence to the JSON schema, and proper handling of edge cases and error scenarios.
[8 empty] | T178 | Set up a local or cloud-based storage system to log or store the generated JSON files. Ensure the system is secure and has enough capacity to handle the expected data load.
[8 empty] | T179 | Create a logging mechanism to record the creation, modification, and access of the JSON files. Include timestamps and user or system identifiers to provide an audit trail.
[8 empty] | T180 | Integrate the JSON output functionality with the existing image processing pipeline. Ensure that the coordinates are captured and outputted in real-time as the image processing tasks are completed.
[8 empty] | T181 | Document the JSON output process, including descriptions of the schema, function usage, and integration steps. Provide examples of output JSON files for reference.
| E005 | Bounding and Tagging of UI Elements | Develop functions to draw bounding boxes around identified UI elements and tag them for easy reference. | S027 | Upload Image Functionality | As a Developer, I want the ability to upload a screenshot in Base64 format so that the system can process the image for UI element identification. | The system accepts Base64 encoded image uploads. The upload triggers the image processing workflow. A confirmation message is displayed upon successful upload. | T182 | Design and implement a Python function named 'upload_base64_image' that accepts a single string parameter representing an image in Base64 format. The function should verify the format of the Base64 string and raise an error if the format is invalid.
[8 empty] | T183 | Enhance the 'upload_base64_image' function to decode the Base64 string into its original binary format for image processing. Use appropriate libraries such as 'base64' in Python to handle the decoding process.
[8 empty] | T184 | Implement checks within the 'upload_base64_image' function to ensure that the decoded image is of a supported file type (e.g., JPEG, PNG) and log an error message if the file type is unsupported.
[8 empty] | T185 | Create a mechanism within the 'upload_base64_image' function to trigger subsequent image processing workflows once the image has been successfully decoded. This could involve calling another function or sending a message/event to a processing system.
[8 empty] | T186 | Develop a user-friendly confirmation message within the 'upload_base64_image' function that informs the user of the successful upload and decoding of the image. This message should be logged and returned by the function.
[8 empty] | T187 | Write unit tests for the 'upload_base64_image' function to ensure it handles various scenarios such as correct and incorrect Base64 strings, supported and unsupported image formats, and successful triggering of the image processing workflow.
[8 empty] | T188 | Document the 'upload_base64_image' function detailing its purpose, inputs, outputs, and any exceptions it might raise. Include examples of usage and expected behavior in different scenarios.
|  |  |  | S028 | Image Resolution Detection | As a Developer, I want the system to automatically determine the resolution of uploaded images so that the image can be accurately processed for UI element segmentation. | The system calculates and logs the resolution of each uploaded image. Resolution data is used to enhance the accuracy of the segmentation process. Resolution detection must complete within 2 seconds of image upload. | T189 | Develop a function `calculate_image_resolution` in Python to compute the resolution of an uploaded image. The function should accept an image file as input and return its resolution (width x height).
[8 empty] | T190 | Implement logging within the `calculate_image_resolution` function to record each image's resolution details. Use Python's logging library to log the resolution of each processed image.
[8 empty] | T191 | Create a data structure or dictionary to store resolution data for each uploaded image. This data will be used to adjust segmentation parameters dynamically based on image resolution.
[8 empty] | T192 | Integrate the `calculate_image_resolution` function within the image upload process to ensure that resolution calculation is triggered immediately after the image is uploaded and decoded.
[8 empty] | T193 | Ensure that the resolution calculation process completes within 2 seconds of image upload. Optimize the function using efficient image processing libraries like PIL or OpenCV in Python.
[8 empty] | T194 | Set up unit tests to verify that the `calculate_image_resolution` function correctly calculates and logs the resolution for a variety of image formats and sizes. Use Python's unittest framework for this purpose.
[8 empty] | T195 | Document the process and function details for the `calculate_image_resolution`, including its inputs, outputs, and any dependencies or libraries used. This documentation should be added to the project's repository for future reference.
|  |  |  | S029 | Image Segmentation | As a Developer, I want the system to segment the uploaded image into smaller parts so that each segment can be individually analyzed for UI element presence. | The image is divided into segments without loss of data on their original positions. Each segment is uniquely identifiable and trackable. Segmentation process must handle images of varying resolutions. | T196 | Develop a function to upload an image in Base64 format. The function should validate the format, decode the image, and prepare it for segmentation.
[8 empty] | T197 | Create a function to divide the decoded image into segments based on predetermined or dynamic segment sizes. This function must ensure that no data is lost during the segmentation and retain metadata about each segment's original position.
[8 empty] | T198 | Implement unique identifiers for each image segment. These identifiers should be attached to the segment metadata to ensure trackability throughout the processing pipeline.
[8 empty] | T199 | Design and implement a function to dynamically adjust the segmentation process based on the resolution of the uploaded image. This function should be capable of handling different image resolutions and adjust segment sizes accordingly to maintain consistent analysis quality.
[8 empty] | T200 | Create a robust error handling mechanism within the segmentation function to manage and log errors related to image resolution variations and segmentation faults. This should ensure system stability and provide meaningful error information for troubleshooting.
|  |  |  | S030 | UI Element Identification | As a Developer, I want the system to identify specific UI elements in image segments based on provided instructions so that relevant interactions can be automated. | The system uses the OpenAI API to analyze segments and recognize UI elements. UI elements are identified according to a pre-defined set of criteria. The system handles cases where UI elements are partially present across multiple segments. | T201 | Develop a function to interface with the OpenAI API that accepts image segments as input and returns analysis results. The function should handle API authentication, request formatting, and response parsing.
[8 empty] | T202 | Implement logic within the function to verify the integrity and format of the image segment before sending it to the OpenAI API to ensure compliance with API requirements.
[8 empty] | T203 | Create a set of predefined criteria for UI element identification that can be configured and modified as needed. This should include parameters like size, shape, color, and other relevant attributes for UI elements.
[8 empty] | T204 | Integrate error handling within the OpenAI API interaction function to manage and log errors such as connection issues, API limits exceeded, and unexpected response formats.
[8 empty] | T205 | Design a system to handle cases where UI elements are partially present in segments. This includes logic to detect partial elements and initiate a process to retrieve adjacent segments for a potential match.
[8 empty] | T206 | Build a function to analyze combined segments from adjacent areas when a partial UI element is detected. This function should re-analyze the broader image area to confirm the presence of the UI element.
[8 empty] | T207 | Implement a testing framework to simulate various scenarios where UI elements are partially present across segments to ensure the system handles these cases correctly.
[8 empty] | T208 | Ensure that the data flow between the segment handling logic and the OpenAI API interaction is seamless and efficient to prevent data loss and ensure timely processing.
[8 empty] | T209 | Develop unit tests for each component of the UI element identification process to verify individual functionality and interactions under controlled conditions.
[8 empty] | T210 | Document the configurations and operational details of the UI element identification process to assist in maintenance and future enhancements.
|  |  |  | S031 | Bounding Box Drawing | As a Developer, I want the system to draw bounding boxes around identified UI elements so that these elements are visually delineated for further processing. | Bounding boxes accurately encompass the identified UI elements. Boxes are drawn on the image in a way that does not obscure the UI element. The system retains the coordinates of the original UI element within the bounding box. | T211 | Design a function that accepts an image (as a path or buffer) and a list of coordinates representing the locations of identified UI elements. This function should output an image with bounding boxes drawn around these elements.
[8 empty] | T212 | Implement a function to calculate the coordinates for each corner of the bounding box based on the center coordinates and size of the UI elements, ensuring the box accurately encompasses the UI element.
[8 empty] | T213 | Develop logic within the bounding box function to adjust line thickness and color, ensuring the bounding box is visible but does not obscure the underlying UI element.
[8 empty] | T214 | Create a functionality in the bounding box drawing function to annotate the image with the original coordinates of each UI element, ensuring these coordinates are retained and displayed near the bounding box for reference.
[8 empty] | T215 | Integrate the bounding box function into the existing image processing pipeline, ensuring that it receives the correct inputs from the UI element identification module.
[8 empty] | T216 | Conduct unit testing on the bounding box function to verify that bounding boxes are accurately placed around UI elements, are visible, and do not obscure the UI element.
[8 empty] | T217 | Set up error handling within the bounding box function to manage and log errors related to image processing and coordinate calculation, ensuring the system remains stable and responsive.
|  |  |  | S032 | Tagging UI Elements | As a Developer, I want the ability to tag identified UI elements with text labels so that they can be easily referenced in further automation scripts. | Each bounding box can be tagged with a user-defined text label. Tags are clearly visible and do not overlap with other UI elements. The tagging system allows for easy modifications if necessary. | T218 | Design a user interface or a function parameter that allows users to input a text label for each UI element identified. This input should support customization allowing the user to specify the label for each bounding box identified in the image.
[8 empty] | T219 | Develop a function to add text labels to the bounding boxes around identified UI elements. Ensure that the text labels are added within or adjacent to the bounding box without overlapping the UI element itself in the image. This function should take the coordinates of the bounding box and the user-defined label as inputs.
[8 empty] | T220 | Implement a rendering method that ensures text visibility against various backgrounds. This could involve text shadowing, contrasting text color, or an opaque text background to enhance readability over differing image backgrounds.
[8 empty] | T221 | Create functionality within the tagging system that allows users to modify the text labels after they have been placed. This could involve selecting an existing label and providing a new text input to update it.
[8 empty] | T222 | Incorporate a verification step to ensure that tags do not overlap with other UI elements. This task involves calculating the spatial relationship between the bounding box of a new tag and all existing tags to prevent visual overlap.
[8 empty] | T223 | Develop a unit test to verify that tags can be added, displayed without overlap, and modified. This test should cover various scenarios including edge cases where bounding boxes are near the edges of the image or close to each other.
|  |  |  | S033 | Coordinate Calculation | As a Developer, I want the system to calculate and output the X, Y coordinates of the center of the identified UI element so that I can use these coordinates for automation tasks. | Coordinates are calculated relative to the original image dimensions. The output is accurate and matches the visual center of the UI element within the bounding box. Coordinates are logged and can be retrieved for automation purposes. | T224 | Design a function to calculate the center X, Y coordinates of an identified UI element within a bounding box. This function should take the bounding box dimensions and position as input and compute the geometric center of the box relative to the original image dimensions.
[8 empty] | T225 | Develop the function such that the output matches the visual center of the UI element within the bounding box, confirming alignment with the UI element's visual representation. This should include precise calculation to avoid rounding errors and other inaccuracies.
[8 empty] | T226 | Implement logging within the coordinate calculation function to record the calculated coordinates. This log should store details such as the image identifier, timestamp of the calculation, and the computed coordinates to maintain a traceable record for auditing and debugging purposes.
[8 empty] | T227 | Create an output format for the coordinates that is consistent and standardized, possibly in JSON format. This output should include labels for each coordinate and reference to the original UI element's identification to ensure clarity and usability in subsequent automation tasks.
[8 empty] | T228 | Develop a testing suite for the coordinate calculation function that verifies both the accuracy of the output and the performance of the function under different conditions (e.g., varying image sizes, resolutions, and UI element positions).
[8 empty] | T229 | Integrate the coordinate calculation function into the broader system where UI elements are detected and bounding boxes are drawn, ensuring that the function is called with the correct inputs once a UI element has been identified and bounded.
[8 empty] | T230 | Create documentation for the coordinate calculation function that includes usage examples, parameter descriptions, and information on the output format, to assist other developers and stakeholders in understanding and integrating the function in their workflows.
|  |  |  | S034 | Output Generation | As a Developer, I want the system to output the coordinates of identified UI elements so that I can use this data to automate interactions with UIs. | Output includes coordinates in a standardized format. Output is generated within 3 seconds after UI element identification. Output can be saved locally or passed to other modules for immediate use. | T231 | Design a function to calculate the coordinates of identified UI elements based on input data from the image processing module. Ensure that the function adheres to a standardized format (e.g., JSON) for coordinates output.
[8 empty] | T232 | Implement a time constraint mechanism within the function to ensure that the coordinates calculation and output generation does not exceed 3 seconds from the point of UI element identification.
[8 empty] | T233 | Develop functionality to save the output containing coordinates into a local file system or pass them as a structured JSON object to other modules for further processing. Include file handling or API integration capabilities.
[8 empty] | T234 | Create unit tests to verify that the output format of the coordinates meets the predefined standard format and that the data handling adheres to system specifications. Ensure tests cover file and data integrity.
[8 empty] | T235 | Set up logging and monitoring to trace the execution time from UI element identification to output generation. Alerts or logs should be in place to report if the process exceeds the allowed time frame.
[8 empty] | T236 | Ensure data security and integrity when passing the output coordinates to other modules or when saving them locally. Implement checks to prevent data corruption or unauthorized access.
| E006 | Error Handling for Partial UI Elements | Implement error handling to manage scenarios where UI elements are only partially detected, including logic to combine adjacent segments to form a complete UI element view. | S035 | Detect Partial UI Elements | As a Developer, I want the system to detect when a UI element is only partially visible in an image segment, so that I can ensure full element identification for accurate interaction. | System identifies segments containing partial UI elements correctly. System flags these segments for further processing. | T237 | Develop a function to analyze image segments and detect partial UI elements. The function should take image data as input and return a list of segments where UI elements are partially detected.
[8 empty] | T238 | Implement a mechanism within the image processing function to flag segments containing partial UI elements. This should include tagging these segments in the system's data structure for easy identification.
[8 empty] | T239 | Create unit tests to verify that the function for detecting partial UI elements correctly identifies and flags segments. These tests should cover various scenarios, including cases with clear, ambiguous, and no partial UI elements.
[8 empty] | T240 | Integrate the partial UI element detection function into the existing image processing pipeline. Ensure that it interacts seamlessly with other components like image upload and segmentation.
[8 empty] | T241 | Document the functionality for detecting and flagging partial UI elements. Include usage examples, input and output specifications, and integration details with the image processing system.
|  |  |  | S036 | Combine Adjacent Image Segments | As a Developer, I want the system to automatically combine adjacent segments when a partial UI element is detected, so that a complete view of the UI element can be formed. | Adjacent segments are identified and combined to form a complete UI element. The combined segment accurately represents the full UI element. | T242 | Design and implement a function `identify_adjacent_segments` that takes segment data (IDs, coordinates) and a detection flag indicating partial UI elements. The function should output a list of adjacent segment IDs that need to be considered for combination.
[8 empty] | T243 | Create a function `combine_segments` that inputs a list of segment IDs and their corresponding image data. It should merge these segments into one unified segment. The output will be the combined image data and its new boundaries.
[8 empty] | T244 | Develop a function `validate_combined_segment` to check if the newly formed segment from `combine_segments` function accurately represents a complete UI element. This involves comparing the combined segment against predefined UI element shapes or models.
[8 empty] | T245 | Integrate `identify_adjacent_segments` and `combine_segments` functions within the existing image processing workflow where partial UI elements are detected. Ensure that this integration is seamless and does not interrupt the flow.
[8 empty] | T246 | Implement error handling within the `identify_adjacent_segments` and `combine_segments` functions to manage and log errors such as non-existent segment IDs, failure in merging processes, and incorrect segment data formats.
[8 empty] | T247 | Write unit tests for `identify_adjacent_segments` and `combine_segments` functions to ensure they handle all edge cases, such as no adjacent segments found, multiple adjacent segment combinations, and segments that do not need combining.
[8 empty] | T248 | Document the functionality, inputs, outputs, and expected behaviors of `identify_adjacent_segments` and `combine_segments` functions to aid in maintenance and future enhancements.
|  |  |  | S037 | Calculate Coordinates of Combined Segments | As a Developer, I want the system to calculate the X, Y coordinates of the center of the combined segment, so that the exact location of the UI element can be used for further processing. | Coordinates are calculated accurately relative to the original image. Coordinates reflect the center of the newly formed UI element. | T249 | Design and implement a function to compute the centroid coordinates of a combined image segment. This function should take as inputs the dimensions and pixel data of the segment and return the X, Y coordinates of the center.
[8 empty] | T250 | Create a coordinate transformation function to map local coordinates (relative to the combined segment) back to the global coordinates system of the original image. Inputs will be the local coordinates and metadata about the segment's position in the original image, with outputs being the transformed global coordinates.
[8 empty] | T251 | Develop a unit test to validate the accuracy of the centroid computation function. Ensure it handles various shapes and sizes of image segments correctly by comparing the function output with pre-calculated expected values.
[8 empty] | T252 | Develop a unit test to ensure the coordinate transformation function correctly maps local segment coordinates back to their corresponding position in the original image. This test should cover different segment positions and dimensions.
[8 empty] | T253 | Integrate the centroid calculation and coordinate transformation functions into the existing image processing pipeline where segments are combined to form a complete UI element. This integration must capture the coordinates of the combined segment relative to the original image.
[8 empty] | T254 | Implement logging within both the centroid calculation and coordinate transformation functions to record the input values and the computed outputs for debugging and validation purposes.
[8 empty] | T255 | Document the functionality, inputs, and outputs of the centroid calculation and coordinate transformation functions in the project's code documentation to assist other developers in understanding and potentially modifying this functionality in the future.
|  |  |  | S038 | Output Coordinates for UI Interaction | As a Developer, I want the system to output the X, Y coordinates of the identified UI element, so that these can be used to automate interactions with the UI. | Output is in a format that can be easily used by other system components. Coordinates are consistently accurate and reliable for automated UI interactions. | T256 | Design a function in Python to calculate the X, Y coordinates of the center of an identified UI element. The function should take the dimensions and position of the UI element as inputs and return the coordinates.
[8 empty] | T257 | Implement a function to format the calculated coordinates into a structured JSON format. Ensure that the JSON object includes key-value pairs for X and Y coordinates, and is readily consumable by other system components.
[8 empty] | T258 | Develop unit tests to validate the accuracy and reliability of the coordinate calculation function. Tests should cover a variety of scenarios to ensure that coordinates are computed correctly across different image resolutions and segment positions.
[8 empty] | T259 | Create an integration script to connect the coordinate output function with other modules of the system, facilitating the automation of UI interactions using the calculated coordinates.
[8 empty] | T260 | Document the function specifications, including input requirements, output format, and any dependencies on other system components. This documentation should be accessible to other developers for easy integration and maintenance.
[8 empty] | T261 | Conduct a code review session with peers to validate the implementation of the coordinate calculation and output functions, ensuring alignment with the acceptance criteria and overall project standards.
[8 empty] | T262 | Setup a logging mechanism to record the operations of the coordinate calculation function. This will help in debugging and maintaining the system, ensuring that the coordinates are consistently accurate and the function is reliable.
|  |  |  | S039 | Error Handling for Image Processing | As a Developer, I want the system to handle errors during the image segmentation and combination process, so that any failures can be managed without disrupting the overall workflow. | System logs and manages errors such as failed segment combinations or coordinate calculations. System provides informative error messages for troubleshooting and maintenance. | T263 | Create a logging system to capture errors during image segmentation and combination processes. This system should log detailed information about the nature of the error, the time it occurred, and any relevant data that could help in understanding the cause of the error.
[8 empty] | T264 | Develop an error management function that detects failures in segment combinations or coordinate calculations. This function should be capable of intercepting these specific errors and handling them in a way that maintains system stability and continuity.
[8 empty] | T265 | Implement a notification mechanism within the error management function that sends alerts or messages to developers or system administrators when critical errors occur. These notifications should include context-rich information to facilitate quick troubleshooting.
[8 empty] | T266 | Design an error-response system that provides informative and actionable error messages back to the end-users or system components that initiated the processes. These messages should guide the user or system on potential ways to mitigate or correct the issue.
[8 empty] | T267 | Incorporate automated retry logic for failed image segment combinations or coordinate calculations. The system should be able to attempt retrying the operation a configurable number of times before logging a final error state.
[8 empty] | T268 | Set up a development environment for testing the error handling mechanisms under various failure scenarios to ensure that the system responds appropriately. This includes simulating different types of failures in image segmentation and coordinate calculation.
[8 empty] | T269 | Document all error handling procedures and typical errors encountered within the system. This documentation should include troubleshooting steps and mitigation strategies to be used by development and maintenance teams.
| E007 | Local Data Management | Manage all data flow and temporary storage of information locally using JSON files, ensuring efficient data handling without external database dependencies. | S040 | Create Local JSON File Storage | As a Developer, I want to implement local JSON file storage so that the application can handle data flow and temporary information storage without relying on external databases. | JSON file creation must be triggered by data input events. JSON files must be stored in a designated local directory. Data read/write operations must be verified through unit tests. | T270 | Design a local storage system for JSON files, ensuring that file generation is triggered by specific data input events from the application. Define event types and data thresholds that will initiate file creation.
[8 empty] | T271 | Implement a file management system in Python that handles the creation, storage, and management of JSON files. This should include specifying the directory structure in a configuration file to ensure that all JSON files are stored in a designated local directory.
[8 empty] | T272 | Develop a data writing module that serializes application data into JSON format and writes it to the local file system. Ensure that the module handles exceptions and errors gracefully, such as handling issues with file permissions or disk space limitations.
[8 empty] | T273 | Create a data reading module that deserializes data from JSON files back into application-specific data structures. This module must ensure data integrity and handle potential exceptions, such as corruption of JSON file format.
[8 empty] | T274 | Set up unit tests to verify read and write operations. Tests should cover scenarios including successful file creation and retrieval, handling of erroneous data inputs, and file access permissions. Ensure tests validate the integrity of the data read from and written to the files.
[8 empty] | T275 | Implement logging for all file operations, capturing both successful operations and issues encountered during file handling. Ensure logs are sufficient for troubleshooting and provide insights into the operations performed by the file management system.
|  |  |  | S041 | Develop Data Serialization Module | As a Developer, I want to develop a data serialization module so that data structures used within the application can be easily converted to and from JSON format. | The module must support serialization of complex data structures. Ensure the integrity of the data during serialization and deserialization. Include error handling for serialization failures. | T276 | Define the data structures to be serialized, considering complex nested structures that represent the application's data models.
[8 empty] | T277 | Research and select a suitable Python library for serialization that supports the necessary complexity and types used within the application's data structures.
[8 empty] | T278 | Implement a serialization function using the chosen library, ensuring that it can serialize all defined data structures into JSON format.
[8 empty] | T279 | Develop a corresponding deserialization function that can accurately reconstruct the original data structures from the JSON strings produced by the serialization function.
[8 empty] | T280 | Create unit tests to verify that serialization and deserialization preserve the integrity and structure of the data, including edge cases for complex nested structures.
[8 empty] | T281 | Implement error handling within the serialization and deserialization functions to manage and log exceptions such as type errors or serialization failures.
[8 empty] | T282 | Document the usage of the serialization module, including examples of data structures it supports and how to handle common errors during serialization and deserialization.
|  |  |  | S042 | Implement Data Loading and Saving Functions | As a Developer, I want to implement functions to load and save JSON data so that the application can persist state between sessions without external dependencies. | Data must be loadable from and savable to JSON files on demand. Ensure data consistency and integrity during load/save operations. Performance tests should confirm that operations are completed within acceptable time limits. | T283 | Design and implement a function `load_json_file(filepath)` that takes a file path as input and returns the data from the JSON file. Include error handling to manage cases where the file does not exist or the data format is corrupted.
[8 empty] | T284 | Design and implement a function `save_json_file(data, filepath)` where `data` is the content to be saved and `filepath` is the target file path. The function should overwrite existing files or create a new one if it does not exist. Include error handling for file write permissions and disk space issues.
[8 empty] | T285 | Implement data validation checks within both `load_json_file` and `save_json_file` functions to ensure the integrity of the data. Use JSON schema validation to check data types and required fields.
[8 empty] | T286 | Create unit tests for both `load_json_file` and `save_json_file` functions. Test for normal operation, error handling, and data validation using a variety of JSON input scenarios.
[8 empty] | T287 | Conduct performance testing to measure the execution time of both `load_json_file` and `save_json_file` under various conditions, such as different file sizes and system load levels. Ensure performance is within acceptable limits as defined in the project requirements.
[8 empty] | T288 | Document the usage of `load_json_file` and `save_json_file` functions, including examples of how to handle different outcomes and errors. Make sure the documentation is accessible to other developers working on the project.
|  |  |  | S043 | Create Data Integrity Checks | As a Developer, I want to create integrity checks for data so that the correctness of the data stored in JSON files can be assured. | Automated checks to validate data against predefined schemas. Logs and alerts for any data integrity issues detected. Recovery options should be available for corrupted data scenarios. | T289 | Design and implement a JSON schema that defines the structure and rules for the data to be stored, ensuring it meets the requirements of the application and covers all necessary fields and data types.
[8 empty] | T290 | Develop a function to validate JSON data against the predefined schema. This function should take JSON data as input and return a boolean indicating whether the data adheres to the schema, along with detailed error messages if validation fails.
[8 empty] | T291 | Create a logging mechanism that captures all data integrity issues identified during JSON validation. Ensure that logs include timestamp, type of error, and a snippet of the invalid data for easier debugging and traceability.
[8 empty] | T292 | Implement an alert system that notifies the development team of any critical data integrity issues detected during routine checks, using the logging mechanism as the source for alerts.
[8 empty] | T293 | Develop a recovery module that can be triggered when corrupted data scenarios are detected. This module should include strategies such as restoring data from backups, retrying data processing, or requesting re-submission of data from the source.
[8 empty] | T294 | Integrate the JSON validation function into the existing data handling processes so that every piece of JSON data is automatically validated at the point of creation or modification before being stored locally.
[8 empty] | T295 | Conduct unit testing for each component (schema validation, logging, alerting, recovery) to ensure that each function performs as expected under various scenarios.
[8 empty] | T296 | Set up a scheduled task that runs at regular intervals to perform integrity checks on all stored JSON files, utilizing the validation function and logging any anomalies detected.
|  |  |  | S044 | Setup Local Cache Using JSON | As a Developer, I want to set up a local caching mechanism using JSON files so that frequently accessed data can be quickly retrieved, enhancing the performance of the application. | Cache must be implemented using JSON files for temporary data storage. Cache hit and miss ratios should be tracked and optimized. Cache should be cleared or updated based on data access patterns. | T297 | Design the schema for the JSON cache file that includes identifier keys and relevant data attributes to support quick retrieval and update operations.
[8 empty] | T298 | Develop a Python function to initialize the cache by creating the JSON file if it does not exist and loading it into memory when the application starts.
[8 empty] | T299 | Implement a Python function to write data into the JSON cache file, ensuring that data is serialized in a manner that supports quick access and update.
[8 empty] | T300 | Create a Python function to read data from the JSON cache file, optimizing for performance to reduce read times.
[8 empty] | T301 | Develop mechanisms within the caching functions to track the number of cache hits and misses, storing these values in a separate metadata section of the JSON file.
[8 empty] | T302 | Implement cache eviction logic based on LRU (Least Recently Used) strategy to automatically clear older or less frequently accessed data when updating the cache.
[8 empty] | T303 | Set up a monitoring script in Python that regularly checks and optimizes the cache file for performance, such as defragmenting the JSON structure or rebalancing the cached data.
[8 empty] | T304 | Write unit tests for each of the cache functions to ensure they handle data correctly, efficiently manage space, and perform within acceptable time limits.
[8 empty] | T305 | Document the caching mechanism including the JSON schema, function descriptions, and usage examples to help in future maintenance or enhancements.
| E008 | Integration with OpenAI API | Incorporate OpenAI API to enhance the image processing capabilities, focusing on accurate UI element identification. | S045 | Image Upload and Base64 Conversion | As a Developer, I want to upload screenshots and convert them to Base64 format so that they can be processed by our Python tool. | User can upload an image through a simple function call. The uploaded image is automatically converted to Base64 format. The function returns a confirmation that the file has been uploaded and converted. | T306 | Design a Python function named 'upload_and_convert_image' that takes a file path as input and is responsible for reading the image from the supplied path.
[8 empty] | T307 | Implement reading of the image file in the 'upload_and_convert_image' function using Python's built-in 'open' function to handle file operations securely.
[8 empty] | T308 | Integrate image conversion within the 'upload_and_convert_image' function using the Python Imaging Library (PIL) to load the image and convert it into a Base64 encoded string.
[8 empty] | T309 | Ensure the 'upload_and_convert_image' function checks the integrity of the image file ensuring it is a valid image format (JPEG, PNG) before proceeding with the conversion.
[8 empty] | T310 | Develop functionality within 'upload_and_convert_image' to return a confirmation response that includes the Base64 string of the image and a success message indicating the image has been successfully uploaded and converted.
[8 empty] | T311 | Write unit tests for 'upload_and_convert_image' to validate that the function correctly handles different image formats, returns the appropriate Base64 encoded content, and confirms successful operation through the response message.
[8 empty] | T312 | Setup a simple API endpoint using a framework like Flask to expose the 'upload_and_convert_image' function, allowing images to be uploaded via an HTTP POST request where the file is included in the request body.
[8 empty] | T313 | Create documentation for the 'upload_and_convert_image' function and its API endpoint, specifying the expected input, the output format, and example usage including curl commands for interacting with the endpoint.
|  |  |  | S046 | Image Size and Resolution Determination | As a Developer, I want the system to automatically determine and record the size and resolution of the uploaded image so that accurate processing can be performed. | Upon image upload, the system determines the image's resolution. The resolution details are stored and accessible for further processing steps. | T314 | Create a Python function 'upload_image' that takes an image file as input, automatically converts it to a Base64 encoded format if not already, and uploads it to the system.
[8 empty] | T315 | Develop a Python function 'determine_resolution' that accepts an uploaded image as input and calculates its resolution (width x height in pixels).
[8 empty] | T316 | Implement a mechanism within 'determine_resolution' to check the integrity and format of the uploaded image before processing to ensure it is a valid image file.
[8 empty] | T317 | Enhance the 'determine_resolution' function to extract and record additional image details such as file size and image type (JPEG, PNG, etc.).
[8 empty] | T318 | Create a local or in-memory database storage system to store the resolution details and other relevant image metadata securely and ensure that they can be accessed efficiently for further processing.
[8 empty] | T319 | Integrate error handling in the image upload and resolution determination processes to manage and log errors such as unsupported file types or corrupted image files.
[8 empty] | T320 | Develop unit tests for 'upload_image' and 'determine_resolution' functions to verify that they handle various image formats correctly and store the resolution details accurately.
[8 empty] | T321 | Document the API endpoints or method usage for 'upload_image' and 'determine_resolution' including example requests and responses to ensure clear understanding and usability for further development stages.
|  |  |  | S047 | Image Segmentation | As a Developer, I want the system to segment the uploaded image into manageable parts while keeping track of their positions relative to the original image so that detailed analysis can be performed on smaller areas. | The system segments the image into predefined sizes or based on specific conditions. Each segment’s position relative to the original image is recorded. Functionality to handle overlapping segments for complete coverage without data loss. | T322 | Develop a function to validate and accept an uploaded image. The function should check for the correct image format and size, ensuring it adheres to system requirements.
[8 empty] | T323 | Create a function to convert the uploaded image into a manageable internal format if necessary, such as a raw pixel array or similar structure that simplifies manipulation.
[8 empty] | T324 | Implement a segmentation algorithm that can divide the image into predefined sizes or dynamically based on specific conditions such as image content or resolution.
[8 empty] | T325 | Design data structures to store information about each image segment, including metadata such as the segment's position relative to the original image and its dimensions.
[8 empty] | T326 | Develop logic within the segmentation function to handle edge cases where segments might overlap, ensuring that all parts of the image are covered without data repetition or loss.
[8 empty] | T327 | Integrate the segmentation functionality with the existing image processing workflow, ensuring that segmented data can be easily passed to subsequent processing stages.
[8 empty] | T328 | Create unit tests to verify that the image segmentation correctly divides the image according to the predefined criteria and accurately records segment positions.
[8 empty] | T329 | Develop a method to visually or programmatically verify the non-overlapping and complete coverage of the segmented image, potentially using a debug overlay or logging.
|  |  |  | S048 | Integration with OpenAI API for Element Identification | As a Developer, I want to integrate the OpenAI API to analyze each image segment to check for the presence of specific UI elements as per given instructions so that we can automate interactions with UI components. | Each image segment is sent to OpenAI's API with appropriate parameters. The API's response is captured and processed to ascertain the presence of the UI element. Handle API errors and exceptions smoothly. | T330 | Develop a function to segment the uploaded image into smaller parts. The function should take a Base64 encoded image as input and output a list of image segments along with their metadata including their relative positions.
[8 empty] | T331 | Create a function to convert each image segment into the format required by OpenAI API, including any necessary parameters such as image format, size, and any other API-specific requirements.
[8 empty] | T332 | Implement a function to asynchronously send each formatted image segment to the OpenAI API. This function should handle the API request and manage the return of data asynchronously to enhance performance.
[8 empty] | T333 | Develop a function to process the responses from the OpenAI API. It should parse the API response to determine the presence of the specified UI elements and extract relevant data such as element type, confidence score, and segment identifier.
[8 empty] | T334 | Implement error handling within the API interaction function to manage and log any API errors or exceptions. This should include retry logic for failed requests, error logging for debugging, and fallback procedures for critical failures.
[8 empty] | T335 | Create a centralized logging mechanism for capturing both successful and failed interactions with the OpenAI API, including timestamps, request and response data, and error messages if applicable.
[8 empty] | T336 | Write unit tests for each function developed, ensuring that they handle expected and edge case scenarios correctly. Tests should cover the successful operation of segmenting images, sending data to the API, receiving and processing API responses, and error handling.
|  |  |  | S049 | Partial Element Handling and Reconstruction | As a Developer, I want the system to identify when a UI element is only partially present in an image segment and automatically integrate adjacent segments to form a complete view of the UI element so that accurate location can be tracked. | The system detects partial UI elements and identifies adjacent segments to consider for a complete view. Adjacent segments are processed and merged if they contain the continuation of the UI element. The reconstructed segment accurately represents the complete UI element. | T337 | Develop a function `detect_partial_ui_elements` that scans an image segment to determine if a UI element is only partially present. This function should return a list of segments that need further analysis or combination. Inputs: Image segment data. Outputs: List of segment identifiers with partial UI elements.
[8 empty] | T338 | Create a function `identify_adjacent_segments` that identifies and retrieves adjacent image segments that are likely to contain the continuation of the partial UI elements detected. Inputs: Segment identifiers. Outputs: List of adjacent segment data.
[8 empty] | T339 | Develop a function `merge_segments` to process and combine identified adjacent segments into a single segment, ensuring that the UI elements are correctly aligned and represented. Inputs: List of adjacent segment data. Outputs: Merged segment representation.
[8 empty] | T340 | Implement a function `validate_segment_integrity` to check that the reconstructed segment accurately represents the complete UI element. The function should compare the merged segment against predefined UI templates or criteria. Inputs: Merged segment data. Outputs: Validation result (boolean).
[8 empty] | T341 | Integrate the functions into an existing image processing pipeline where each segment of the image is analyzed. Ensure the pipeline handles the flow from detection of partial UI elements to the merging and validation phases efficiently. Inputs: Full image data divided into segments. Outputs: Processed image with UI elements identified and merged appropriately.
[8 empty] | T342 | Design a logging mechanism to record the processing steps and outcomes at each stage of detecting, merging, and validating segments. This should include any errors or mismatches encountered during the processing. Inputs: Process steps and data. Outputs: Log entries.
[8 empty] | T343 | Set up unit tests for each function (`detect_partial_ui_elements`, `identify_adjacent_segments`, `merge_segments`, `validate_segment_integrity`) to ensure they perform as expected under various conditions. Inputs: Sample image data and test cases. Outputs: Test results.
|  |  |  | S050 | Coordinate Calculation of UI Elements | As a Developer, I want the system to calculate the X, Y coordinates of the center of the UI element from the processed image so that these coordinates can be used to automate clicks or interactions. | Upon successful identification of a UI element, the system calculates its center's X, Y coordinates relative to the original image. Coordinates are accurate and replicable on subsequent operations. Coordinates are stored and accessible for further automation tasks. | T344 | Create a function to identify UI elements within an image. This function receives the image data and uses the OpenAI API to detect UI elements, returning their bounding boxes and any associated metadata.
[8 empty] | T345 | Develop a function to calculate the X, Y coordinates of the center of each identified UI element. The function must take the bounding box data as input and compute the center point, ensuring the coordinates are relative to the original image dimensions.
[8 empty] | T346 | Implement a mechanism to store the calculated coordinates in a structured data format, such as JSON, which includes the coordinates along with identifiers for the respective UI elements. Ensure the storage system allows for easy access and retrieval of these coordinates for further automation tasks.
[8 empty] | T347 | Set up unit tests to validate the accuracy and replicability of the coordinate calculations. Tests should check that the coordinates correctly represent the center of the UI elements and are consistent across multiple operations.
[8 empty] | T348 | Integrate the coordinate calculation functionality with the existing image processing pipeline to ensure that coordinates are calculated immediately after a UI element is successfully identified.
[8 empty] | T349 | Document the APIs and functions developed for calculating and storing coordinates, including example usage and expected input and output formats. Ensure the documentation is clear and accessible to other developers.
[8 empty] | T350 | Create an error handling mechanism for the coordinate calculation process. This should include logging errors, retrying the calculation if possible, and failing gracefully if critical errors occur.
|  |  |  | S051 | Output Generation for Coordinates | As a Developer, I want the system to output the determined coordinates in a structured format so that they can be easily used in other parts of our system for automating tasks. | Coordinates are outputted in a JSON format. The output file is saved locally and can be accessed by other system components. Ensure that the output generation is error-free and reliably consistent. | T351 | Design a function `generate_coordinates_output` that receives coordinates as input and returns a JSON structured output containing the coordinates. The function should ensure the output is formatted with clear labeling of the X and Y values.
[8 empty] | T352 | Implement the function `generate_coordinates_output` to create a JSON file with the coordinates data. The function should include error checking to confirm that the input coordinates are formatted correctly before proceeding to file creation.
[8 empty] | T353 | Develop functionality within `generate_coordinates_output` to save the generated JSON file to a specified local directory. This directory should be configurable, allowing system administrators to change the path as needed.
[8 empty] | T354 | Incorporate error handling mechanisms in the `generate_coordinates_output` function to ensure the system captures and logs any issues during the JSON file creation or saving processes. Provide meaningful error messages that can aid in troubleshooting.
[8 empty] | T355 | Create unit tests for `generate_coordinates_output` to validate that the function correctly generates a JSON output, saves the file locally, and handles potential input and file system errors gracefully. Tests should cover various scenarios including incorrect input formats and file system permissions issues.
[8 empty] | T356 | Document the `generate_coordinates_output` function within the project's code repository. Documentation should include details on the function's purpose, input parameters, output format, and examples of how to use the function within the larger system.
| E009 | Performance Optimization | Initially ensure functionality, with subsequent optimization of processing speed and responsiveness, including considerations for future use of CPU/GPU resources. | S052 | Base64 Image Upload | As a Developer, I want to upload screenshots in Base64 format so that the system can process images for UI element identification. | The system accepts images in Base64 format. Uploaded images are validated for format integrity and size. A confirmation is returned upon successful upload. | T357 | Implement a function to accept image uploads through an HTTP POST request. This function should specifically handle images encoded in Base64 format. Ensure that the function is capable of receiving and parsing Base64 encoded data from the request body.
[8 empty] | T358 | Develop logic within the upload function to validate the format of the Base64 encoded image. This includes checking if the Base64 string is properly padded, contains only valid Base64 characters, and converts successfully to binary format without errors.
[8 empty] | T359 | Create functionality to calculate and validate the size of the uploaded image after decoding from Base64 to ensure it does not exceed system limits for processing. This should include both the pixel dimensions of the image and the file size in bytes.
[8 empty] | T360 | Implement a response mechanism within the image upload function to return a confirmation message to the user upon successful upload and validation of the image. This should include a success status code and a message indicating that the image has been accepted and is ready for further processing.
[8 empty] | T361 | Write unit tests for the image upload functionality to ensure that the endpoint correctly handles various scenarios such as valid and invalid Base64 formats, images that are too large, and correct response messaging. Include tests that simulate network requests to the image upload endpoint.
[8 empty] | T362 | Set up logging for the image upload process to record details about the upload attempts, including successful validations and any errors or exceptions encountered. This should help in future debugging and maintaining the system.
|  |  |  | S053 | Image Resolution Detection | As a Developer, I want the system to automatically determine and record the resolution of uploaded images so that the image processing can be accurately calibrated. | The system detects and logs the resolution of each uploaded image. Resolution data is used to adjust image processing parameters. The system handles and logs errors when image resolution is undetectable. | T363 | Design and implement a function `detect_image_resolution(image_data)` that takes Base64 encoded image data as input, decodes it, and detects the image resolution. The output should be a tuple containing the width and height of the image in pixels.
[8 empty] | T364 | Implement a logging mechanism within `detect_image_resolution(image_data)` to record the resolution of each uploaded image. Ensure logs are structured and stored persistently to facilitate easy access and analysis.
[8 empty] | T365 | Create a configuration file or a settings module to adjust image processing parameters dynamically based on the resolution data obtained. This configuration should be easily accessible and modifiable by the system administrators or developers.
[8 empty] | T366 | Develop a robust error handling framework within the `detect_image_resolution(image_data)` function to manage and log errors when the image resolution cannot be detected. This should include specific error messages that detail the nature of the error and potential causes.
[8 empty] | T367 | Integrate the `detect_image_resolution(image_data)` function with the main image processing pipeline, ensuring that the function is called immediately after the image upload and Base64 decoding steps.
[8 empty] | T368 | Implement unit tests for `detect_image_resolution(image_data)` to cover various scenarios including valid images in different formats, corrupted image data, and unsupported image formats. Ensure each test verifies that the correct resolution is detected or appropriate errors are handled.
|  |  |  | S054 | Image Segmentation | As a Developer, I want the system to segment uploaded images into manageable parts while retaining their positional data so that detailed analysis can be performed on smaller sections. | Uploaded images are segmented into predefined sizes. Each segment retains metadata about its position relative to the original image. The system ensures all parts of the image are covered without overlaps or missing sections. | T369 | Design a function `upload_image` that takes a Base64 encoded image as input, decodes it, and verifies the integrity before processing. The function should log the successful upload and decoding of the image.
[8 empty] | T370 | Implement a function `segment_image` that takes the decoded image from `upload_image` as input and segments it into predefined sizes. The function should ensure that the entire image is covered by the segments without any overlaps or missing sections.
[8 empty] | T371 | Develop a method within `segment_image` to calculate and attach metadata to each segment detailing its position relative to the original image. The metadata should include coordinates or a reference system that marks the segment's location.
[8 empty] | T372 | Create a data structure to store the segments along with their metadata. This structure should allow easy access and manipulation of the segment data for further processing.
[8 empty] | T373 | Set up error handling within the `segment_image` function to handle and log errors related to image segmentation, such as calculation errors in the determination of segment boundaries or metadata assignment.
[8 empty] | T374 | Write unit tests for `upload_image` and `segment_image` functions to ensure they handle different types of input correctly, manage errors gracefully, and perform their operations within the specified requirements.
|  |  |  | S055 | UI Element Identification via OpenAI API | As a Developer, I want to integrate the OpenAI API to identify specific UI elements in image segments so that the system can locate these elements accurately. | The system sends image segments to the OpenAI API with relevant instructions. UI elements are identified within the segments with a confidence score. API responses are logged and errors are handled gracefully. | T375 | Create a function to segment the uploaded image into smaller parts. This function takes an image as input and returns a list of image segments along with metadata about their positions relative to the original image.
[8 empty] | T376 | Develop a module to encode each image segment into Base64 format before sending it to the OpenAI API. This module should accept an image segment as input and return a Base64 encoded string.
[8 empty] | T377 | Implement a function to interface with the OpenAI API. This function should take the Base64 encoded image segments and relevant instructions as input and return the API's raw response.
[8 empty] | T378 | Create a utility to parse the OpenAI API response. This should input the raw API response and output structured data including the presence of UI elements and their confidence scores.
[8 empty] | T379 | Set up a logging system to record details of the API requests and responses. This system should log each API request and response, and should also record any errors encountered during the API interaction.
[8 empty] | T380 | Design an error handling mechanism for API interactions. This should include retries for failed requests and graceful handling of non-successful API responses. The system should also log detailed error information for troubleshooting.
|  |  |  | S056 | Coordinate Calculation of UI Elements | As a Developer, I want the system to calculate the X, Y coordinates of the identified UI elements relative to the original image so that accurate interaction points can be provided. | For each identified UI element, the system calculates its center X, Y coordinates. Coordinates are calculated relative to the original image size and resolution. Calculated coordinates are logged and can be reviewed. | T381 | Design a function to identify UI elements within an image. The function will accept an image segment and return the identified UI elements.
[8 empty] | T382 | Implement a function to calculate the center X, Y coordinates of each identified UI element. This function will take the dimensions and position of the UI element within the image segment as inputs and output the coordinates relative to the original image.
[8 empty] | T383 | Develop a logging system to record the X, Y coordinates of identified UI elements. Ensure the logging format allows for easy review and auditing.
[8 empty] | T384 | Create unit tests to verify that the coordinate calculation function accurately computes the center coordinates based on various input scenarios and image resolutions.
[8 empty] | T385 | Integrate the coordinate calculation function with the existing image processing workflow to ensure that coordinates are computed as part of the standard processing pipeline once UI elements are identified.
[8 empty] | T386 | Implement error handling within the coordinate calculation function to manage and log exceptions, such as invalid input data or calculation errors, ensuring the system's stability and reliability.
|  |  |  | S057 | Performance Optimization | As a Developer, I want to monitor and optimize the processing speed and responsiveness of the system so that image processing can scale with increased demand. | Benchmark current processing times for image uploads and segment analysis. Implement performance enhancements such as threading or GPU utilization. Re-evaluate performance after enhancements to ensure significant improvements. | T387 | Develop a benchmarking tool to measure current processing times for image uploads and segment analysis. The tool should accurately measure time taken for each process and output results in a structured format for analysis.
[8 empty] | T388 | Implement multi-threading in the image processing pipeline to handle multiple image uploads and segmentations concurrently. Ensure that the implementation does not affect the stability of the system.
[8 empty] | T389 | Explore and integrate GPU utilization for image processing tasks to enhance performance. This includes modifying existing algorithms to run on GPU architectures and ensuring compatibility with the current system setup.
[8 empty] | T390 | Create a structured report format to log and compare the performance metrics pre and post performance enhancements. This report should include parameters like processing time, system throughput, and resource utilization.
[8 empty] | T391 | Conduct a detailed analysis after implementing performance enhancements to validate improvements against the benchmarks initially set. This should include repeated runs to ensure consistency and the collection of statistical data to support findings.
[8 empty] | T392 | Document all changes made during the optimization process including code modifications, configurations, and setup required for threading and GPU utilization. Ensure this documentation is accessible to other team members for review and further modifications.
|  |  |  | S058 | Error Handling for Partial UI Elements | As a Developer, I want the system to effectively handle cases where UI elements are only partially present in image segments so that a complete and accurate identification can still be made. | The system detects partial UI elements and attempts to locate adjacent segments to complete the view. A composite segment is created when necessary to fully capture the UI element. The system logs these incidents and how they were resolved. | T393 | Design and implement a function 'detect_partial_ui_elements' that scans image segments for UI elements that are not fully captured. The function should use image processing techniques to recognize patterns indicative of UI elements and flag segments that contain partial elements.
[8 empty] | T394 | Develop a function 'locate_adjacent_segments' that takes as input the coordinates of the segments containing partial UI elements. This function should return a list of adjacent segments that need to be considered to form a complete view of the UI element.
[8 empty] | T395 | Create a function 'create_composite_segment' that combines the flagged partial segment with identified adjacent segments. The function should ensure that the composite segment is correctly aligned and maintains the integrity of the image data.
[8 empty] | T396 | Implement logging within each of the above functions to record the process of detecting partial elements, locating adjacent segments, and creating composite segments. The logs should include timestamps, function names, input parameters, and outcomes to assist in debugging and maintenance.
[8 empty] | T397 | Design and implement a validation mechanism to review the accuracy of the composite segment compared to predefined criteria or mockups to ensure the composite accurately represents the complete UI element.
[8 empty] | T398 | Integrate the functions into the main image processing workflow where image segments are initially processed. This integration should allow the system to automatically handle partial UI elements without manual intervention.
[8 empty] | T399 | Develop unit tests for each function to test various scenarios including cases with no partial elements, multiple partial elements, and edge cases where UI elements are split across multiple segments. Ensure that each function performs as specified under all test conditions.
|  |  |  | S059 | Local Data Management | As a Developer, I want to manage processing data locally using JSON files so that the system remains lightweight and manageable without external dependencies. | Data related to image processing tasks are stored in JSON format. JSON files are organized and accessible within the local environment. Data integrity and backup processes are implemented. | T400 | Design and implement a local storage system for JSON files that will handle data related to image processing tasks. Ensure that all data is stored in a clearly structured JSON format.
[8 empty] | T401 | Create a directory structure on the local system to organize JSON files. This structure should categorize files based on the specific image processing task they relate to, such as image upload details, segmentation results, and UI element detection outcomes.
[8 empty] | T402 | Develop functions for creating, reading, updating, and deleting JSON files. These functions must handle file I/O operations efficiently and be integrated into the main image processing workflow.
[8 empty] | T403 | Implement data integrity checks that automatically verify the format and content of JSON files against predefined schemas to ensure data consistency and correctness.
[8 empty] | T404 | Establish a backup process for the JSON files. This should include periodic snapshots of the data and mechanisms to restore data from these snapshots in case of data loss.
[8 empty] | T405 | Set up monitoring tools that log access and changes to the JSON files, providing an audit trail for data operations which can be used for troubleshooting and ensuring compliance with data handling standards.
| E010 | System Scalability | Design the system with modularity to facilitate easy scaling and performance improvements such as threading in future deployments. | S060 | Implement modular architecture | As a Developer, I want to implement a modular architecture for the image processing function so that each sub-function (image segmentation, resolution detection, UI element identification) can be developed, tested, and maintained independently. | The system is broken down into distinct modules such as image upload, segmentation, OpenAI API integration, and coordinate calculation. Each module can be deployed and tested independently. Changes in one module do not affect the functionality of others. | T406 | Design a high-level architecture diagram that outlines the separate modules such as image upload, segmentation, OpenAI API integration, and coordinate calculation. The diagram should visually separate these components, showing clear interfaces for interactions between them.
[8 empty] | T407 | Create detailed specifications for each module (image upload, segmentation, OpenAI API integration, and coordinate calculation) defining the inputs, outputs, and expected behaviors. Include API contracts for interactions between modules.
[8 empty] | T408 | Develop a prototype for the image upload module, ensuring it can receive an image, convert it to the necessary format, and pass it to the segmentation module. Use placeholder functions for downstream modules.
[8 empty] | T409 | Implement the image segmentation module to accept images from the upload module, segment them according to predefined criteria, and forward segmented data to the OpenAI API integration module. Include error handling for image format and segmentation issues.
[8 empty] | T410 | Set up the OpenAI API integration module to receive segmented images, interact with the OpenAI API to identify UI elements, and pass the data to the coordinate calculation module. Handle API response errors and retry logic.
[8 empty] | T411 | Create the coordinate calculation module to process data received from the OpenAI API module, compute the coordinates, and prepare them for output. Ensure accuracy and error handling for calculation discrepancies.
[8 empty] | T412 | Develop integration tests to verify that each module correctly interacts with its adjacent modules according to the API contracts. Include tests for data format, error handling, and boundary cases.
[8 empty] | T413 | Set up a continuous integration (CI) environment that allows for independent deployment and testing of each module. This setup should support rolling updates and rollbacks without affecting other parts of the system.
[8 empty] | T414 | Document the development setup, deployment instructions, and usage guidelines for each module to ensure they can be independently used and maintained by other developers.
[8 empty] | T415 | Conduct a review session with stakeholders to demonstrate the modular architecture and gather feedback on the deployment strategy, integration points, and independence of modules.
|  |  |  | S061 | Thread management for performance | As a Developer, I want to implement thread management capabilities so that the image processing tasks can be handled in parallel, improving the overall performance and scalability of the system. | The system utilizes multi-threading to process multiple images concurrently. There is a noticeable improvement in processing time per image. The system remains stable and responsive under the load of multiple simultaneous processing tasks. | T416 | Design a threading model for the image processing system that supports concurrent processing of multiple images. The task involves selecting an appropriate threading library and defining how threads will be managed, created, and destroyed.
[8 empty] | T417 | Implement the threading model in the image processing function. This includes writing Python code that utilizes the threading library to manage multiple threads for image uploading, segmentation, and processing tasks simultaneously.
[8 empty] | T418 | Develop a thread-safe mechanism for sharing resources among threads without causing data corruption. This includes implementing locks, semaphores, or other synchronization techniques to ensure data integrity when threads access shared data.
[8 empty] | T419 | Create a testing framework to simulate multiple image processing tasks running concurrently. This setup should help in evaluating the threading model's effectiveness and identifying potential deadlocks or race conditions.
[8 empty] | T420 | Conduct performance tests to compare processing times before and after implementing threading. This task involves setting up a benchmark system that measures the time taken to process images with and without threading, to assess the performance improvement.
[8 empty] | T421 | Perform stress testing by running the image processing system under high load conditions to ensure that the system remains stable and responsive. Monitor the system's behavior and gather metrics on CPU and memory usage during these tests.
[8 empty] | T422 | Document the threading implementation, including the threading model used, code changes made, and any configurations required for optimal performance. This documentation will assist in maintenance and further development.
[8 empty] | T423 | Review and refine the error handling mechanisms to manage exceptions in a multi-threaded environment effectively. Ensure that errors in one thread do not impact the stability of other threads or the entire system.
[8 empty] | T424 | Implement logging for thread activities to help in debugging and monitoring the system. This includes logging thread creation, execution, and termination events, as well as any anomalies detected during the processing.
|  |  |  | S062 | Dynamic error handling | As a Developer, I want to integrate dynamic error handling within each module so that any errors, especially those related to partial UI element detection, are managed gracefully without affecting the overall system performance. | The system identifies and logs errors related to image processing. The system attempts to auto-correct partial UI detections or escalates issues when necessary. Error handling does not significantly impact the performance of the system. | T425 | Design and implement an error logging mechanism that captures and stores errors related to image processing. Include metadata such as timestamp, module name, and error details.
[8 empty] | T426 | Develop a function to automatically detect partial UI element detections and log the relevant details. This function should be able to trigger a secondary analysis or escalate the error for manual review if auto-correction is not possible.
[8 empty] | T427 | Integrate the error handling mechanism within each module (image upload, segmentation, OpenAI API integration, coordinate calculation) ensuring that errors are processed in a way that does not halt or slow down the overall system performance.
[8 empty] | T428 | Create automated tests to verify that the error handling mechanism accurately identifies and logs errors without impacting system performance. Include stress tests to simulate high load scenarios.
[8 empty] | T429 | Implement performance monitoring tools to measure the impact of the error handling mechanism on the system’s processing speed and responsiveness. Set up alerts for performance degradation.
|  |  |  | S063 | Integration testing with OpenAI API | As a Developer, I want to develop and execute integration tests for the OpenAI API to ensure that the interaction between our system and the API is robust and the data exchange is accurate. | Successful API calls to OpenAI with appropriate request formats. Correct handling of API responses for various scenarios (e.g., correct identification, partial identification). The system logs all API interactions for auditing and troubleshooting purposes. | T430 | Design and implement a function in Python that constructs API requests to the OpenAI API, ensuring the request data is properly formatted according to OpenAI's specifications. The function should accept image data and other necessary parameters as inputs and return the structured request payload.
[8 empty] | T431 | Develop a function to handle API responses from OpenAI. This function should parse the JSON response, extract relevant data such as identification results, and handle different scenarios like complete or partial UI element detection. The function should return a structured object with the parsed data.
[8 empty] | T432 | Create a logging system for API interactions that records each request and response with OpenAI. The log should include timestamps, request details, response status, and any errors encountered. This system should be capable of being queried for audit and troubleshooting purposes.
[8 empty] | T433 | Integrate the request construction and response handling functions into the existing system. Ensure that these new components are interacting correctly with the rest of the system, particularly where image data is provided to the API and results are received and processed.
[8 empty] | T434 | Conduct unit tests on the API interaction functions to verify that requests are formatted correctly and responses are handled as expected. This includes tests for various scenarios like successful identification, partial identification, and error conditions.
[8 empty] | T435 | Set up an integration testing environment that simulates real interactions with the OpenAI API using test API keys. Validate the full workflow from sending the API request to processing the response and logging, ensuring that all components operate as intended under conditions that mimic production use.
|  |  |  | S064 | Performance optimization and monitoring | As a Developer, I want to implement performance optimization and monitoring tools so that I can measure the efficiency of the system and make informed decisions about potential areas for improvement, especially before scaling operations. | Implementation of performance benchmarks for each module. Regular reports on system performance including response times and resource usage. Identification of bottlenecks and performance issues with actionable insights for optimization. | T436 | Design and implement a benchmarking framework that can measure the performance of individual modules such as image upload, segmentation, OpenAI API integration, and coordinate calculation. The framework should be able to collect metrics such as execution time and resource consumption.
[8 empty] | T437 | Develop a module within the system that automatically collects and stores performance data at regular intervals. This module should gather data on response times and resource usage from the benchmarking framework and save it in a structured format such as JSON or CSV.
[8 empty] | T438 | Create a dashboard or a set of visualization tools that can display real-time performance data collected by the system. This tool should allow developers to easily monitor the operational status and performance of each module.
[8 empty] | T439 | Implement logging for all performance-related data. Ensure that logs include detailed information such as timestamps, module names, metric values, and any errors or warnings that occur during operations.
[8 empty] | T440 | Set up alerts that notify developers when performance metrics fall below a certain threshold or when anomalies are detected in the system. These alerts should provide immediate information to help identify and troubleshoot potential issues.
[8 empty] | T441 | Conduct a series of controlled load tests to simulate different levels of system usage. Assess how the system performs under varied conditions to identify bottlenecks and areas that may require optimization.
[8 empty] | T442 | Review and analyze the collected performance data to identify consistent performance issues or bottlenecks in each module. Prepare a detailed report with findings and recommend strategies for optimization based on actionable insights.
[8 empty] | T443 | Implement optimizations based on the analysis, such as improving algorithm efficiency, adjusting thread management, or upgrading hardware resources. Validate the effectiveness of these optimizations through subsequent benchmarking.